## Schedule
2010
FIRE UNIT
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | 2004-08-01 | 2004-08-01 | 2005-02-01 | 2004-08-01
Design & Development Contract Award | 2004-09-01 | 2004-09-01 | 2005-03-01 | 2004-09-01
Acquisition Increment 1
Milestone C | 2007-10-01 | 2007-10-01 | 2008-10-01 | 2007-10-01
FUE | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
IOT&E
Start | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
Complete | 2009-09-01 | 2009-09-01 | 2010-09-01 | 2009-09-01
Full Rate Production Decision | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Acquisition Increment 2
Milestone C | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Lightweight Launcher FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2011-03-01
IOT&E
Start | 2011-06-01 | 2011-06-01 | 2012-06-01 | 2011-06-01
Complete | 2011-09-01 | 2011-09-01 | 2012-09-01 | 2011-09-01
Full Rate Production Decision | 2011-11-01 | 2011-11-01 | 2012-11-01 | 2011-11-01
Acquisition Increment 3
Milestone C | 2012-11-01 | 2012-11-01 | 2013-11-01 | 2012-11-01
FUE | 2015-09-01 | 2015-09-01 | 2016-09-01 | 2015-09-01
IOT&E
Start | 2016-06-01 | 2016-06-01 | 2017-06-01 | 2016-06-01
Complete | 2016-12-01 | 2016-12-01 | 2017-12-01 | 2016-12-01
Full Rate Production Decision | 2017-03-01 | 2017-03-01 | 2018-03-01 | 2017-03-01
IOC | 2017-09-01 | 2017-09-01 | 2018-09-01 | 2017-09-01
Missile
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSU First Intercept | 2008-06-01 | 2008-06-01 | 2009-06-01 | 2010-02-01
MSU FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2014-09-01
APB Breach
2011
Fire Unit
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | 2004-08-01 | 2004-08-01 | 2005-02-01 | 2004-08-01
Design & Development Contract Award | 2004-09-01 | 2004-09-01 | 2005-03-01 | 2004-09-01
Acquisition Increment 1
Milestone C | 2007-10-01 | 2007-10-01 | 2008-10-01 | 2007-10-01
FUE | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
IOT&E
Start | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
Complete | 2009-09-01 | 2009-09-01 | 2010-09-01 | 2009-09-01
Full Rate Production Decision | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Acquisition Increment 2
Milestone C | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Lightweight Launcher FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2011-03-01
IOT&E
Start | 2011-06-01 | 2011-06-01 | 2012-06-01 | 2011-06-01
Complete | 2011-09-01 | 2011-09-01 | 2012-09-01 | 2011-09-01
Full Rate Production Decision | 2011-11-01 | 2011-11-01 | 2012-11-01 | 2011-11-01
Acquisition Increment 3
Milestone C | 2012-11-01 | 2012-11-01 | 2013-11-01 | 2012-11-01
FUE | 2015-09-01 | 2015-09-01 | 2016-09-01 | 2015-09-01
IOT&E
Start | 2016-06-01 | 2016-06-01 | 2017-06-01 | 2016-06-01
Complete | 2016-12-01 | 2016-12-01 | 2017-12-01 | 2016-12-01
Full Rate Production Decision | 2017-03-01 | 2017-03-01 | 2018-03-01 | 2017-03-01
IOC | 2017-09-01 | 2017-09-01 | 2018-09-01 | 2017-09-01
Missile
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSU First Intercept | 2008-06-01 | 2008-06-01 | 2009-06-01 | 2010-02-01
MSU FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2015-09-01
APB Breach
2012
FIRE UNIT
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | 2004-08-01 | 2004-08-01 | 2005-02-01 | 2004-08-01
Design & Development Contract Award | 2004-09-01 | 2004-09-01 | 2005-03-01 | 2004-09-01
Acquisition Increment 1
Milestone C | 2007-10-01 | 2007-10-01 | 2008-10-01 | 2007-10-01
FUE | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
IOT&E
Start | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
Complete | 2009-09-01 | 2009-09-01 | 2010-09-01 | 2009-09-01
Full Rate Production Decision | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Acquisition Increment 2
Milestone C | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Lightweight Launcher FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2011-03-01
IOT&E
Start | 2011-06-01 | 2011-06-01 | 2012-06-01 | 2011-06-01
Complete | 2011-09-01 | 2011-09-01 | 2012-09-01 | 2011-09-01
Full Rate Production Decision | 2011-11-01 | 2011-11-01 | 2012-11-01 | 2011-11-01
Acquisition Increment 3
Milestone C | 2012-11-01 | 2012-11-01 | 2013-11-01 | 2012-11-01
FUE | 2015-09-01 | 2015-09-01 | 2016-09-01 | 2015-09-01
IOT&E
Start | 2016-06-01 | 2016-06-01 | 2017-06-01 | 2016-06-01
Complete | 2016-12-01 | 2016-12-01 | 2017-12-01 | 2016-12-01
Full Rate Production Decision | 2017-03-01 | 2017-03-01 | 2018-03-01 | 2017-03-01
IOC | 2017-09-01 | 2017-09-01 | 2018-09-01 | 2017-09-01
Missile
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSU First Intercept | 2008-06-01 | 2008-06-01 | 2009-06-01 | 2010-02-01
MSU FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2015-09-01
APB Breach
2013
Fire Unit
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | 2004-08-01 | 2004-08-01 | 2005-02-01 | 2004-08-01
Design & Development Contract Award | 2004-09-01 | 2004-09-01 | 2005-03-01 | 2004-09-01
Acquisition Increment 1
Milestone C | 2007-10-01 | 2007-10-01 | 2008-10-01 | 2007-10-01
FUE | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
IOT&E
Start | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
Complete | 2009-09-01 | 2009-09-01 | 2010-09-01 | 2009-09-01
Full Rate Production Decision | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Acquisition Increment 2
Milestone C | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Lightweight Launcher FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2011-03-01
IOT&E
Start | 2011-06-01 | 2011-06-01 | 2012-06-01 | 2011-06-01
Complete | 2011-09-01 | 2011-09-01 | 2012-09-01 | 2011-09-01
Full Rate Production Decision | 2011-11-01 | 2011-11-01 | 2012-11-01 | 2011-11-01
Acquisition Increment 3
Milestone C | 2012-11-01 | 2012-11-01 | 2013-11-01 | 2012-11-01
FUE | 2015-09-01 | 2015-09-01 | 2016-09-01 | 2015-09-01
IOT&E
Start | 2016-06-01 | 2016-06-01 | 2017-06-01 | 2016-06-01
Complete | 2016-12-01 | 2016-12-01 | 2017-12-01 | 2016-12-01
Full Rate Production Decision | 2017-03-01 | 2017-03-01 | 2018-03-01 | 2017-03-01
IOC | 2017-09-01 | 2017-09-01 | 2018-09-01 | 2017-09-01
Missile
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSU First Intercept | 2008-06-01 | 2008-06-01 | 2009-06-01 | 2010-02-01
MSU FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2015-09-01