## Schedule
2011
| Start |  | End
Events | Quarter | Year | Quarter | Year
Prime Contract Proposal Review/Negotiations | 3 | 2010 | 3 | 2011
Contract Award | 3 | 2011 | 3 | 2011
Design, Development and Demonstration Phase | 3 | 2011 | 1 | 2015
Production Phase | 2 | 2015 | 4 | 2016
2012 - USAF
| Start |  | End
Events | Quarter | Year | Quarter | Year
Design/Development | 2 | 2012 | 2 | 2012
Flight Test | 3 | 2012 | 2 | 2016
Aircraft Delivery | 3 | 2015 | 1 | 2016
Aircraft Delivery | 2 | 2016 | 4 | 2016
Ground Station Delivery | 4 | 2015 | 2 | 2017
2012 - Defense Wide
| Start |  | End
Events | Quarter | Year | Quarter | Year
Contract Award | 3 | 2011 | 3 | 2011
Design, Development and Demonstration Phase | 3 | 2011 | 1 | 2015
Production Phase | 2 | 2015 | 4 | 2016
2013
| Start |  | End
Events | Quarter | Year | Quarter | Year
Contract Award | 3 | 2012 | 3 | 2012
IOC | 1 | 2017 | 1 | 2017
FOC | 3 | 2017 | 3 | 2017
Flight Test | 4 | 2015 | 3 | 2016
Aircraft Delivery | 4 | 2016 | 2 | 2017
Ground Station Delivery | 4 | 2016 | 3 | 2017
Design and Development Maritime Mode | 3 | 2012 | 3 | 2015
Test and Evaluation Support | 1 | 2012 | 3 | 2017
Tech Support | 1 | 2012 | 4 | 2018
2014
2015
| Start |  | End
Events | Quarter | Year | Quarter | Year
IOC | 1 | 2017 | 1 | 2017
FOC | 3 | 2017 | 3 | 2017
Design and Development - AGS | 1 | 2014 | 1 | 2017
Design and Development - Maritime Mode | 1 | 2014 | 3 | 2015
Test and Evaluation Support | 1 | 2014 | 3 | 2017
Flight Test | 3 | 2015 | 3 | 2016
Tech Support | 1 | 2014 | 4 | 2017
Aircraft Delivery | 4 | 2016 | 2 | 2017
Ground Station Delivery | 4 | 2016 | 3 | 2017