## Table 1
F-35 Aircraft
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -426.0
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and
extended program from FY 2037 to FY 2038 (Air Force) (Schedule) 0.0 +158.3
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and
extended program from FY 2032 to FY 2033 (Navy) (Schedule) 0.0 +880.8
Adjustment for current and prior escalation. (Estimating) +160.6 +167.1 Revised estimate of subcontractor cost due to the incorporation of the latest actuals
from early LRIP lots (Air Force) (Estimating) -516.3 -759.5
Revised estimate of subcontractor cost due to the incorporation of the latest actuals
from early LRIP lots (Navy) (Estimating) -189.1 -347.0
Revised estimate of Airframe cost due to the incorporation of the latest actuals from
early LRIP lots (Air Force) (Estimating) +899.5 +1323.5
Revised estimate of Airframe cost due to the incorporation of the latest actuals from
early LRIP lots (Navy) (Estimating) -379.6 -695.7
Increase due to the incorporation of latest Prime and subcontractor Labor Rates and
exchange rates (Air Force) (Estimating) +2386.5 +3512.6
Increase due to the incorporation of latest Prime and subcontractor Labor Rates and
exchange rates (Navy) (Estimating) +854.2 +1563.8
Increase due to slower International Partner (IP) procurement quantity profile (Air Force)
(Estimating) +566.1 +832.9
Increase due to slower IP procurement quantity profile (Navy) (Estimating) | 104.4 |  | 191.4
Updated methodologies, material costs, and learning curves (Air Force) (Estimating) | -1381 |  | -2032.3
Updated methodologies, material costs, and learning curves (Navy) (Estimating) | 84.8 |  | 155.7
Adjustment for current and prior escalation. (Support) | 44.3 |  | 46.7
Decrease in Other Support due to maturation of technical baseline, definition of
customer requirements, and further definition of Service beddown plans (Air Force) (Support) | -191.4 |  |  | -531.5
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Navy) | -724.6 |  |  | -943.8
(Support)
Increase in Initial Spares due to revised estimate of required risk funding (Air Force)
(Support) +153.8 +551.6
Increase in Initial Spares due to revised estimate of required risk funding (Navy)
(Support) -1.2 +170.0
Procurement Subtotal +1871.0 +3818.6
MILCON |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -14.4
Adjustment for current and prior escalation. (Estimating) |  | 8.6 | 9.1
Increase due to revised estimate of MILCON requirements (Air Force) (Estimating) |  | 23.1 | 64.4
Decrease due to revised estimate of MILCON requirements (Navy) (Estimating) |  | -227.6 | -238.3
MILCON Subtotal |  | -195.9 | -179.2
F-35 Engine
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -11.7
Adjustment for current and prior escalation. (Estimating) +8.7 +8.9 Realignment of costs between Aircraft subprogram and Engine subprogram (Air Force)
(Estimating) +174.4 +155.0
Decrease due to realignment of program funding, Congressional Reductions, and
Actual Funding Investment (Air Force) (Estimating) -104.7 -108.4
Realignment of costs between Aircraft subprogram and Engine subprogram (Navy)
(Estimating) +21.9 +22.7
Decrease due to realignment of program funding, Congressional Reductions, and
Actual Funding Investment (Navy) (Estimating) +191.7 +208.6
Realignment of costs between Aircraft subprogram and Engine subprogram
(International) (Estimating) +30.7 +27.7
Realignment of cost between Aircraft subprogram and Engine subprogram
(International) (Estimating) +0.9 0.0
RDT&E Subtotal +323.6 +302.8
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -79.8
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and
extended program from FY 2037 to FY 2038 (Air Force) (Schedule) 0.0 +30.0
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and
extended program from FY 2032 to FY 2033 (Navy) (Schedule) 0.0 +166.1
Adjustment for current and prior escalation. (Estimating) +26.0 +27.5
Updated exchange rates (Air Force) (Estimating) +944.7 +1384.5
Updated exchange rates (Navy) (Estimating) +253.8 +350.8 Increase due to incorporation of latest actual costs from LRIP lots (Air Force)
(Estimating) +630.6 +923.8
Increase due to incorporation of latest actual costs from LRIP lots (Navy) (Estimating) +591.8 +818.0 Increase due to slower International procurement quantity profile (Air Force)
(Estimating) +57.1 +83.4
Increase due to slower International procurement quantity profile (Navy) (Estimating) Adjustment for current and prior escalation. (Support) Decrease in Other Support due to maturation of technical baseline, definition of | +13.8 +8.5 |  |  | +18.9 +8.4
customer requirements, and further definition of Service beddown plans (Air Force) (Support) | 2 |  |  | -34.6
Increase in Other Support due to maturation of technical baseline, definition of customer
requirements, and further definition of Service beddown plans (Navy) (Support) +23.4 +3.0
Increase in Initial Support due to revised estimate of required risk funding (Air Force)
(Support) +59.2 +239.6
Increase in Initial Support due to revised estimate of required risk funding (Navy)
(Support) +6.7 +79.4
Procurement Subtotal +2617.6 +4019.0