## Table 1
F-35 Aircraft
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -65.4
Adjustment for current and prior escalation. (Estimating) +26.9 +28.1
Increase due to additional scope to Initial Operational Test and Evaluation International
Program. (Estimating)
Realignment of costs between Aircraft subprogram and Engine subprogram. (Air Force) (Estimating)
Realignment of costs between Aircraft subprogram and Engine subprogram. (Navy) (Estimating)
Decrease due to realignment of program funding, Congressional reductions, and actual funding investment. (Air Force) (Estimating)
Increase due to realignment of program funding and actual funding investment. (Navy) (Estimating)
+45.0 +50.9
+18.0 +18.5
+119.4 +124.9
-4.2 -3.6
-1.7 +0.8
RDT&E Subtotal +203.4 +154.2
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -3417.6
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended
Department of the Navy program from FY 2033 to FY 2034. (Air Force) (Schedule) Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended
Department of the Navy program from FY 2033 to FY 2034. (Navy) (Schedule)
0.0 +548.1
0.0 +351.7
Adjustment for current and prior escalation. (Estimating) | 120.1 |  | 127.5
Decrease due to revised International procurement quantity profile. (Air Force) (Estimating) | -123.7 |  | -167.8
Decrease due to revised International procurement quantity profile. (Navy) (Estimating) | -83.7 |  | -96.2
Revised estimate of subcontractor cost due to the incorporation of the latest actuals from | -501.5 |  | -715.2
early LRIP lots. (Air Force) (Estimating)
Revised estimate of subcontractor cost due to the incorporation of the latest actuals from early LRIP lots. (Navy) (Estimating)
Revised estimate of Airframe cost due to the incorporation of the latest actuals from early LRIP lots. (Air Force) (Estimating)
Revised estimate of Airframe cost due to the incorporation of the latest actuals from early LRIP lots. (Navy) (Estimating)
Revised estimate of Airframe cost due to the incorporation of the latest Prime and subcontractor Labor/Exchange Rates. (Air Force) (Estimating)
Revised estimate of Airframe cost due to the incorporation of the latest Prime and subcontractor Labor/Exchange Rates. (Navy) (Estimating)
+197.8 +238.2
+2701.6 +3526.0
+333.3 +395.2
-2531.9 -3455.5
-803.0 -982.0
Adjustment for current and prior escalation. (Support) +29.6 +31.1
Decrease in Other Support due to maturation of technical baseline, definition of customer
requirements, and further definition of Service beddown plans. (Air Force) (Support)
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Navy) (Support)
Decrease in Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Air Force) (Support)
-713.0 -959.5
-414.9 -527.0
-61.1 -32.1
Decrease in Initial Spares due to maturation of technical baseline, definition of customer
requirements, and further definition of Service beddown plans. (Navy) (Support)
-887.2 -1068.0
Procurement Subtotal -2737.6 -6203.1
MILCON |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) |  | N/A | -70.4
Adjustment for current and prior escalation. (Estimating) |  | 3.1 | 3.2
Increase due to revised estimate of MILCON requirements. (Air Force) (Estimating) |  | 150 | 165.3
Increase due to revised estimate of MILCON requirements. (Navy) (Estimating) |  | 74.4 | 108
MILCON Subtotal |  | 227.5 | 206.1
F-35 Engine
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -9.5
Adjustment for current and prior escalation. (Estimating) +5.8 +6.1
Realignment of cost between Aircraft subprogram and Engine subprogram. (Air Force)
(Estimating)
Increase due to realignment of program funding and actual funding investment. (Air Force) (Estimating)
Realignment of cost between Aircraft subprogram and Engine subprogram. (Navy) (Estimating)
Increase due to realignment of program funding and actual funding investment. (Navy) (Estimating)
-18.0 -18.5
+1.1 +1.1
-119.2 -124.9
+2.1 +2.3
RDT&E Subtotal -128.2 -143.4
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -689.8
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended
Department of the Navy program from FY 2033 to FY 2034. (Air Force) (Schedule) Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended
Department of the Navy program from FY 2033 to FY 2034. (Navy) (Schedule)
0.0 +108.9
0.0 +69.3
Adjustment for current and prior escalation. (Estimating) | 16.5 |  | 17.3
Decrease due to revised International procurement quantity profile. (Air Force) (Estimating) | -36.2 |  | -59.2
Decrease due to revised International procurement quantity profile. (Navy) (Estimating) | -8.5 |  | -13.6
Revised estimate due to the incorporation of the latest actuals from early LRIP lots. (Air | -130.5 |  | -220.1
Force) (Estimating)
Revised estimate due to the incorporation of the latest actuals from early LRIP lots. (Navy) (Estimating)
-24.1 -42.2
Adjustment for current and prior escalation. (Support) +5.9 +6.4
Decrease in Other Support due to maturation of technical baseline, definition of customer
requirements, and further definition of Service beddown plans. (Air Force) (Support)
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Navy) (Support)
Decrease in Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Air Force) (Support)
Decrease in Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Navy) (Support)
-80.6 -109.1
-48.7 -61.3
-35.1 -22.4
-372.2 -447.9
Procurement Subtotal -713.5 -1463.7