## Table 1
F-35 Aircraft
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -36.7
Adjustment for current and prior escalation. (Estimating) +26.7 +27.8
Realignment of cost between the aircraft subprogram and engine subprogram (Air Force
(AF)). (Estimating)
Realignment of cost between the aircraft subprogram and engine subprogram (Navy). (Estimating)
+60.5 +64.3
-44.4 -46.2
Revised estimate for Small Business Innovation Research in FY 2015 (Navy). (Estimating) -24.1 -25.4
Revised estimate for additional operational testing requirements (AF). (Estimating) +74.3 +81.2 Revised estimate for additional operational testing requirements (Navy). (Estimating) +147.7 +161.7
Revised estimate to reflect application of new outyear inflation indices (Non- Treasury
Funds). (Estimating)
Increase due to realignment of program funding, congressional addition, and actual funding investment (AF). (Estimating)
Decrease due to realignment of program funding, congressional reductions, and actual funding investment (AF). (Estimating)
Increase due to realignment of program funding, congressional addition, and actual funding investment (Navy). (Estimating)
+1.3 +0.8
+8.6 +9.1
-0.8 -0.8
+6.7 +7.5
RDT&E Subtotal +256.5 +243.3
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1842.6
Adjustment for current and prior escalation. (Estimating) +120.5 +128.9
Stretch-out of procurement buy profile in FY 2016 to FY 2038 (Aircraft Procurement, AF
(APAF)). (Schedule)
Acceleration of procurement buy profile in FY 2016 to FY 2031 (Aircraft Procurement, Navy (APN)). (Schedule)
Revised estimate for International procurement quantity profile adjustments (APAF). (Estimating)
Revised estimate for International procurement quantity profile adjustments (APN). (Estimating)
Revised estimate of Airframe cost due to the incorporation of the latest prime and subcontractor actuals and labor/exchange rates (APAF). (Estimating)
Revised estimate of Airframe cost due to the incorporation of the latest prime and subcontractor actuals and labor/exchange rates (APN). (Estimating)
0.0 +1446.0
0.0 -958.8
-128.1 -160.6
-18.1 -23.7
+11.7 +131.1
+572.8 +676.1
Update for fact of life changes for prior years/lots 2006-2016 (APAF). (Estimating) -266.9 -291.1
Update for fact of life changes for prior years/lots 2006-2016 (APN). (Estimating) -71.4 -75.5
Decrease based on revised estimating assumptions for Block Buy and Multi-Year
Procurement (APN). (Estimating)
Decrease based on revised estimating assumptions for Block Buy and Multi-Year Procurement (APAF). (Estimating)
-733.8 -922.1
-1259.9 -1713.6
Revised estimate of non-recurring costs (APAF). (Estimating) +224.3 +254.6
Revised estimate of non-recurring costs (APN). (Estimating) +199.2 +122.8
Additional funding for Band 2/5 requirements (APAF) (Engineering) +945.2 +1313.8
Additional funding for Band 2/5 requirements (APN). (Engineering) +401.2 +513.0
Revised estimate for Other Support due to maturation of technical baseline, definition of
customer requirements, and further definition of Service beddown plans (APAF). (Support)
+1.8 +92.0
Adjustment for current and prior escalation. (Support) +25.7 +27.1
Revised estimate for Other Support due to maturation of technical baseline, definition of
customer requirements, and further definition of Service beddown plans (APN). (Support)
Revised estimate for Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (APAF). (Support)
Revised estimate for Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (APN). (Support)
-494.5 -544.4
-2480.8 -3648.8
-470.4 -664.1
Procurement Subtotal -3421.5 -6139.9
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -25.2
Adjustment for current and prior escalation. (Estimating) | 5.1 | 5.4
Revised estimate as a result of refined requirements (AF). (Estimating) | 313.1 | 361.9
Revised estimate as a result of refined requirements (AF). (Estimating) | -153.8 | -185.3
Revised estimate as a result of refined requirements ( Navy). (Estimating) | 7.6 | 9.4
MILCON Subtotal | 172 | 166.2
F-35 Engine
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -4.7
Adjustment for current and prior escalation. (Estimating) +4.3 +4.3
Realignment of cost between the engine subprogram and aircraft subprogram (AF).
(Estimating)
Realignment of cost between the engine subprogram and aircraft subprogram (Navy). (Estimating)
Decrease due to realignment of program funding, congressional reductions, and actual funding investment (AF). (Estimating)
-60.9 -64.3
+43.4 +46.2
-0.2 -0.2
RDT&E Subtotal -13.4 -18.7
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -373.1
Adjustment for current and prior escalation. (Estimating) +17.8 +19.0
Stretch-out of procurement buy profile in FY 2016 to FY 2038 (Engine Procurement, AF).
(Schedule)
Acceleration of procurement buy profile in FY 2016 to FY 2031 (Engine Procurement, Navy). (Schedule)
Revised estimate for International procurement quantity adjustments (Engine Procurement, AF). (Estimating)
Revised estimate for International procurement quantity adjustments (Engine Procurement, Navy). (Estimating)
0.0 +293.2
0.0 -194.7
-9.2 -12.5
-3.8 -5.1
Revised estimate to reflect actuals (Engine Procurement, AF). (Estimating) -1445.7 -2326.2
Revised estimate to reflect actuals (Engine Procurement, Navy). (Estimating) -330.6 -547.2
Decrease based on revised estimating assumptions for Block Buy and Multi-Year
Procurement (Engine Procurement, AF). (Estimating)
Decrease based on revised estimating assumptions for Block Buy and Multi-Year Procurement (Engine Procurement, Navy). (Estimating)
Update for fact of life changes for prior years/lots 2006-2016 (Engine Procurement, AF). (Estimating)
Update for fact of life changes for prior years/lots 2006-2016 (Engine Procurement, Navy). (Estimating)
-457.1 -643.3
-266.8 -343.0
-47.9 -52.1
-127.0 -138.3
Adjustment for current and prior escalation. (Support) +4.8 +5.0
Revised estimate for Other Support due to maturation of technical baseline, definition of
customer requirements, and further definition of Service beddown plans (Engine Procurement, AF). (Support)
Revised estimate for Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Engine Procurement, Navy). (Support)
Revised estimate for Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Engine Procurement, AF). (Support)
-17.7 -11.6
-85.3 -96.7
-1143.5 -1680.7
Revised estimate for Initial Spares due to maturation of technical baseline, definition of -166.3 -236.3
customer requirements, and further definition of Service beddown plans (Engine
Procurement, Navy). (Support)
Procurement Subtotal -4078.3 -6343.6