## Table 1
RDT&E |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A +63.0
Adjustment for current and prior escalation. (Estimating) -53.1 -59.2 Increase due to revised estimate of required risk funding based on OSD lead
Independent program assessments. (Navy) (Estimating) +2327.0 +2976.4
Increase due to revised estimate of required risk funding based on OSD lead
Independent program assessments. (Air Force) (Estimating) +975.9 +1248.4
RDT&E Subtotal +3249.8 +4228.6
Procurement |  | $M
Current Change Explanations |  | Base Year | Then Year
Revised escalation indices. (Economic) N/A -1449.8
Increase for revised DoD procurement profile, (i.e. lower near-term ramp). (Air Force)
(Schedule) 0.0 +1755.9
Increase for revised DoD procurement profile, (i.e. lower near-term ramp and
procurement completion extended one year to FY 2027). (Navy) (Schedule) 0.0 +1395.1
Adjustment for current and prior escalation. (Estimating) +33.8 +40.8 Increase to Airframe due to incorporation of latest actual costs for LRIP lots. (Air Force)
(Estimating) +6099.2 +9730.1
Increase to Airframe due to incorporation of latest actual costs for LRIP lots. (Navy)
(Estimating) +1878.0 +2910.1
Increase to Mission Systems due to incorporation of latest actual costs for LRIP lots.
(Air Force) (Estimating) +593.5 +947.3
Increase to Mission Systems due to incorporation of latest actual costs for LRIP lots.
(Navy) (Estimating) +178.2 +276.0
Decrease to Vehicle Systems due to incorporation of latest actual costs for LRIP lots.
(Air Force) (Estimating) -20.8 -32.7
Increase to Vehicle Systems due to incorporation of latest actual costs for LRIP lots.
(Navy) (Estimating) +124.5 +193.0
Increase due to incorporation of latest prime and subcontractor labor rates. (Air Force)
(Estimating) +1357.3 +2165.5
Increase due to incorporation of latest prime and subcontractor labor rates. (Navy)
(Estimating) +393.1 +609.1
Increase due to revised estimate of required risk funding based on OSD led
Independent program assessments for Air Vehicle and Propulsion. (Air Force)
(Estimating)
Increase due to revised estimate of required risk funding based on OSD led Independent program assessments for Air Vehicle and Propulsion. (Navy) (Estimating)
Increase for revised, slower International Partner procurement quantity profile. (Air
+8835.8 +14095.2
+1486.7 +2301.8
Force) (Estimating) +1039.0 +1657.2
Increase for revised, slower International Partner procurement quantity profile. (Navy)
(Estimating) +238.5 +369.4
Increase to Propulsion due to incorporation of latest actual costs for LRIP lots. (Air
Force) (Estimating) +266.3 +425.1
Increase to Propulsion due to incorporation of latest actual costs for LRIP lots. (Navy)
(Estimating) +1349.0 +2090.1
Decrease to Propulsion due to changes in estimating assumptions based on latest
data from analogous engine. (Air Force) (Estimating) -1509.3 -2407.7
Decrease to Propulsion due to changes in estimating assumptions based on latest
data from analogous engine. (Navy) (Estimating) -836.7 -1294.5
Multi-Year start changed from FY 2016 to 2018. (Air Force) (Estimating) +579.9 +924.9
Multi-Year start changed from FY 2016 to 2018. (Navy) (Estimating) +267.5 +414.7 Adjustment for current and prior escalation. (Support) +8.6 +10.6 Increase due to cost maturity, definition of customer requirements, and further definition
of Service beddown plans. (Air Force) (Support) +3247.5 +4558.4
Increase in Initial Spares due to revised estimate. (Air Force) (Support) +1251.6 +2094.5 Increase due to cost maturity, definition of customer requirements, and further definition
of Service beddown plans. (Navy) (Support) +1548.2 +2465.6
Initial spares increase due to revised estimate. (Navy) (Support) | 341.9 |  | 665.6
Procurement Subtotal | 28751.3 |  | 46911.3