## Cost Variance
Summary, Current TY $M
| RDT&E | PROC | MILCON | TOTAL
Planning Estimate | 248001 | -- | -- | 24800
Previous Changes | -- | -- | -- | --
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -- | -- | --
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -- | -- | --
Current Changes
Economic | -1230.4 | -- | -- | -1230.4
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -403.7 | -- |  | -403.7
Other | -- | -- |  | --
Support | -- | -- | -- | --
Subtotal | -1634.1 | -- | -- | -1634.1
Total Changes | -1634.1 | -- | -- | -1634.1
Current Estimates | 23165.9 | -- | -- | 23165.9
Summary, FY94 BY $M
| RDT&E | PROC | MILCON | TOTAL
Planning Estimate | 19000 | -- | -- | 19000
Previous Changes | -- | -- | -- | --
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -- | -- | -- | --
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -- | -- | -- | --
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -139.6 | -- |  | -139.6
Other | -- | -- |  | --
Support | -- | -- | -- | --
Subtotal | -139.6 | -- | -- | -139.6
Total Changes | -139.6 | -- | -- | -139.6
Current Estimates | 18860.4 | -- | -- | 18860.4
$M
RDT&E | BY | TY
Revised escalation rates from 1995 to 1997 (Economic) | N/A | -1230.4
Adjustment to reflect uniform application of escalation in prior estimate (Estimating) | -139.6 | -403.7
RDT&E Subtotal | -139.6 | -1634.1

## Contract Information
TY, $M
RDT&E | Initial Contract Price
Propulsion CDP | Target | Ceiling | Qty
Pratt and Whitney, West Palm Beach FL N00019-97-C-0050, CPAF | 832
Award: January 23, 1997
Definitized: January 23, 1997
Current Contract Price |  |  | Estimated Price At Completion
Target | Ceiling | Qty | Target | Ceiling | Qty
832
Initial Contract Price
Weapon System CDP | Target | Ceiling | Qty
Lockheed Martin Corp., Ft. Worth TX N00019-97-C-0038, CPFF | 718.8
Award: November 16, 1996
Definitized: November 16, 1996
Current Contract Price |  |  | Estimated Price At Completion
Target | Ceiling | Qty | Target | Ceiling | Qty
718.8
Initial Contract Price
Weapon System CDP | Target | Ceiling | Qty
Boeing Defense and Space, Seattle WA N00019-97-C, CPFF | 661.8
Award: November 16, 1996
Definitized: November 16, 1996
Current Contract Price |  |  | Estimated Price At Completion
Target | Ceiling | Qty | Target | Ceiling | Qty
661.8
| Initial Contract Price |  |  |  |  | m
Alternate Engine | Target | Ceiling | Qty
General Electric, Cinncinnati, OH N00019-96-C-0176 | 96
Award: February 13, 1997
Definitized: February 13, 1997
Current Contract Price |  |  | Estimated Price At Completion
Target | Ceiling | Qty | Contractor | Program Manager
96
Initial Contract Price
J/IST | Target | Ceiling | Qty
McDonnell Douglas Corp., St. Louis MO F33615-95-K-3801 | 63.6
Award: September 22, 1995
Definitized: September 22, 1995
Current Contract Price |  |  | Estimated Price At Completion
Target | Ceiling | Qty | Contractor | Program Manager
63.6
| Cost Variance | Schedule Variance
Previous Cumulative Variances | N/A | N/A
Cumulative Variances To Date | -0.4 | -0.5
Net Change | -0.4 | -0.5
Explanation of Change:
Initial SAR; variance is not significant
Initial Contract Price
J/IST | Target | Ceiling | Qty
Huges Aircraft Company, Los Angeles CA N00019-96-C-0074, CPFF | 54.6
Award: February 12, 1996
Definitized: February 12, 1996
Current Contract Price |  |  | Estimated Price At Completion
Target | Ceiling | Qty | Contractor | Program Manager
54.6 |  |  | 54.6 | 54.6
| Cost Variance | Schedule Variance
Previous Cumulative Variances | N/A | N/A
Cumulative Variances To Date | 0.8 | -0.5
Net Change | 0.8 | -0.5
Explanation of Change:
Initial SAR; variance is not significant

## Program Funding Summary
Appropriation Summary, TY $M
Appropriation | Prior Years | Budget Year | Budget Year | Balance to Complete | Total
| FY94-97 | FY98 | FY99 | FY00-08
RDT&E | 1070.1 | 995.5 | 950.7 | 20149.6 | 23165.9
Procurement | -- | -- | -- | -- | --
MILCON | -- | -- | -- | -- | --
O&M | -- | -- | -- | -- | --
Total | 1070.1 | 995.5 | 950.7 | 20149.6 | 23165.9
Approptiation : 0400 RDT&E, Defense Agencies
FY | Qty | Flyaway FY94 Dollars Nonrec | Flyaway FY94 Dollars Rec | Total Program Base-Year $ | Total Program Then-Year $
1996 |  |  |  | 27.4 | 28.9
1997 |  |  |  | 71.4 | 76.9
1998 |  |  |  | 21.7 | 23.9
Subtotal |  |  |  | 120.5 | 129.7
Appropriation : 1319 Research, Development, Test + Eval, Navy
FY | Qty | Flyaway FY94 Dollars Nonrec | Flyaway FY94 Dollars Rec | Total Program Base-Year $ | Total Program Then-Year $
1994 |  |  |  | 29.1 | 29.5
1995 |  |  |  | 95.1 | 98.3
1996 |  |  |  | 75.8 | 80
1997 |  |  |  | 228.5 | 246.1
1998 |  |  |  | 408.2 | 448.9
1999 |  |  |  | 394.9 | 443.5
2000 |  |  |  | 217.5 | 249.4
2001 |  |  |  | 498.4 | 583.6
2002 |  |  |  | 1168.5 | 1398
2003 |  |  |  | 1562.8 | 1913.7
2004 |  |  |  | 1556.6 | 1955.6
2005 |  |  |  | 1286.7 | 1658.6
2006 |  |  |  | 778 | 1028.9
2007 |  |  |  | 411.9 | 558.9
2008 |  |  |  | 91.5 | 127.4
Subtotal |  |  |  | 8803.5 | 10820.4
Appropriation : 3600 Research, Development, Test + Eval, AF
FY | Qty | Flyaway FY94 Dollars Nonrec | Flyaway FY94 Dollars Rec | Total Program Base-Year $ | Total Program Then-Year $
1995 |  |  |  | 81.1 | 83.8
1996 |  |  |  | 77.1 | 81.3
1997 |  |  |  | 233.9 | 252
1998 |  |  |  | 416.5 | 458.1
1999 |  |  |  | 414.6 | 465.6
2000 |  |  |  | 214 | 245.4
2001 |  |  |  | 498.6 | 583.9
2002 |  |  |  | 1170.1 | 1399.9
2003 |  |  |  | 1564.5 | 1915.7
2004 |  |  |  | 1555.5 | 1954.2
2005 |  |  |  | 1283.3 | 1654.2
2006 |  |  |  | 778 | 1028.9
2007 |  |  |  | 411.9 | 558.9
2008 |  |  |  | 91.5 | 127.4
Subtotal |  |  |  | 8790.6 | 10809.3
Appropriation: Other RDT&E Funding
FY | Qty | Flyaway FY94 Dollars Nonrec | Flyaway FY94 Dollars Rec | Total Program Base-Year $ | Total Program Then-Year $
1996 |  |  |  | 13.3 | 14
1997 |  |  |  | 73.6 | 79.3
1998 |  |  |  | 58.7 | 64.6
1999 |  |  |  | 37 | 41.6
2000 |  |  |  | 27 | 31
2001 |  |  |  | 59.5 | 70.1
2002 |  |  |  | 140.3 | 167.8
2003 |  |  |  | 186.9 | 228.9
2004 |  |  |  | 204.5 | 256.9
2005 |  |  |  | 181.1 | 233.4
2006 |  |  |  | 99.3 | 131.3
2007 |  |  |  | 52.5 | 71.3
2008 |  |  |  | 11.7 | 16.3
Subtotal |  |  |  | 1145.8 | 1406.5
"Other RDT&E Funding" reflects current and anticipated foreign funding
Service | Qty | Flyway Dollars Nonrec | Flyaway Dollars | Total Program Base-Year $ | Total Program Then-Year $
OSD |  |  |  | 120.5 | 129.7
Navy |  |  |  | 8803.5 | 10820.4
USAF |  |  |  | 8790.6 | 10809.3
Other Funding |  |  |  | 1145.8 | 14065
Grand Total |  |  |  | 18860.4 | 23165.9