## Cost Summary
Total Acquisition Cost and Quantity
| BY2002 $M |  |  |  | TY $M
Appropriation | SAR Baseline Deve Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 32300 | 42100 | 46310 | 39987.8 | 34400 | 44800 | 44194.1
Procurement | 143300 | 168980.8 | 185878.9 | 168980.8 | 196600 | 231735.5 | 255096.9
Flyaway | 121215.6 | -- | -- | 5678 | 166349.7 | -- | 205189.8
Recurring | 116093.7 | -- | -- | 129582.1 | 159390.4 | -- | 196299.4
Non Recurring | 5121.9 | -- | -- | 6095.9 | 6959.3 | -- | 8890.4
Support | 22084.4 | -- | -- | 33302.8 | 30250.3 | -- | 49907.1
Other Support | 15403.4 | -- | -- | 21219.2 | 21109.3 | -- | 31543.6
Initial Spares | 6681 | -- | -- | 12083.6 | 9141 | -- | 18363.5
MILCON | 1500 | 1500 | 1700 | 433 | 2000 | 2000 | 533.1
Acq O&M | -- | -- | -- | -- | -- | -- | --
Total | 177100 | 212580.8 | N/A | 209401.6 | 23000 | 278535.5 | 299842.1
Quantity | SAR Baseline Dev Est | Current APB Development | Current Estimate
RDT&E | 14 | 15 | 15
Procurement | 2852 | 2443 | 2443
Total | 2866 | 2458 | 2458

## Funding Summary
Appropriation and Quantity Summary
FY2008 President's Budget / December 2006 SAR (TY$ M)
Appropriation | Prior | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | FY2012 | FY22013 | To Complete | Total
RDT&E | 2443.3 | 4997.9 | 3966.8 | 3311.5 | 2357.3 | 1991.4 | 1727.3 | 1398.6 | 0 | 44194.1
Procurement | 117 | 773 | 2778.8 | 3715.3 | 6065.3 | 6966.8 | 10589.8 | 10869.3 | 213220.7 | 255096.9
MILCON | 55.1 | 0 | 74.3 | 64.5 | 98.4 | 128.9 | 34 | 77.9 | 0 | 533.1
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2008 Total | 24615.8 | 5770.9 | 6819.9 | 7091.3 | 8521 | 9087.1 | 12351.1 | 12346.3 | 213220.7 | 299824.1
PB 2007 Total | 24796.7 | 6090.9 | 7267.1 | 9863 | 9469.4 | 8997.7 | 14278.1 | 15834 | 179862 | 276458.9
Delta | -180.9 | -320 | -447.2 | -2771.7 | -948.4 | 89.4 | -1927 | -3847.7 | 33358.7 | 23365.2
Quantity | Prior | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | FY2012 | FY2013 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
Production | 0 | 2 | 12 | 16 | 30 | 43 | 82 | 90 | 2168 | 2443
PB2005 Total | 0 | 2 | 12 | 16 | 30 | 43 | 82 | 90 | 2168 | 2458
PB2004 Total | 0 | 5 | 16 | 47 | 56 | 64 | 103 | 135 | 2017 | 2458
Delta | 0 | -0.3 | -4 | -31 | -26 | -21 | -21 | -45 | 15 | 0

## Annual Funding by Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 29.5
1995 | -- | -- | -- | -- | -- | -- | 98.3
1996 | -- | -- | -- | -- | -- | -- | 80.4
1997 | -- | -- | -- | -- | -- | -- | 243.3
1998 | -- | -- | -- | -- | -- | -- | 448.2
1999 | -- | -- | -- | -- | -- | -- | 471.3
2000 | -- | -- | -- | -- | -- | -- | 238.4
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 721.3
2003 | -- | -- | -- | -- | -- | -- | 1640.9
2004 | -- | -- | -- | -- | -- | -- | 2081.4
2005 | -- | -- | -- | -- | -- | -- | 2083.8
2006 | -- | -- | -- | -- | -- | -- | 2187.1
2007 | -- | -- | -- | -- | -- | -- | 2163.9
2008 | -- | -- | -- | -- | -- | -- | 1707.4
2009 | -- | -- | -- | -- | -- | -- | 1548.9
2010 | -- | -- | -- | -- | -- | -- | 1045.3
2011 | -- | -- | -- | -- | -- | -- | 165.9
2012 | -- | -- | -- | -- | -- | -- | 745.6
2013 | -- | -- | -- | -- | -- | -- | 663.7
Subtotal | 7 | -- | -- | -- | -- | -- | 19605.8
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1994 | -- | -- | -- | -- | -- | -- | 32.5
1995 | -- | -- | -- | -- | -- | -- | 106.4
1996 | -- | -- | -- | -- | -- | -- | 85.6
1997 | -- | -- | -- | -- | -- | -- | 255.9
1998 | -- | -- | -- | -- | -- | -- | 467.5
1999 | -- | -- | -- | -- | -- | -- | 485.9
2000 | -- | -- | -- | -- | -- | -- | 242.2
2001 | -- | -- | -- | -- | -- | -- | 342
2002 | -- | -- | -- | -- | -- | -- | 715.7
2003 | -- | -- | -- | -- | -- | -- | 1604.7
2004 | -- | -- | -- | -- | -- | -- | 1980.1
2005 | -- | -- | -- | -- | -- | -- | 1931.2
2006 | -- | -- | -- | -- | -- | -- | 1971.8
2007 | -- | -- | -- | -- | -- | -- | 1904.4
2008 | -- | -- | -- | -- | -- | -- | 1468.3
2009 | -- | -- | -- | -- | -- | -- | 1302.8
2010 | -- | -- | -- | -- | -- | -- | 860.8
2011 | -- | -- | -- | -- | -- | -- | 860.1
2012 | -- | -- | -- | -- | -- | -- | 589.6
2013 | -- | -- | -- | -- | -- | -- | 514.8
Subtotal | 7 | -- | -- | -- | -- | -- | 17722.5
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | -- | -- | -- | -- | -- | -- | 83.8
1996 | -- | -- | -- | -- | -- | -- | 81.3
1997 | -- | -- | -- | -- | -- | -- | 251.6
1998 | -- | -- | -- | -- | -- | -- | 444.3
1999 | -- | -- | -- | -- | -- | -- | 456.1
2000 | -- | -- | -- | -- | -- | -- | 249.1
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 712.4
2003 | -- | -- | -- | -- | -- | -- | 1610.6
2004 | -- | -- | -- | -- | -- | -- | 2019.9
2005 | -- | -- | -- | -- | -- | -- | 2080.1
2006 | -- | -- | -- | -- | -- | -- | 2264.8
2007 | -- | -- | -- | -- | -- | -- | 2132.9
2008 | -- | -- | -- | -- | -- | -- | 1780.9
2009 | -- | -- | -- | -- | -- | -- | 1541.7
2010 | -- | -- | -- | -- | -- | -- | 1146
2011 | -- | -- | -- | -- | -- | -- | 789
2012 | -- | -- | -- | -- | -- | -- | 975.2
2013 | -- | -- | -- | -- | -- | -- | 734.9
Subtotal | 8 | -- | -- | -- | -- | -- | 19695.8
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1995 | -- | -- | -- | -- | -- | -- | 90.7
1996 | -- | -- | -- | -- | -- | -- | 86.5
1997 | -- | -- | -- | -- | -- | -- | 264.6
1998 | -- | -- | -- | -- | -- | -- | 463.4
1999 | -- | -- | -- | -- | -- | -- | 470.2
2000 | -- | -- | -- | -- | -- | -- | 253.1
2001 | -- | -- | -- | -- | -- | -- | 342
2002 | -- | -- | -- | -- | -- | -- | 706.9
2003 | -- | -- | -- | -- | -- | -- | 1575.1
2004 | -- | -- | -- | -- | -- | -- | 1921.6
2005 | -- | -- | -- | -- | -- | -- | 1927.8
2006 | -- | -- | -- | -- | -- | -- | 2041.8
2007 | -- | -- | -- | -- | -- | -- | 1877.2
2008 | -- | -- | -- | -- | -- | -- | 1531.5
2009 | -- | -- | -- | -- | -- | -- | 1296.8
2010 | -- | -- | -- | -- | -- | -- | 943.7
2011 | -- | -- | -- | -- | -- | -- | 636.7
2012 | -- | -- | -- | -- | -- | -- | 771.5
2013 | -- | -- | -- | -- | -- | -- | 570
Subtotal | 8 | -- | -- | -- | -- | -- | 17771.1
Annual Funding TY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 28.9
1997 | -- | -- | -- | -- | -- | -- | 68.2
1998 | -- | -- | -- | -- | -- | -- | 20.9
Subtotal | -- | -- | -- | -- | -- | -- | 118
Annual Funding BY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1996 | -- | -- | -- | -- | -- | -- | 30.8
1997 | -- | -- | -- | -- | -- | -- | 71.7
1998 | -- | -- | -- | -- | -- | -- | 21.8
Subtotal | -- | -- | -- | -- | -- | -- | 124.3
Annual Funding TY$
9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 14
1997 | -- | -- | -- | -- | -- | -- | 71
1998 | -- | -- | -- | -- | -- | -- | 77.2
1999 | -- | -- | -- | -- | -- | -- | 54.7
2000 | -- | -- | -- | -- | -- | -- | 34.5
2001 | -- | -- | -- | -- | -- | -- | 2.5
2002 | -- | -- | -- | -- | -- | -- | 306.4
2003 | -- | -- | -- | -- | -- | -- | 425.8
2004 | -- | -- | -- | -- | -- | -- | 517.8
2005 | -- | -- | -- | -- | -- | -- | 758.6
2006 | -- | -- | -- | -- | -- | -- | 802.5
2007 | -- | -- | -- | -- | -- | -- | 701.1
2008 | -- | -- | -- | -- | -- | -- | 478.5
2009 | -- | -- | -- | -- | -- | -- | 220.9
2010 | -- | -- | -- | -- | -- | -- | 166
2011 | -- | -- | -- | -- | -- | -- | 136.5
2012 | -- | -- | -- | -- | -- | -- | 6.5
Subtotal | -- | -- | -- | -- | -- | -- | 4774.5
Annual Funding TY$
9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1996 | -- | -- | -- | -- | -- | -- | 14.9
1997 | -- | -- | -- | -- | -- | -- | 74.7
1998 | -- | -- | -- | -- | -- | -- | 80.5
1999 | -- | -- | -- | -- | -- | -- | 56.4
2000 | -- | -- | -- | -- | -- | -- | 35.1
2001 | -- | -- | -- | -- | -- | -- | 2.5
2002 | -- | -- | -- | -- | -- | -- | 304
2003 | -- | -- | -- | -- | -- | -- | 416.4
2004 | -- | -- | -- | -- | -- | -- | 492.6
2005 | -- | -- | -- | -- | -- | -- | 703.1
2006 | -- | -- | -- | -- | -- | -- | 723.5
2007 | -- | -- | -- | -- | -- | -- | 617
2008 | -- | -- | -- | -- | -- | -- | 411.5
2009 | -- | -- | -- | -- | -- | -- | 185.8
2010 | -- | -- | -- | -- | -- | -- | 136.7
2011 | -- | -- | -- | -- | -- | -- | 110.1
2012 | -- | -- | -- | -- | -- | -- | 5.1
Subtotal | -- | -- | -- | -- | -- | -- | 4369.9
Annual Funding TY$
1506 ¦ RDT&E ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2007 | -- | 124.5 | -- | -- | 124.5 | -- | 124.5
2008 | 6 | 1038.3 | -- | 69.7 | 1108 | 209.1 | 1317.1
2009 | 8 | 1403.1 | -- | 129.3 | 1532.4 | 276.6 | 1809
2010 | 18 | 2633.5 | -- | 163.8 | 2797.3 | 810.7 | 3608
2011 | 19 | 2454.7 | -- | 225.9 | 2680.6 | 742.1 | 3422.7
2012 | 40 | 4457.3 | -- | 292.9 | 4750.2 | 925.5 | 5675.7
2013 | 42 | 4329.6 | -- | 215.1 | 4544.7 | 1102.5 | 5647.2
2014 | 50 | 4724.4 | -- | 264.4 | 4988.8 | 1417.3 | 6406.1
2015 | 50 | 4462.8 | -- | 125.6 | 4588.4 | 1355.2 | 5943.6
2016 | 50 | 4336.7 | -- | 124.5 | 4461.2 | 1325.7 | 5786.9
2017 | 50 | 4251.9 | -- | 123.7 | 4375.6 | 1306.5 | 5682.1
2018 | 50 | 4215.9 | -- | 124 | 4339.9 | 1299.9 | 5639.8
2019 | 50 | 4223.9 | -- | 126.3 | 4350.2 | 1304.7 | 5654.9
2020 | 50 | 4256.1 | -- | 128.8 | 4384.9 | 1316 | 5700.9
2021 | 50 | 4294.3 | -- | 130.9 | 4425.2 | 1328.7 | 5753.9
2022 | 50 | 4334.2 | -- | 133.4 | 4467.6 | 1328.3 | 5795.9
2023 | 49 | 4111.9 | -- | 133 | 4244.9 | 1307.6 | 5552.5
2024 | 25 | 2350.8 | -- | 93.4 | 2444.2 | 679.5 | 3123.7
2025 | 23 | 2004 | -- | 88.8 | 2092.8 | 631.3 | 2724.1
Subtotal | 680 | 64007.9 | -- | 2693.5 | 66701.4 | 18667.2 | 85368.6
Annual Funding BY$
1506 ¦ RDT&E ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2007 | -- | 107.9 | -- | -- | 107.9 | -- | 107.9
2008 | 6 | 880.1 | -- | 59.1 | 939.2 | 177.2 | 1116.4
2009 | 8 | 1164 | -- | 107.3 | 1271.3 | 229.4 | 1500.7
2010 | 18 | 2140 | -- | 133.1 | 2273.1 | 658.8 | 2931.9
2011 | 19 | 1955.1 | -- | 179.9 | 2135 | 591.1 | 2726.1
2012 | 40 | 3480.5 | -- | 228.7 | 3709.2 | 722.7 | 4431.9
2013 | 42 | 3314.5 | -- | 164.7 | 3479.2 | 844 | 4323.2
2014 | 50 | 3545.8 | -- | 198.4 | 3744.2 | 1063.8 | 4808
2015 | 50 | 3283.8 | -- | 92.4 | 3376.2 | 997.2 | 4373.4
2016 | 50 | 3128.5 | -- | 89.8 | 3218.3 | 956.3 | 4174.6
2017 | 50 | 3007.1 | -- | 87.5 | 3094.6 | 924.1 | 4018.7
2018 | 50 | 2923.2 | -- | 86 | 3009.2 | 901.3 | 3910.5
2019 | 50 | 2871.3 | -- | 85.9 | 2957.2 | 886.9 | 3844.1
2020 | 50 | 2836.5 | -- | 85.8 | 2922.3 | 877.1 | 3799.4
2021 | 50 | 2805.8 | -- | 85.5 | 2891.3 | 868.2 | 3759.5
2022 | 50 | 2776.4 | -- | 85.5 | 2861.9 | 850.8 | 3712.7
2023 | 49 | 2582.3 | -- | 83.5 | 2665.8 | 821.3 | 3487.1
2024 | 25 | 1447.4 | -- | 57.5 | 1504.9 | 418.4 | 1923.3
2025 | 23 | 1209.7 | -- | 53.6 | 1263.3 | 381 | 1644.3
Subtotal | 680 | 45459.9 | -- | 1964.2 | 47424.1 | 13169.6 | 60593.7
Cost Quantity Information
1506 ¦ RDT&E ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2002 $M)
2007 | -- | --
2008 | 6 | 778.5
2009 | 8 | 1098
2010 | 18 | 2075.5
2011 | 19 | 2007.7
2012 | 40 | 3442.5
2013 | 42 | 3290.3
2014 | 50 | 3623.4
2015 | 50 | 3438.6
2016 | 50 | 3132
2017 | 50 | 3010
2018 | 50 | 2925.4
2019 | 50 | 2873.4
2020 | 50 | 2839.7
2021 | 50 | 2805.4
2022 | 50 | 2776.9
2023 | 49 | 2616.5
2024 | 25 | 1504.6
2025 | 23 | 1221.5
Subtotal | 680 | 45459.9
Annual Funding TY$
3010 ¦ Procurement ¦ Aircraft Procurement, AF
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | 117.4 | -- | -- | 117.4 | -- | 117.4
2007 | 2 | 409.1 | -- | 10.2 | 419.3 | 229.2 | 648.5
2008 | 6 | 1065.9 | -- | 158.3 | 1224.2 | 237.5 | 1461.7
2009 | 8 | 1180.5 | -- | 226.3 | 1406.8 | 499.5 | 1906.3
2010 | 12 | 1690.4 | -- | 202.1 | 1892.5 | 564.8 | 2457.3
2011 | 24 | 2579.2 | -- | 247.2 | 2826.4 | 717.7 | 3544.1
2012 | 42 | 3636.2 | -- | 289.2 | 3925.4 | 988.7 | 4914.1
2013 | 48 | 3895.1 | -- | 362.1 | 4257.2 | 965.4 | 5222.6
2014 | 60 | 4356 | -- | 508.2 | 4864.2 | 1093.5 | 5957.7
2015 | 80 | 5396.1 | -- | 190.9 | 5587 | 1317 | 6904
2016 | 80 | 5274.2 | -- | 189.4 | 5463.6 | 1293.8 | 6757.4
2017 | 80 | 5218.4 | -- | 188.8 | 5407.2 | 1285 | 6692.2
2018 | 80 | 5214.9 | -- | 189.1 | 5404 | 1287 | 6691
2019 | 80 | 5284.1 | -- | 193.1 | 5477.2 | 1305.9 | 6783.1
2020 | 80 | 5338.9 | -- | 195.8 | 5534.7 | 1321.8 | 6856.5
2021 | 80 | 5405.5 | -- | 198.5 | 5604 | 1339.5 | 6943.5
2022 | 80 | 5502.1 | -- | 202.3 | 5704.4 | 1354.6 | 7059
2023 | 80 | 5602.5 | -- | 205.7 | 5808.2 | 1370 | 7178.2
2024 | 80 | 5710.1 | -- | 210.5 | 5920.6 | 1320.4 | 7241
2025 | 80 | 5799.5 | -- | 213 | 6012.5 | 1330.6 | 7343.1
2026 | 80 | 5942.1 | -- | 219.3 | 6161.4 | 1269.9 | 7431.3
2027 | 80 | 6045.7 | -- | 222.5 | 6268.2 | 1270.7 | 7538.9
2028 | 80 | 6180 | -- | 228.4 | 6408.4 | 1299.6 | 7708
2029 | 80 | 6277.7 | -- | 231.5 | 6509.2 | 1320.8 | 7830
2030 | 80 | 6377.2 | -- | 234.5 | 6611.7 | 1342.6 | 7954.3
2031 | 80 | 6479.1 | -- | 237.9 | 6717 | 1364.7 | 8081.7
2032 | 80 | 6584 | -- | 241.1 | 6825.1 | 1378.3 | 8203.4
2033 | 80 | 6391.2 | -- | 244.6 | 6635.8 | 1381.6 | 8017.4
2034 | 41 | 3338.4 | -- | 156.4 | 3494.8 | 789.8 | 4284.6
Subtotal | 1763 | 132291.5 | -- | 6196.9 | 138488.4 | 31239.9 | 169728.3
Annual Funding TY$
3010 ¦ Procurement ¦ Aircraft Procurement, AF
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2006 | -- | 104.2 | -- | -- | 104.2 | -- | 104.2
2007 | 2 | 354.7 | -- | 8.8 | 363.5 | 198.7 | 562.2
2008 | 6 | 903.5 | -- | 134.2 | 1037.7 | 201.3 | 1239
2009 | 8 | 979.3 | -- | 187.7 | 1167 | 414.4 | 1581.4
2010 | 12 | 1373.6 | -- | 164.2 | 1537.8 | 459 | 1996.8
2011 | 24 | 2054.3 | -- | 196.9 | 2251.2 | 571.6 | 2822.8
2012 | 42 | 2839.4 | -- | 225.8 | 3065.2 | 772 | 3837.2
2013 | 48 | 2981.9 | -- | 277.2 | 3259.1 | 739.1 | 3998.2
2014 | 60 | 3269.3 | -- | 381.4 | 3650.7 | 820.8 | 4471.5
2015 | 80 | 3970.6 | -- | 140.5 | 4111.1 | 969 | 5080.1
2016 | 80 | 3804.8 | -- | 136.6 | 3941.4 | 933.3 | 4874.7
2017 | 80 | 3690.7 | -- | 133.5 | 3824.2 | 908.8 | 4733
2018 | 80 | 3615.9 | -- | 131.1 | 3747 | 892.4 | 4639.4
2019 | 80 | 3592.1 | -- | 131.3 | 3723.4 | 887.6 | 4611
2020 | 80 | 3558.1 | -- | 130.5 | 3688.6 | 880.9 | 4569.5
2021 | 80 | 3531.9 | -- | 129.7 | 3661.6 | 875.2 | 4536.8
2022 | 80 | 3524.5 | -- | 129.6 | 3654.1 | 867.7 | 4521.8
2023 | 80 | 3518.5 | -- | 129.2 | 3647.7 | 860.3 | 4508
2024 | 80 | 3515.7 | -- | 129.6 | 3645.3 | 813 | 4458.3
2025 | 80 | 3500.7 | -- | 128.6 | 3629.3 | 803.2 | 4432.5
2026 | 80 | 3516.5 | -- | 129.8 | 3646.3 | 751.5 | 4397.8
2027 | 80 | 3507.7 | -- | 129.1 | 3636.8 | 737.2 | 4374
2028 | 80 | 3515.3 | -- | 129.9 | 3645.2 | 739.2 | 4384.4
2029 | 80 | 3500.8 | -- | 129.1 | 3629.9 | 736.6 | 4366.5
2030 | 80 | 3486.6 | -- | 128.2 | 3614.8 | 734 | 4348.8
2031 | 80 | 3472.8 | -- | 127.5 | 3600.3 | 731.5 | 4331.8
2032 | 80 | 3459.9 | -- | 126.7 | 3586.6 | 724.2 | 4310.8
2033 | 80 | 3292.7 | -- | 126 | 3418.7 | 711.8 | 4130.5
2034 | 41 | 1686.2 | -- | 79 | 1765.2 | 398.9 | 2164.1
Subtotal | 1763 | 84122.2 | -- | 4131.7 | 88253.9 | 20133.2 | 108387.1
Cost Quantity Information
3010 ¦ RDT&E ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2002 $M
2006 | -- | --
2007 | 2 | 330.1
2008 | 6 | 911
2009 | 8 | 888.4
2010 | 12 | 1181.7
2011 | 24 | 1938.8
2012 | 42 | 2786
2013 | 48 | 3059.6
2014 | 60 | 3547.6
2015 | 80 | 3976.9
2016 | 80 | 3809.6
2017 | 80 | 3694.5
2018 | 80 | 3619.5
2019 | 80 | 3595.9
2020 | 80 | 3560.9
2021 | 80 | 3533.8
2022 | 80 | 3524.1
2023 | 80 | 3514.1
2024 | 80 | 3517.1
2025 | 80 | 3506.1
2026 | 80 | 3525.3
2027 | 80 | 3686.9
2028 | 80 | 3515.3
2029 | 80 | 3500.8
2030 | 80 | 3486.6
2031 | 80 | 3472.8
2032 | 80 | 3459.9
2033 | 80 | 3292.7
2034 | 41 | 1686.2
Subtotal | 1763 | 84122.2
Annual Funding TY$
1215 ¦ MILCON ¦Military Construction, Navy and Marine Corps
Fiscal Year | Total Program TY $M
2004 | 24.4
Subtotal | 24.4
Annual Funding BY$
1215 ¦ MILCON ¦Military Construction, Navy and Marine Corps
Fiscal Year | Total Program BY 2002 $M
2004 | 22.7
Subtotal | 22.7
Annual Funding TY$
3300 ¦ MILCON ¦Military Construction, Air Force
Fiscal Year | Total Program TY $M
2004 | 20.1
2005 | 10.6
2006 | --
2007 | --
2008 | 74.3
2009 | 64.5
2010 | 98.4
2011 | 128.9
2012 | 34
2013 | 77.9
Subtotal | 508.7
Annual Funding BY$
3300 ¦ MILCON ¦Military Construction, Air Force
Fiscal Year | Total Program BY 2002 $M
2004 | 18.7
2005 | 9.6
2006 | --
2007 | --
2008 | 62.5
2009 | 53
2010 | 79.3
2011 | 101.8
2012 | 26.3
2013 | 59.1
Subtotal | 410.3

## Unit Cost
BY2002 $M
Unit Cost | Current UCR Baseline (MAR 2007 APB) | Current Estimate (DEC 2006 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 212580.8 | 209401.6
Quantity | 2458 | 2458
Unit Cost | 86.485 | 85.192 | -1.5
Average Procurement Unit Cost (APUC)
Cost | 168980.8 | 168980.8
Quantity | 2443 | 2443
Unit Cost | 69.169 | 69.169 | 0
BY2002 $M
Unit Cost | Original UCR Baseline (OCT 2001 APB) | Current Estimate (DEC 200^ SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 1771700 | 209401.6
Quantity | 2866 | 2456
Unit Cost | 61.793 | 85.192 | 37.87
Average Procurement Unit Cost (APUC)
Cost | 143300 | 168980.8
Quantity | 2852 | 2443
Unit Cost | 50.245 | 69.169 | 37.66
Nunn-McCurdy Breach
This program reflects a significant Nunn-McCurdy breach to the original baseline that was first reported in the December 2005 SAR. The supporting breach information and explanations can be found in the Unit Cost Report section of that SAR.

## Unit Cost History
APB Unit Cost History
|  | BY2002 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2001-10-01 | 61.793 | 50.245 | 81.298 | 68.934
APB as of January 2006 | 2004-03-01 | 78.592 | 61.195 | 100.407 | 81.826
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | 2004-03-01 | 146.461 | 61.195 | 100.407 | 81.826
Current APB | 2007-03-01 | 86.485 | 69.169 | 113.318 | 94.857
Prior Annual SAR | 2005-12-01 | 82.071 | 65.964 | 112.473 | 94.857
Current Estimate | 2006-12-01 | 85.192 | 69.169 | 121.979 | 104.42
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY$M)
Initial PAUC Dev Est | Changes | [7 empty] | PAUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
81.298 | 2.956 | 3.147 | 12.048 | 5.203 | 9.636 | 0 | 7.691 | 40.681 | 121.979
Current SAR Baseline to Current Estimate (TY$M)
Initial APUC Dev Est | Changes Econ: Changes | APUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
68.934 | 2.455 | 1.13 | 8.902 | 3.853 | 11.408 | 0 | 7.738 | 35.486 | 104.42
SAR Baseline History
| SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE)
Item/Event | Changes Eng: Current
Estimate
Milestone I | Changes Econ: N/A; Changes Qty: 1996-11-01; Changes Sch: N/A; Changes Eng: 1996-11-01
Milestone B | Changes Econ: 2001-03-01; Changes Qty: 2001-10-01; Changes Sch: N/A; Changes Eng: 2001-10-01
Milestone C | Changes Econ: TBD; Changes Qty: 2012-04-01; Changes Sch: N/A; Changes Eng: 2013-10-01
IOC | Changes Econ: TBD; Changes Qty: 2010-04-01; Changes Sch: N/A; Changes Eng: 2012-03-01
Total Cost (TY $M) | Changes Econ: 24800; Changes Qty: 233000; Changes Sch: N/A; Changes Eng: 299824.1
Total Quantity | Changes Econ: N/A; Changes Qty: 2866; Changes Sch: N/A; Changes Eng: 2458
Prog. Acq. Unit Cost (PAUC) | Changes Econ: N/A; Changes Qty: 81.298; Changes Sch: N/A; Changes Eng: 121.979

## Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 34400 | 196600 | 2000 | 233000
Previous Changes
Economic | 1021.7 | 6578.6 | 7.5 | 7607.8
Quantity | 0 | -25434.9 | 0 | -25434.9
Schedule | 7866.9 | 10539.4 | 0 | 18406.3
Engineering | 2427.8 | 8087.6 | 252.8 | 10768.2
Estimating | -1213.8 | 22884.6 | -2039.5 | 19631.3
Other | 0 | 0 | 0 | 0
Support | 0 | 12480.2 | 0 | 12480.2
Subtotal | 10102.6 | 35135.5 | -1779.2 | 43458.9
Current Changes
Economic | 236.3 | -581.6 | 3.2 | -342.1
Quantity | -- | -- | -- | --
Schedule | -- | 11207.8 | -- | 11207.8
Engineering | 694.7 | 1326.4 | -- | 2021.1
Estimating | -1239.5 | 4985.6 | 309.1 | 4055.2
Other | -- | -- | -- | --
Support | -- | 6423.2 | -- | 6423.2
Subtotal | -308.5 | 23361.4 | 312.3 | 23365.2
Total Changes | 9794.1 | 58496.9 | -1466.9 | 66824.1
CE - Cost Variance | 44194.4 | 255096.9 | 533.1 | 299824.1
CE - Cost & Funding | 44194.1 | 255096.9 | 533.1 | 299824.1
Summary Base Year 2002 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 32300 | 143300 | 1500 | 177100
Previous Changes
Economic | 0 | 0 | 0 | 0
Quantity | 0 | -16249.1 | 0 | -16249.1
Schedule | 6779.4 | 1428.5 | 0 | 8207.9
Engineering | 2231 | 5820.5 | 227.3 | 8278.8
Estimating | -922 | 18795.2 | -1535.5 | 16337.7
Other | 0 | 0 | 0 | 0
Support | 0 | 8054.1 | 0 | 8054.1
Subtotal | 8088.4 | 17849.2 | -1308.2 | 24629.4
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | 589.2 | -- | 589.2
Engineering | 583.6 | 824.3 | -- | 1407.9
Estimating | -984.2 | 3253.9 | 241.2 | 2510.9
Other | -- | -- | -- | --
Support | -- | 3164.2 | -- | 3164.2
Subtotal | -400.6 | 7831.6 | 241.2 | 7672.2
Total Changes | 7687.8 | 25680.8 | -1067 | 32301.6
CE - Cost Variance | 39987.8 | 168980.8 | 433 | 209401.6
CE - Cost & Funding | 39987.8 | 168980.8 | 433 | 209401.6

## Contracts
Contract Name: JSF Air System SDD
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
18981.9 | N/A | 14 | 25873.2 | N/A | 15 | 25873.2 | 25873.2
Variance | Cost Variance | Schedule Variance
Previous Cumulative Variances | -111.7 | -102.6
Cumulative Variances to Date (12/25/2006) | -219.7 | -239.7
Net Change | -108 | -137.1
Contract Name: Propulsion JSF F135 SDD
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
4827.8 | N/A | 33 | 5848.6 | N/A | 33 | 6080.9 | 6276.3
Variance | Cost Variance | Schedule Variance
Previous Cumulative Variances | -106.3 | -27.2
Cumulative Variances to Date (12/25/2006) | -176.2 | -103.1
Net Change | -69.9 | -75.9
Contract Name: F136 Propulsion Sys SDD
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2486.2 | N/A | 6 | 2486.2 | N/A | 6 | 2486.2 | 777.2
Variance | Cost Variance | Schedule Variance
Previous Cumulative Variances | 1.7 | -2.4
Cumulative Variances to Date (12/25/2006) | -4 | -2.4
Net Change | -5.7 | 0

## Deliveries and Expenditures
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 15 | 0%
Production | 0 | 0 | 2443 | 0%
Total Program Quantities Delivered | 0 | 0 | 2458 | 0%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 299824.1 | Years Appropriated | 14
Expenditures to Date | 23791.4 | Percent Years Appropriated | 34.15%
Precent Expended | 7.94% | Appropriated to Date | 30386.7
Total Funding Years | 41 | Percent Appropriated | 10.13%

## Sheet4
Costs BY 2002 $K
Cost Element | JSF Cost per Flying Hour ($) | F-16C/D Cost per Flying Hour ($)
Mission Pay & Allowance | 3.889 | 5.36
Unit Level Consumption | 6.574 | 5.829
Intermediate Maintenance | 0 | 0.003
Depot Maintenance | 0.723 | 0.978
Contractor Support | 0.542 | 0.089
Sustaining Support | 2.116 | 0.63
Indirect | 1.43 | 0.848
Other | -- | --
Total Unitized Cost (Base Year 2002 $) | 15.274 | 13.737
Total O&S Costs $M | JSF | F-16C/D
Base Year | 282519 | --
Then Year | 650295.9 | --