## Table 1
FIRE UNIT
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 20.1
Adjustment for current and prior escalation. (Estimating) | -11.8 | -14
Decrease in FY 2011 and FY 2012 due to Congressional reductions. (Estimating) | -28 | -33.5
Revised estimate to reflect change in dollar value in FY 2013. (Estimating) | -1.9 | -2.3
RDT&E Subtotal | -41.7 | -29.7
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A +1.7
Decrease in FY 2013 due to U.S. DoD decision to end Medium Extended Air Defense
System program after the Design and Development phase. (Estimating) -79.0 -98.4
Procurement Subtotal -79.0 -96.7
MISSILE
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 2.8
Adjustment for current and prior escalation. (Estimating) | -1.9 | -2.3
Increase due to Omnibus reprogramming in FY 2011 to support Missile Segment
Enhancement follow-on tests. (Estimating) +49.4 +58.5
RDT&E Subtotal +47.5 +59.0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 219.6
Stretch-out of production program in FY 2013 to FY 2031. (Subtotal) | 59.4 | 239.5
Production delay by one year from FY 2013 to FY 2014. (Schedule) (QR) | 0 | -150
Additional Schedule Variance due to stretch-out of procurement buy profile from
FY 2015 - FY 2031. (Schedule) (QR) (+48.6) (+75.4)
Refinement of cost estimate associated with production delay of one year (FY
2013 to FY2014). (Estimating) (QR) (+10.8) (+14.1)
Adjustment for current and prior escalation. (Estimating) -0.7 -0.9 Reallocation of funds from support to non-recurring flyaway for Initial Production
Facilitization in FY 2013, due to production schedule slip from FY 2013 to FY 2014. -12.8 -1.9
(Support)
Procurement Subtotal +45.9 +456.3
(QR) Quantity Related