## A400M
2002
Performance against approved in-service date
Date
Current forcase ISD | 2010-06-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 6
In-year changes in 2001/2002 | 16
Reasons for variations from approved ISD
Factor | Increase (months) | Decrease (months) | Explanation
Changed Budgetary Priorities | 16 |  | Change in the customers' requirement flowing from changed budgetary priorities
Risk Differential |  | 10 | Difference between the risk allowed for in the msot likely (50%) and highest acceptable (90%) estimates at Main Gate (-10 months)
Total | 16 | -10
Net Variation | 6
Duration of Assessment Phase
Date
Date of Main Gate Approval | 2000-05-01
Target Date for Main Gate Approval at Initial Gate | 1999-06-01
Variation (months) | 11
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Most Likely | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Forecast ISD at Initial Gate | - | 2007-12-01 | -
2003
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2002/2003 | 9
Reasons for variations from approved ISD
Factor | Increase (months) | Decrease (months) | Explanation
Changed Budgetary Priorities | 16 |  | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Procurement Strategy | 9 |  | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Risk Differential | 16 | 10 | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Total | 25 | -10
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Most Likely | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Forecast ISD at Initial Gate | - | 2007-12-01 | -
2004
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2003/2004 | 0
Reasons for variations from approved ISD
Factor | Increase (months) | Decrease (months) | Explanation
Changed Budgetary Priorities | 16 |  | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Procurement Strategy | 9 |  | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Risk Differential | 16 | 10 | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Total | 25 | -10
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Most Likely | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Forecast ISD at Initial Gate | - | 2007-12-01 | -
2005
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2004/2005 | 0
Reasons for Variation from approved ISD
Date | Variation (months) | Factor | Explanation
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Most Likely | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Forecast ISD at Initial Gate | - | 2007-12-01 | -
2006
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2004/2005 | 0
Reasons for Variation from approved ISD
Date | Variation (months) | Factor | Explanation
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Budgeted For | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Envelope within which capability was expected to be available at Initial Gate | - | - | 2007-12-01
2007
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2004/2005 | 0
Reasons for Variation from approved ISD
Date | Variation (months) | Factor | Explanation
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Budgeted For | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Envelope within which capability was expected to be available at Initial Gate | - | 2007-12-01 | -
2008
Performance against approved in-service date
Date
Current forcase ISD | 2011-12-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 24
In-year changes in 2004/2005 | 9
Reasons for Variation from approved ISD
Date | Variation (months) | Factor | Explanation
2008-02-01 | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 24
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Budgeted For | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Envelope within which capability was expected to be available at Initial Gate | - | 2007-12-01 | -
2009
Planned/Actual Boundaries for introduction of the capability
Description | Earliest Forecast / Approved | Budgeted For (Post-Main Investment Decision Projects only) | Latest Forecast / Approved
A400M |  | 2009-02-01 | 2009-12-01
Progress against approved Dates
Description | Approved Date | Actual / Forecast Date | Variation | In-Year Variation
A400M | 2009-12-01 | 2015-12-01 | 72 | 48
Timescale Variation
Date | Variation (months) | Factor | Explanation
2009-03-01 | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
2009-01-01 | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
2008-10-01 | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
2008-09-01 | *** | Technical Factors | Reflects lateste delay and risk assessment beyond first flight
2008-02-01 | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 24
2010
Duration of the Assessment Phase
Description | Forecast / Actual Date of Main Gate Approval | Date of Initial Gate Approval | Length of Assessment Phase (Months)
A400m | 2000-05-01 | 1997-07-01 | 35
Planned/Actual Boundaries for introduction of the capability
Description | Earliest Forecast / Approved | Budgeted For (Post-Main Investment Decision Projects only) | Latest Forecast / Approved
A400M |  | 2009-02-01 | 2009-12-01
Progress against approved Dates
Description | Approved Date | Actual / Forecast Date | Variation | In-Year Variation
A400M | 2009-12-01 | 2015-03-01 | 63 | -9
Timescale Variation
Date | Variation (months) | Factor | Explanation
2010-03-01 | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
2009-03-01 | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects lateste delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 24
2011
Duration of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Planned/Actual Boundaries for introduction of the capability
Description | Earliest Forecast / Approved | Budgeted For (Post-Main Investment Decision Projects only) | Latest Forecast / Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic | 9 | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation | 73
2012
Length of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Actual Boundaries for In Service Date or Initial Operating Capability
Project/Increment Title | Earliest Approved | Budgeted For | Latest Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic | 9 | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation | 73
2013
Length of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Actual Boundaries for In Service Date or Initial Operating Capability
Project/Increment Title | Earliest Approved | Budgeted For | Latest Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic | 9 | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation | 73
2014
Length of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Actual Boundaries for In Service Date or Initial Operating Capability
Project/Increment Title | Earliest Approved | Budgeted For | Latest Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic | 9 | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation
2015
Length of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Actual Boundaries for In Service Date or Initial Operating Capability
Project/Increment Title | Earliest Approved | Budgeted For | Latest Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
2015-01-01 | 6 | Technical Factors | Updated programme estimate based on an assessment of the Airbus Defence & Space revised delivery schedule
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic |  | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation | 79

## JSF
2009-12-01
Milestones | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1997-05-01 | 1996-11-01
Milestone B | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-10-01 | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2004-04-01 | 2005-10-01 | 2006-04-01 | 2006-02-01
CDR (STOVL&Common) | 2004-10-01 | 2006-05-01 | 2006-11-01 | 2006-02-01
CDR (CV&Common) | 2005-07-01 | 2007-01-01 | 2007-07-01 | 2007-06-01
DAE (IPR 1) | 2005-04-01 | 2006-01-01 | 2006-07-01 | 2006-03-01
1st Flt CTOL | 2005-11-01 | 2006-07-01 | 2007-01-01 | 2006-12-01
1st Flt STOVL | 2006-04-01 | 2008-03-01 | 2008-09-01 | 2008-06-01
1st Flt CV | 2007-01-01 | 2009-04-01 | 2009-10-01 | MAY 2010 1
DAE (IPR 2) | 2006-04-01 | 2007-01-01 | 2007-07-01 | 2007-04-01
1st Production Aircraft Delivered | N/A | 2010-01-01 | 2010-07-01 | OCT 2010 1
1st Operational Aircraft Delivered | 2008-06-01 | N/A | N/A | N/A
USMC IOC | 2010-04-01 | 2012-03-01 | 2012-09-01 | 2012-03-01
USAF IOC | 2011-06-01 | 2013-03-01 | 2013-09-01 | 2013-03-01
Completed IOT&E | 2012-03-01 | 2013-10-01 | 2014-04-01 | APR 2016 1
USN IOC | 2012-04-01 | 2015-03-01 | 2015-09-01 | 2015-03-01
DAB Milestone C | 2012-04-01 | 2013-10-01 | 2014-04-01 | APR 2016 1
APB Breach
2010-12-01
Milestones | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | N/A | N/A | 1996-11-01
Milestone B | 2001-10-01 | N/A | N/A | 2001-10-01
EMD Contract Award | 2001-10-01 | N/A | N/A | 2001-10-01
Preliminary Design Review | 2003-04-01 | N/A | N/A | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2004-04-01 | N/A | N/A | 2006-02-01
CDR (STOVL&Common) | 2004-10-01 | N/A | N/A | 2006-02-01
CDR (CV&Common) | 2005-07-01 | N/A | N/A | 2007-06-01
DAE (IPR 1) | 2005-04-01 | N/A | N/A | 2006-03-01
1st Flt CTOL | 2005-11-01 | N/A | N/A | 2006-12-01
1st Flt STOVL | 2006-04-01 | N/A | N/A | 2008-06-01
1st Flt CV | 2007-01-01 | N/A | N/A | 2010-06-01
DAE (IPR 2) | 2006-04-01 | N/A | N/A | 2007-04-01
1st Production Aircraft Delivered | N/A | N/A | N/A | 2011-04-01
1st Operational Aircraft Delivered | 2008-06-01 | N/A | N/A | N/A
USMC IOC | 2010-04-01 | N/A | N/A | TBD
USAF IOC | 2011-06-01 | N/A | N/A | TBD
Completed IOT&E | 2012-03-01 | N/A | N/A | TBD
USN IOC | 2012-04-01 | N/A | N/A | TBD
DAB Milestone C | 2012-04-01 | N/A | N/A | TBD
2011-12-01
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1997-05-01 | 1996-11-01
Milestone B | 2010-11-01 | 2011-11-01 | 2012-05-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-10-01 | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2005-10-01 | 2005-10-01 | 2006-04-01 | 2006-02-01
CDR (STOVL&Common) | 2006-05-01 | 2006-05-01 | 2006-11-01 | 2006-02-01
CDR (CV&Common) | 2007-01-01 | 2007-01-01 | 2007-07-01 | 2007-06-01
DAE (IPR 1) | 2006-01-01 | 2006-01-01 | 2006-07-01 | 2006-03-01
1st Flt CTOL | 2006-07-01 | 2006-07-01 | 2007-01-01 | 2006-12-01
DAE (IPR 2) | 2007-01-01 | 2007-01-01 | 2007-07-01 | 2007-04-01
1st Flt STOVL | 2008-03-01 | 2008-03-01 | 2008-09-01 | 2008-06-01
1st Flt CV | 2010-05-01 | 2010-05-01 | 2010-11-01 | 2010-06-01
1st Production Aircraft Delivered | 2010-12-01 | 2010-12-01 | 2011-06-01 | 2011-05-01
Block 2B Fleet Release | N/A | 2015-03-01 | 2015-09-01 | 2015-03-01
Block 3F Fleet Release | N/A | 2017-08-01 | 2018-02-01 | 2017-08-01
Completed IOT&E | 2016-04-01 | 2019-02-01 | 2019-08-01 | 2019-02-01
Full Rate Production Decision | N/A | 2019-04-01 | 2019-10-01 | 2019-04-01
DAB Milestone C | 2016-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
USMC IOC | 2012-12-01 | TBD | TBD | TBD
USAF IOC | 2016-04-01 | TBD | TBD | TBD
USN IOC | 2016-04-01 | TBD | TBD | TBD
2012-12-01
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1997-05-01 | 1996-11-01
Milestone B | 2011-11-01 | 2011-11-01 | 2012-05-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-10-01 | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2005-10-01 | 2005-10-01 | 2006-04-01 | 2006-02-01
CDR (STOVL&Common) | 2006-05-01 | 2006-05-01 | 2006-11-01 | 2006-02-01
CDR (CV&Common) | 2007-01-01 | 2007-01-01 | 2007-07-01 | 2007-06-01
DAE (IPR 1) | 2006-01-01 | 2006-01-01 | 2006-07-01 | 2006-03-01
1st Flt CTOL | 2006-07-01 | 2006-07-01 | 2007-01-01 | 2006-12-01
DAE (IPR 2) | 2007-01-01 | 2007-01-01 | 2007-07-01 | 2007-04-01
1st Flt STOVL | 2008-03-01 | 2008-03-01 | 2008-09-01 | 2008-06-01
1st Flt CV | 2010-05-01 | 2010-05-01 | 2010-11-01 | 2010-06-01
1st Production Aircraft Delivered | 2010-12-01 | 2010-12-01 | 2011-06-01 | 2011-05-01
Block 2B Fleet Release | 2015-03-01 | 2015-03-01 | 2015-09-01 | 2015-06-01
Block 3F Fleet Release | 2017-08-01 | 2017-08-01 | 2018-02-01 | 2017-08-01
Completed IOT&E | 2019-02-01 | 2019-02-01 | 2019-08-01 | 2019-02-01
Full Rate Production Decision | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
DAB Milestone C | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
USMC IOC | TBD | TBD | TBD | TBD
USAF IOC | TBD | TBD | TBD | TBD
USN IOC | TBD | TBD | TBD | TBD
2013-12-01
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1996-11-01 | 1996-11-01
Milestone B | 2001-10-01 | 2001-10-01 | 2001-10-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2001-10-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-04-01 | 2003-04-01
CDR
CDR (CTOL&Common) | 2006-02-01 | 2006-02-01 | 2006-02-01 | 2006-02-01
CDR (STOVL&Common) | 2006-02-01 | 2006-02-01 | 2006-02-01 | 2006-02-01
CDR (CV&Common) | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-01
DAE (IPR 1) | 2006-03-01 | 2006-03-01 | 2006-03-01 | 2006-03-01
1st Flt CTOL | 2006-12-01 | 2006-12-01 | 2006-12-01 | 2006-12-01
DAE (IPR 2) | 2007-04-01 | 2007-04-01 | 2007-04-01 | 2007-04-01
1st Flt STOVL | 2008-06-01 | 2008-06-01 | 2008-06-01 | 2008-06-01
1st Flt CV | 2010-06-01 | 2010-06-01 | 2010-06-01 | 2010-06-01
1st Production Aircraft Delivered | 2011-05-01 | 2011-05-01 | 2011-05-01 | 2011-05-01
Milestone B Re-approval | 2012-03-01 | 2012-03-01 | 2012-03-01 | 2012-03-01
Block 2B Fleet Release | 2015-03-01 | 2015-03-01 | 2015-09-01 | 2015-06-01
USMC IOC | TBD | TBD | TBD | 2015-07-01
USAF IOC | TBD | TBD | TBD | 2016-08-01
Block 3F Fleet Release | 2017-08-01 | 2017-08-01 | 2018-02-01 | 2017-08-01
USN IOC | TBD | TBD | TBD | 2018-08-01
Completed IOT&E | 2019-02-01 | 2019-02-01 | 2019-08-01 | 2019-02-01
Full Rate Production Decision | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
DAB Milestone C | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
2014-12-01
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1996-11-01 | 1996-11-01
Milestone B | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2001-10-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-03-01 | 2003-03-01 | 2003-03-01
CDR
CDR (CTOL&Common) | 2006-02-01 | 2006-02-01 | 2006-02-01 | 2006-02-01
CDR (STOVL&Common) | 2006-02-01 | 2006-02-01 | 2006-02-01 | 2006-02-01
CDR (CV&Common) | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-01
DAE (IPR 1) | 2006-03-01 | 2006-03-01 | 2006-03-01 | 2006-03-01
1st Flt CTOL | 2006-12-01 | 2006-12-01 | 2006-12-01 | 2006-12-01
DAE (IPR 2) | 2007-04-01 | 2007-04-01 | 2007-04-01 | 2007-04-01
1st Flt STOVL | 2008-06-01 | 2008-06-01 | 2008-06-01 | 2008-06-01
1st Flt CV | 2010-06-01 | 2010-05-01 | 2010-05-01 | 2010-05-01
1st Production Aircraft Delivered | 2011-05-01 | 2011-05-01 | 2011-05-01 | 2011-05-01
Milestone B Re-approval | 2012-03-01 | 2011-11-01 | 2012-05-01 | 2012-03-01
Block 2B Fleet Release | 2015-03-01 | 2015-03-01 | 2015-09-01 | 2015-06-01
USMC IOC | TBD | 2015-07-01 | 2015-12-01 | 2015-07-01
USAF IOC | TBD | 2016-08-01 | 2016-12-01 | 2016-08-01
Block 3F Fleet Release | 2017-08-01 | 2017-08-01 | 2018-02-01 | 2017-08-01
USN IOC | TBD | 2018-08-01 | 2019-02-01 | 2018-08-01
Completed IOT&E | 2019-02-01 | 2019-02-01 | 2019-08-01 | 2019-02-01
Full Rate Production Decision | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
DAB Milestone C | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01

## MEADS
2010
FIRE UNIT
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | 2004-08-01 | 2004-08-01 | 2005-02-01 | 2004-08-01
Design & Development Contract Award | 2004-09-01 | 2004-09-01 | 2005-03-01 | 2004-09-01
Acquisition Increment 1
Milestone C | 2007-10-01 | 2007-10-01 | 2008-10-01 | 2007-10-01
FUE | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
IOT&E
Start | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
Complete | 2009-09-01 | 2009-09-01 | 2010-09-01 | 2009-09-01
Full Rate Production Decision | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Acquisition Increment 2
Milestone C | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Lightweight Launcher FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2011-03-01
IOT&E
Start | 2011-06-01 | 2011-06-01 | 2012-06-01 | 2011-06-01
Complete | 2011-09-01 | 2011-09-01 | 2012-09-01 | 2011-09-01
Full Rate Production Decision | 2011-11-01 | 2011-11-01 | 2012-11-01 | 2011-11-01
Acquisition Increment 3
Milestone C | 2012-11-01 | 2012-11-01 | 2013-11-01 | 2012-11-01
FUE | 2015-09-01 | 2015-09-01 | 2016-09-01 | 2015-09-01
IOT&E
Start | 2016-06-01 | 2016-06-01 | 2017-06-01 | 2016-06-01
Complete | 2016-12-01 | 2016-12-01 | 2017-12-01 | 2016-12-01
Full Rate Production Decision | 2017-03-01 | 2017-03-01 | 2018-03-01 | 2017-03-01
IOC | 2017-09-01 | 2017-09-01 | 2018-09-01 | 2017-09-01
Missile
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSU First Intercept | 2008-06-01 | 2008-06-01 | 2009-06-01 | 2010-02-01
MSU FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2014-09-01
APB Breach
2011
Fire Unit
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | 2004-08-01 | 2004-08-01 | 2005-02-01 | 2004-08-01
Design & Development Contract Award | 2004-09-01 | 2004-09-01 | 2005-03-01 | 2004-09-01
Acquisition Increment 1
Milestone C | 2007-10-01 | 2007-10-01 | 2008-10-01 | 2007-10-01
FUE | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
IOT&E
Start | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
Complete | 2009-09-01 | 2009-09-01 | 2010-09-01 | 2009-09-01
Full Rate Production Decision | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Acquisition Increment 2
Milestone C | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Lightweight Launcher FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2011-03-01
IOT&E
Start | 2011-06-01 | 2011-06-01 | 2012-06-01 | 2011-06-01
Complete | 2011-09-01 | 2011-09-01 | 2012-09-01 | 2011-09-01
Full Rate Production Decision | 2011-11-01 | 2011-11-01 | 2012-11-01 | 2011-11-01
Acquisition Increment 3
Milestone C | 2012-11-01 | 2012-11-01 | 2013-11-01 | 2012-11-01
FUE | 2015-09-01 | 2015-09-01 | 2016-09-01 | 2015-09-01
IOT&E
Start | 2016-06-01 | 2016-06-01 | 2017-06-01 | 2016-06-01
Complete | 2016-12-01 | 2016-12-01 | 2017-12-01 | 2016-12-01
Full Rate Production Decision | 2017-03-01 | 2017-03-01 | 2018-03-01 | 2017-03-01
IOC | 2017-09-01 | 2017-09-01 | 2018-09-01 | 2017-09-01
Missile
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSU First Intercept | 2008-06-01 | 2008-06-01 | 2009-06-01 | 2010-02-01
MSU FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2015-09-01
APB Breach
2012
FIRE UNIT
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | 2004-08-01 | 2004-08-01 | 2005-02-01 | 2004-08-01
Design & Development Contract Award | 2004-09-01 | 2004-09-01 | 2005-03-01 | 2004-09-01
Acquisition Increment 1
Milestone C | 2007-10-01 | 2007-10-01 | 2008-10-01 | 2007-10-01
FUE | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
IOT&E
Start | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
Complete | 2009-09-01 | 2009-09-01 | 2010-09-01 | 2009-09-01
Full Rate Production Decision | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Acquisition Increment 2
Milestone C | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Lightweight Launcher FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2011-03-01
IOT&E
Start | 2011-06-01 | 2011-06-01 | 2012-06-01 | 2011-06-01
Complete | 2011-09-01 | 2011-09-01 | 2012-09-01 | 2011-09-01
Full Rate Production Decision | 2011-11-01 | 2011-11-01 | 2012-11-01 | 2011-11-01
Acquisition Increment 3
Milestone C | 2012-11-01 | 2012-11-01 | 2013-11-01 | 2012-11-01
FUE | 2015-09-01 | 2015-09-01 | 2016-09-01 | 2015-09-01
IOT&E
Start | 2016-06-01 | 2016-06-01 | 2017-06-01 | 2016-06-01
Complete | 2016-12-01 | 2016-12-01 | 2017-12-01 | 2016-12-01
Full Rate Production Decision | 2017-03-01 | 2017-03-01 | 2018-03-01 | 2017-03-01
IOC | 2017-09-01 | 2017-09-01 | 2018-09-01 | 2017-09-01
Missile
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSU First Intercept | 2008-06-01 | 2008-06-01 | 2009-06-01 | 2010-02-01
MSU FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2015-09-01
APB Breach
2013
Fire Unit
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Milestone B | 2004-08-01 | 2004-08-01 | 2005-02-01 | 2004-08-01
Design & Development Contract Award | 2004-09-01 | 2004-09-01 | 2005-03-01 | 2004-09-01
Acquisition Increment 1
Milestone C | 2007-10-01 | 2007-10-01 | 2008-10-01 | 2007-10-01
FUE | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
IOT&E
Start | 2009-03-01 | 2009-03-01 | 2010-03-01 | 2009-03-01
Complete | 2009-09-01 | 2009-09-01 | 2010-09-01 | 2009-09-01
Full Rate Production Decision | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Acquisition Increment 2
Milestone C | 2009-10-01 | 2009-10-01 | 2010-10-01 | 2009-10-01
Lightweight Launcher FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2011-03-01
IOT&E
Start | 2011-06-01 | 2011-06-01 | 2012-06-01 | 2011-06-01
Complete | 2011-09-01 | 2011-09-01 | 2012-09-01 | 2011-09-01
Full Rate Production Decision | 2011-11-01 | 2011-11-01 | 2012-11-01 | 2011-11-01
Acquisition Increment 3
Milestone C | 2012-11-01 | 2012-11-01 | 2013-11-01 | 2012-11-01
FUE | 2015-09-01 | 2015-09-01 | 2016-09-01 | 2015-09-01
IOT&E
Start | 2016-06-01 | 2016-06-01 | 2017-06-01 | 2016-06-01
Complete | 2016-12-01 | 2016-12-01 | 2017-12-01 | 2016-12-01
Full Rate Production Decision | 2017-03-01 | 2017-03-01 | 2018-03-01 | 2017-03-01
IOC | 2017-09-01 | 2017-09-01 | 2018-09-01 | 2017-09-01
Missile
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Acquisition Increment 2
MSU First Intercept | 2008-06-01 | 2008-06-01 | 2009-06-01 | 2010-02-01
MSU FUE | 2011-03-01 | 2011-03-01 | 2012-03-01 | 2015-09-01

## SM-3 Block IIA
2010
2011
2012
2013
2014
2015

## AGS
2011
| Start |  | End
Events | Quarter | Year | Quarter | Year
Prime Contract Proposal Review/Negotiations | 3 | 2010 | 3 | 2011
Contract Award | 3 | 2011 | 3 | 2011
Design, Development and Demonstration Phase | 3 | 2011 | 1 | 2015
Production Phase | 2 | 2015 | 4 | 2016
2012 - USAF
| Start |  | End
Events | Quarter | Year | Quarter | Year
Design/Development | 2 | 2012 | 2 | 2012
Flight Test | 3 | 2012 | 2 | 2016
Aircraft Delivery | 3 | 2015 | 1 | 2016
Aircraft Delivery | 2 | 2016 | 4 | 2016
Ground Station Delivery | 4 | 2015 | 2 | 2017
2012 - Defense Wide
| Start |  | End
Events | Quarter | Year | Quarter | Year
Contract Award | 3 | 2011 | 3 | 2011
Design, Development and Demonstration Phase | 3 | 2011 | 1 | 2015
Production Phase | 2 | 2015 | 4 | 2016
2013
| Start |  | End
Events | Quarter | Year | Quarter | Year
Contract Award | 3 | 2012 | 3 | 2012
IOC | 1 | 2017 | 1 | 2017
FOC | 3 | 2017 | 3 | 2017
Flight Test | 4 | 2015 | 3 | 2016
Aircraft Delivery | 4 | 2016 | 2 | 2017
Ground Station Delivery | 4 | 2016 | 3 | 2017
Design and Development Maritime Mode | 3 | 2012 | 3 | 2015
Test and Evaluation Support | 1 | 2012 | 3 | 2017
Tech Support | 1 | 2012 | 4 | 2018
2014
2015
| Start |  | End
Events | Quarter | Year | Quarter | Year
IOC | 1 | 2017 | 1 | 2017
FOC | 3 | 2017 | 3 | 2017
Design and Development - AGS | 1 | 2014 | 1 | 2017
Design and Development - Maritime Mode | 1 | 2014 | 3 | 2015
Test and Evaluation Support | 1 | 2014 | 3 | 2017
Flight Test | 3 | 2015 | 3 | 2016
Tech Support | 1 | 2014 | 4 | 2017
Aircraft Delivery | 4 | 2016 | 2 | 2017
Ground Station Delivery | 4 | 2016 | 3 | 2017

## LW155
1998
1999 - USMC
2000 - USMC
2001 USMC
2002 USMC
2003 USMC
| FY 2002 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009
Complete Development Testing (EMD Guns) | bar: FY 2002
Operational Assessment | bar: FY 2002
Pilot Production (PP) Guns (Qty 2) | bar: FY 2002 to FY 2003
Milestone C | bar: FY 2003
LRIP Contract Award | bar: FY 2003
Complete Development Testing (PP Guns) | bar: FY 2003
MOT&E | bar: FY 2004
Full Rate Production Decision | bar: FY 2005
IOC | bar: FY 2005
FOC | bar: FY 2008
1997 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2002: FY 1996; FY 2003: FY 1997; FY 2004: FY 1998; FY 2005: FY 1999
P3I Integration Efforts on the LW155 | bar: FY 2003
Perform Laser Ignition Integration | bar: FY 2003
Initiate/Develop Component Simulations | bar: FY 2003
Conduct Trade Off Study | bar: FY 2003
Initiate Evaluation of Automated FC | bar: FY 2005
1999 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 1996 | FY 1997 | FY 1998 | FY 1999 | FY 2000 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005
MS I/II | FY 2000: 1st Qtr
Contract Awar | FY 2000: 2nd Qtr
Developmental Testing Begins | FY 2001: 1st Qtr
Developmental Testing Ends | FY 2002: 4th Qtr
Multi-service Operational Testing Begins | FY 2003: 1st Qtr
Multi-Service Operational Testing Ends | FY 2003: 2nd Qtr
Milestone III | FY 2003: 4th Qtr
Production | FY 2004: 1st Qtr
2000 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 1996 | FY 1997 | FY 1998 | FY 1999 | FY 2000 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005
Towed Artillery Digitization (TAD) Milestone I/II | FY 2000: 1st Qtr
TAD System Contract Award | FY 2000: 3rd Qtr
TAD System Developmental Testing Begins | FY 2001: 2nd Qtr
TAD System Developmental Testing Ends | FY 2002: 4th Qtr
TAD Milti-service Operational Testing Begins | FY 2003: 1st Qtr
TAD Milti-service Operational Testing Ends | FY 2003: 2nd Qtr
TAD System Milestone III | FY 2003: 4th Qtr
Production of LW155 Howitzer with TAD System | FY 2004: 1st Qtr
2001 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2000 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007
Towed Artillery Digitization (TAD) Milestone I/II | 1Q |  |  | 0 | 0 | 0 | 0 | 0
TAD Contract Award | 2Q |  |  | 0 | 0 | 0 | 0 | 0
TAD Developmental Testing Begins |  | 4Q |  | 0 | 0 | 0 | 0 | 0
TAD Developmental Testing Ends |  |  | 4Q | 0 | 0 | 0 | 0 | 0
TAD Multi-service Operational Test |  |  |  | 0 | 0 | 0 | 0 | 0
TAD Milestone III |  |  |  | 0 | 0 | 0 | 0 | 0
2002 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007
TAD Design | FY 2000: 1-4Q; FY 2001: 1-4Q; FY 2002: 1-2Q
TAD Technical Testing | FY 2002: 2-4Q
Begin Technical Testing and Conduct Logistics Demonstration | FY 2003: 1-2Q
TAD Multi-service Operational Test | bar: FY 2003
TAD Milestone C | bar: FY 2003
2003 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2002 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009
Novated TAD Contract (General Dynamics) to M777E1 Contract (BAE Systems) | bar: FY 2002
Design Verification and Testing | FY 2003: 1-4Q; FY 2004: 1-3Q
Operational Test | bar: FY 2004
Full Rate Production Decision | bar: FY 2005
Initial Operational Capability | bar: FY 2006
2004 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009
System Development and Demonstration | FY 2002: 1-3Q
Design Verification and Test / Technical Testing | FY 2002: 2-4Q; FY 2003: 1-3Q
Artic Operational Test and Evaluation (M777E1) | bar: FY 2003
Joint Operational Test and Evaluation (M777E1) | bar: FY 2003
Milestone C | bar: FY 2004
Full Rate Production Decision | bar: FY 2004
Initial Operational Capability | bar: FY 2005
2007 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011
IBR | bar: FY 2004
Trade Study / Downselect | bar: FY 2004
Software Requirements Definition | bar: FY 2004
Preliminary Design | FY 2004: 2Q - 4Q
Preliminary Design Review | bar: FY 2005
Detailed Design | FY 2005: 1Q - 4Q
Component Qualification Testing | FY 2006: 1Q - 2Q
Coding and Unit Test | FY 2006: 2Q - 3Q
Coding Complete | bar: FY 2006
Integration and Engineering Evaluation Test | FY 2006: 3Q - 4Q
Software Formal Qualification Test | bar: FY 2006
2008 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011
IBR | bar: FY 2003
Trade Study / Downselect | bar: FY 2003
Software Requirements Definition | bar: FY 2003
Preliminary Design | FY 2003: 2Q - 4Q
Preliminary Design Review | bar: FY 2004
Detailed Design | FY 2004: 1Q - 4Q
Component Qualification Testing | FY 2005: 1Q - 2Q
Coding and Unit Test | FY 2005: 2Q - 3Q
Coding Complete | bar: FY 2005
Integration and Engineering Evaluation Test | FY 2005: 3Q - 4Q
Software Formal Qualification Test | bar: FY 2005
2009 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2002: FY 2008; FY 2003: FY 2009; FY 2004: FY 2010; FY 2005: FY 2011
IBR | bar: FY 2002
Trade Study / Downselect | bar: FY 2002
Software Requirements Definition | bar: FY 2002
Preliminary Design | FY 2002: 2Q - 4Q
Preliminary Design Review | bar: FY 2003
Detailed Design | FY 2003: 1Q - 4Q
Component Qualification Testing | FY 2004: 1Q - 2Q
Coding and Unit Test | FY 2004: 2Q - 3Q
Coding Complete | bar: FY 2004
Integration and Engineering Evaluation Test | FY 2004: 3Q - 4Q
Software Formal Qualification Test | bar: FY 2004
2010 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2002: FY 2009; FY 2003: FY 2010; FY 2004: FY 2011; FY 2005: FY 2012
Component Qualification Testing | bar: FY 2002 to FY 2003
Coding and Unit Test | FY 2003: Q1-Q2
Coding Complete | bar: FY 2003
Integration and Engineering Evaluation Test | FY 2003: Q2-Q3
Software Formal Qualification Test | bar: FY 2003
2015 - Army | FY 2002: Start; FY 2004: End
Budget Activity 5 - Engineering and Manufacturing Development | FY 2002: Quarter; FY 2003: Year; FY 2004: Quarter; FY 2005: Year
Schedule Profile - Project D509
Feasibility and Concept Studies | FY 2002: 1; FY 2003: 2015; FY 2004: 2; FY 2005: 2016
Preliminary Designs | FY 2002: 2; FY 2003: 2016; FY 2004: 1; FY 2005: 2018
Fabrication Prototypes | FY 2002: 2; FY 2003: 2018; FY 2004: 2; FY 2005: 2019
Technology Demonstrator | FY 2002: 3; FY 2003: 2019; FY 2004: 2; FY 2005: 2020
Test and Evaluation | FY 2002: 3; FY 2003: 2020; FY 2004: 2; FY 2005: 2021
2016 - Army | FY 2002: Start; FY 2004: End
Budget Activity 5 - Engineering and Manufacturing Development | FY 2002: Quarter; FY 2003: Year; FY 2004: Quarter; FY 2005: Year
Schedule Profile - Project D509
M777 Engineering Tools Development & Validation | FY 2002: 1; FY 2003: 2015; FY 2004: 2; FY 2005: 2016
XM907 Common Cannon Assembly Support | FY 2002: 1; FY 2003: 2015; FY 2004: 2; FY 2005: 2019
Objective M777ER Design, Analysis & Drawings | FY 2002: 1; FY 2003: 2015; FY 2004: 2; FY 2005: 2018
Objective M777ER Component Fabrication | FY 2002: 2; FY 2003: 2018; FY 2004: 2; FY 2005: 2019
Integration | FY 2002: 2; FY 2003: 2019; FY 2004: 2; FY 2005: 2020