## Pg 80
F-35 Aircraft
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -82.3
Adjustment for current and prior escalation. (Estimating) | 46 | 47.5
Realignment of costs between Aircraft subprogram and Engine subprogram (Air Force) (Estimating) | -174.9 | -155
Increase due to realignment of program funding and Actual Funding Investment (AirForce) (Estimating) | +5.1 | 16.9
Realignment of costs between Aircraft subprogram and Engine subprogram (Navy) (Estimating) | -21.9 | -22.7
Decrease due to realignment of program funding, Congressional reductions and Actual Funding Investment (Navy) (Estimating) | -368.1 | -364.1
Realignment of costs between Aircraft subprogram and Engine subprogram (International) (Estimating) | -35 | -28.4
RDT&E Subtotal | -548.8 | -588.1
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -426
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended program from FY 2037 to FY 2038 (Air Force) (Schedule) | 0 | +158.3
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended program from FY 2032 to FY 2033 (Navy) (Schedule) | 0 | +880.8
Adjustment for current and prior escalation. (Estimating) | +160.6 | +167.1
Revised estimate of subcontractor cost due to the incorporation of the latest actuals from early LRIP lots (Air Force) (Estimating) | -516.3 | -759.5
Revised estimate of subcontractor cost due to the incorporation of the latest actuals from early LRIP lots (Navy) (Estimating) | -189.1 | -347
Revised estimate of Airframe cost due to the incorporation of the latest actuals from early LRIP lots (Air Force) (Estimating) | +899.5 | +1323.5
Revised estimate of Airframe cost due to the incorporation of the latest actuals from early LRIP lots (Navy) (Estimating) | -379.6 | -695.7
Increase due to the incorporation of latest Prime and subcontractor Labor Rates and exchange rates (Air Force) (Estimating) | +2386.5 | +3512.6
Increase due to the incorporation of latest Prime and subcontractor Labor Rates and exchange rates (Navy) (Estimating) | +854.2 | +1563.8
Increase due to slower International Partner (IP) procurement quantity profile (Air Force) (Estimating) | +566.1 | +832.9
Increase due to slower IP procurement quantity profile (Navy) (Estimating) | +104.4 | 191.4
Updated methodologies, material costs, and learning curves (Air Force) (Estimating) | -1381 | -2032.3
Updated methodologies, material costs, and learning curves (Navy) (Estimating) | +84.8 | 155.7
Adjustment for current and prior escalation. (Support) | +44.3 | 46.7
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Air Force) (Support) | -191.4 | -531.5
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Navy) (Support) | -724.6 | -943.8
Increase in Initial Spares due to revised estimate of required risk funding (Air Force) (Support) | +153.8 | +551.6
Increase in Initial Spares due to revised estimate of required risk funding (Navy) (Support) | -1.2 | +170.0
Procurement Subtotal | +1871 | +3818.6
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -14.4
Adjustment for current and prior escalation. (Estimating) | 8.6 | +9.1
Increase due to revised estimate of MILCON requirements (Air Force) (Estimating) | 23.1 | +64.4
Decrease due to revised estimate of MILCON requirements (Navy) (Estimating) | -227.6 | -238.3
MILCON Subtotal | -195.9 | -179.2
F-35 Engine
RDT&E | $M
Current Change Explanations | Base Year
Revised escalation indices. (Economic) | N/A | -11.7
Adjustment for current and prior escalation. (Estimating) | +8.7 | +8.9
Realignment of costs between Aircraft subprogram and Engine subprogram (Air Force) (Estimating) | +174.4 | +155
Decrease due to realignment of program funding, Congressional Reductions, and Actual Funding Investment (Air Force) (Estimating) | -104.7 | -108.4
Realignment of costs between Aircraft subprogram and Engine subprogram (Navy) (Estimating) | +21.9 | +22.7
Decrease due to realignment of program funding, Congressional Reductions, and Actual Funding Investment (Navy) (Estimating) | +191.7 | +208.6
Realignment of costs between Aircraft subprogram and Engine subprogram (International) (Estimating) | +30.7 | +27.7
Realignment of cost between Aircraft subprogram and Engine subprogram (International) (Estimating) | +0.9 | 0
RDT&E Subtotal | +323.6 | +302.8
Procurement | $M
Current Change Explanations | Base Year
Revised escalation indices. (Economic) | N/A | -79.8
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended program from FY 2037 to FY 2038 (Air Force) (Schedule) | 0 | +30
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended program from FY 2032 to FY 2033 (Navy) (Schedule) | 0 | +166.1
Adjustment for current and prior escalation. (Estimating) | +26 | +27.5
Updated exchange rates (Air Force) (Estimating) | +944.7 | +1384.5
Updated exchange rates (Navy) (Estimating) | +253.8 | +350.8
Increase due to incorporation of latest actual costs from LRIP lots (Air Force) (Estimating) | +630.6 | +923.8
Increase due to incorporation of latest actual costs from LRIP lots (Navy) (Estimating) | +591.8 | +818
Increase due to slower International procurement quantity profile (Air Force) (Estimating) | +57.1 | +83.4
Increase due to slower International procurement quantity profile (Navy) (Estimating) | +13.8 | +18.9
Adjustment for current and prior escalation. (Support) | +8.5 | +8.4
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Air Force) (Support) | +2.0 | -34.6
Increase in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Navy) (Support) | +23.4 | +3.0
Increase in Initial Support due to revised estimate of required risk funding (Air Force) (Support) | +59.2 | +239.6
Increase in Initial Support due to revised estimate of required risk funding (Navy) (Support) | +6.7 | +79.4
Procurement Subtotal | +2617.6 | +4019.0