## Pg 75
F-35 Aircraft
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) N/A -36.7 | N/A | -36.7
Adjustment for current and prior escalation. (Estimating) | +26.7 | +27.8
Realignment of cost between the aircraft subprogram and engine subprogram (Air Force(AF)). (Estimating) | +60.5 | +64.3
Realignment of cost between the aircraft subprogram and engine subprogram (Navy). (Estimating) | -44.4 | -46.2
Revised estimate for Small Business Innovation Research in FY 2015 (Navy). (Estimating) | -24.1 | -25.4
Revised estimate for additional operational testing requirements (AF). (Estimating) | +74.3 | +81.2
Revised estimate for additional operational testing requirements (Navy). (Estimating) | +147.7 | +161.7
Revised estimate to reflect application of new outyear inflation indices (Non- Treasury Funds). (Estimating) | 1.3 | 0.8
Increase due to realignment of program funding, congressional addition, and actual funding investment (AF). (Estimating) | 8.6 | 9.1
Decrease due to realignment of program funding, congressional reductions, and actual funding investment (AF). (Estimating) | -0.8 | -0.8
Increase due to realignment of program funding, congressional addition, and actual funding investment (Navy). (Estimating) | 6.7 | 7.5
RDT&E Subtotal | +256.5 | +243.3
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -1842.6
Adjustment for current and prior escalation. (Estimating) | +120.5 | +128.9
Stretch-out of procurement buy profile in FY 2016 to FY 2038 (Aircraft Procurement, AF (APAF)). (Schedule) | 0 | 1446
Acceleration of procurement buy profile in FY 2016 to FY 2031 (Aircraft Procurement, Navy (APN)). (Schedule) | 0 | -958.8
Revised estimate for International procurement quantity profile adjustments (APAF). (Estimating) | -128.1 | -160.6
Revised estimate for International procurement quantity profile adjustments (APN). (Estimating) | -18.1 | -23.7
Revised estimate of Airframe cost due to the incorporation of the latest prime and subcontractor actuals and labor/exchange rates (APAF). (Estimating) | 11.7 | 131.1
Revised estimate of Airframe cost due to the incorporation of the latest prime and subcontractor actuals and labor/exchange rates (APN). (Estimating) | 572.8 | 676.1
Update for fact of life changes for prior years/lots 2006-2016 (APAF). (Estimating) | -266.9 | -291.1
Update for fact of life changes for prior years/lots 2006-2016 (APN). (Estimating) | -71.4 | -75.5
Decrease based on revised estimating assumptions for Block Buy and Multi-Year Procurement (APN). (Estimating) | -733.8 | -922.1
Decrease based on revised estimating assumptions for Block Buy and Multi-Year Procurement (APAF). (Estimating) | -1259.9 | -1713.6
Revised estimate of non-recurring costs (APAF). (Estimating) | +224.3 | +254.6
Revised estimate of non-recurring costs (APN). (Estimating) | +199.2 | +122.8
Additional funding for Band 2/5 requirements (APAF) (Engineering) | +945.2 | +1313.8
Additional funding for Band 2/5 requirements (APN). (Engineering) | +401.2 | +513.0
Revised estimate for Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (APAF). (Support) | +1.8 | +92.0
Adjustment for current and prior escalation. (Support) | +25.7 | +27.1
Revised estimate for Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (APN). (Support) | -494.5 | -544.4
Revised estimate for Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (APAF). (Support) | -2480.8 | -3648.8
Revised estimate for Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (APN). (Support) | -470.4 | -664.1
Procurement Subtotal | -3421.5 | -6139.9
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -25.2
Adjustment for current and prior escalation. (Estimating) | 5.1 | 5.4
Revised estimate as a result of refined requirements (AF). (Estimating) | 313.1 | 361.9
Revised estimate as a result of refined requirements (AF). (Estimating) | -153.8 | -185.3
Revised estimate as a result of refined requirements ( Navy). (Estimating) | 7.6 | 9.4
MILCON Subtotal | 172 | 166.2
F-35 Engine
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -4.7
Adjustment for current and prior escalation. (Estimating) | +4.3 | +4.3
Realignment of cost between the engine subprogram and aircraft subprogram (AF). (Estimating) | -60.9 | -64.3
Realignment of cost between the engine subprogram and aircraft subprogram (Navy). (Estimating) | 43.4 | 46.2
Decrease due to realignment of program funding, congressional reductions, and actual funding investment (AF). (Estimating) | -0.2 | -0.2
RDT&E Subtotal | -13.4 | -18.7
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -373.1
Adjustment for current and prior escalation. (Estimating) | +17.8 | +19.0
Stretch-out of procurement buy profile in FY 2016 to FY 2038 (Engine Procurement, AF). (Schedule) | 0 | 293.2
Acceleration of procurement buy profile in FY 2016 to FY 2031 (Engine Procurement, Navy). (Schedule) | 0 | -194.7
Revised estimate for International procurement quantity adjustments (Engine Procurement, AF). (Estimating) | -9.2 | -12.5
Revised estimate for International procurement quantity adjustments (Engine Procurement, Navy). (Estimating) | -3.8 | -5.1
Revised estimate to reflect actuals (Engine Procurement, AF). (Estimating)
Revised estimate to reflect actuals (Engine Procurement, Navy). (Estimating)
Decrease based on revised estimating assumptions for Block Buy and Multi-Year Procurement (Engine Procurement, AF). (Estimating) | -457.1 | -643.3
Decrease based on revised estimating assumptions for Block Buy and Multi-Year Procurement (Engine Procurement, Navy). (Estimating) | -266.8 | -343
Update for fact of life changes for prior years/lots 2006-2016 (Engine Procurement, AF). (Estimating) | -47.9 | -52.1
Update for fact of life changes for prior years/lots 2006-2016 (Engine Procurement, Navy). (Estimating) | -127 | -138.3
Adjustment for current and prior escalation. (Support) | +4.8 | +5.0
Revised estimate for Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Engine Procurement, AF). (Support) | -17.7 | -11.6
Revised estimate for Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Engine Procurement, Navy). (Support) | -85.3 | -96.7
Revised estimate for Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Engine Procurement, AF). (Support) | -1143.5 | -1680.7
Revised estimate for Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans (Engine Procurement, Navy). (Support) | -166.3 | -236.3
Procurement Subtotal | -4078.3 | -6343.6