## Cost Summary
Total Acquisition Cost and Quantity - Total Program
| BY2004 $M |  |  |  | TY $M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 4992.3 | 4992.3 | -- | 3410.7 | 5737 | 5737 | 3897.7
Procurement | 17759.1 | 17759.1 | -- | 5908.6 | 24158.4 | 24158.4 | 8718.6
Flyaway | -- | -- | -- | 5397.5 | -- | -- | 7972.8
Recurring | -- | -- | -- | 5329.1 | -- | -- | 7889.6
Non Recurring | -- | -- | -- | 68.4 | -- | -- | 83.2
Support | -- | -- | -- | 511.1 | -- | -- | 745.8
Other Support | -- | -- | -- | 511.1 | -- | -- | 745.8
Initial Spares | -- | -- | -- | 0 | -- | -- | 0
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 22751.4 | 22751.4 | N/A | 9319.3 | 29895.4 | 29895.4 | 12616.3
Total Acquisition Cost and Quantity - Fire Unit
| BY2004 $M |  |  |  | TY $M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 4531.4 | 4531.4 | 5211.1 | 2708.8 | 5255 | 5255 | 3112.4
Procurement | 11999.1 | 11999.1 | 13199 | 0 | 16584.4 | 16584.4 | 0
Flyaway | -- | -- | -- | 0 | -- | -- | 0
Recurring | -- | -- | -- | 0 | -- | -- | 0
Non Recurring | -- | -- | -- | 0 | -- | -- | 0
Support | -- | -- | -- | 0 | -- | -- | 0
Other Support | -- | -- | -- | 0 | -- | -- | 0
Initial Spares | -- | -- | -- | 0 | -- | -- | 0
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 16530.5 | 16530.5 | N/A | 2708.8 | 21839.4 | 21839.4 | 3112.4
Quantity | SAR Baseline Dev Est | Current APB Development | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 48 | 48 | 0
Total | 48 | 48 | 0
Total Acquisition Cost and Quantity - Missile
| BY2004 $M |  |  |  | TY $M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 460.9 | 460.9 | 530 | 701.9 | 482 | 482 | 785.3
Procurement | 5760 | 5760 | 6336 | 5908.6 | 7574 | 7574 | 8718.6
Flyaway | -- | -- | -- | 0 | -- | -- | 7972.8
Recurring | -- | -- | -- | 0 | -- | -- | 7889.6
Non Recurring | -- | -- | -- | 0 | -- | -- | 83.2
Support | -- | -- | -- | 0 | -- | -- | 745.8
Other Support | -- | -- | -- | 0 | -- | -- | 745.8
Initial Spares | -- | -- | -- | 0 | -- | -- | 0
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 6220.9 | 6220.9 | N/A | 6610.5 | 8056 | 8056 | 9503.9
Quantity | SAR Baseline Dev Est | Current APB Development | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 1528 | 1528 | 1528
Total | 1528 | 1528 | 1528

## Funding Summary
Appropriation and Quantity Summary - Total Program
FY2015 President's Budget / December 2013 SAR (TY$ M)
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | Fy2019 | To Complete | Total
RDT&E | 3897.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3897.7
Procurement | 83.2 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 8718.6
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 3980.9 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 12616.3
PB 2014 Total | 4038.3 | 540.4 | 540.5 | 559.6 | 566.8 | 655.2 | 536.8 | 5394.4 | 12832 |  | CHECK THIS NUMBERS
Delta | -57.4 | 150 | -155.9 | -139.8 | -144.2 | -196.5 | -39.2 | 367.3 | -215.7
Appropriation and Quantity Summary - Fire Unit
FY2015 President's Budget / December 2013 SAR (TY$ M)
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | Fy2019 | To Complete | Total
RDT&E | 3112.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112.4
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 3112.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112.4
PB 2014 Total | 3165.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3165.1
Delta | -52.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -52.7
Quantity | Undistributed | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | Fy2019 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB2005 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB2004 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Appropriation and Quantity Summary - Missile
FY2015 President's Budget / December 2013 SAR (TY$ M)
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | Fy2019 | To Complete | Total
RDT&E | 785.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785.3
Procurement | 83.2 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 8718.6
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 868.5 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 9503.9
PB 2014 Total | 873.2 | 540.4 | 540.5 | 559.6 | 566.8 | 655.2 | 536.8 | 5394.4 | 9666.9
Delta | -4.7 | 150 | -155.9 | -139.8 | -144.2 | -196.5 | -39.2 | 367.3 | -163
Quantity | Undistributed | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | Fy2019 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | 0 | 0 | 86 | 70 | 76 | 80 | 88 | 94 | 1034 | 1528
PB2005 Total | 0 | 0 | 86 | 70 | 76 | 80 | 88 | 94 | 1034 | 1528
PB2004 Total | 0 | 0 | 56 | 72 | 80 | 82 | 104 | 108 | 1026 | 1528
Delta | 0 | 0 | 30 | -2 | -4 | -2 | -16 | -14 | 8 | 0

## Annual Funding by Appropriation
Annual Funding TY$ - Fire Unit
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2004 | -- | -- | -- | -- | -- | -- | 126.9
2005 | -- | -- | -- | -- | -- | -- | 164
2006 | -- | -- | -- | -- | -- | -- | 193
2007 | -- | -- | -- | -- | -- | -- | 211
2008 | -- | -- | -- | -- | -- | -- | 316.3
2009 | -- | -- | -- | -- | -- | -- | 423.7
2010 | -- | -- | -- | -- | -- | -- | 501.1
2011 | -- | -- | -- | -- | -- | -- | 450.6
2012 | -- | -- | -- | -- | -- | -- | 377.6
2013 | -- | -- | -- | -- | -- | -- | 348.2
Subtotal | -- | -- | -- | -- | -- | -- | 3112.4
Annual Funding BY$ Fire Unit
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2004 $M | Non End Item Recurring Flyaway BY 2004 $M | Non Recurring Flyaway BY 2004 $M | Total Flyaway BY 2004 $M | Total Support BY 2004 $M | Total Program BY 2004 $M
2004 | -- | -- | -- | -- | -- | -- | 124
2005 | -- | -- | -- | -- | -- | -- | 155.7
2006 | -- | -- | -- | -- | -- | -- | 178.3
2007 | -- | -- | -- | -- | -- | -- | 190.4
2008 | -- | -- | -- | -- | -- | -- | 280.1
2009 | -- | -- | -- | -- | -- | -- | 370.4
2010 | -- | -- | -- | -- | -- | -- | 431.5
2011 | -- | -- | -- | -- | -- | -- | 380.5
2012 | -- | -- | -- | -- | -- | -- | 313.8
2013 | -- | -- | -- | -- | -- | -- | 284.1
Subtotal | -- | -- | -- | -- | -- | -- | 2708.8
Annual Funding TY$ - Missile
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2004 | -- | -- | -- | -- | -- | -- | 109.9
2005 | -- | -- | -- | -- | -- | -- | 87.3
2006 | -- | -- | -- | -- | -- | -- | 81.4
2007 | -- | -- | -- | -- | -- | -- | 111.9
2008 | -- | -- | -- | -- | -- | -- | 53.5
2009 | -- | -- | -- | -- | -- | -- | 31
2010 | -- | -- | -- | -- | -- | -- | 65.1
2011 | -- | -- | -- | -- | -- | -- | 121.5
2012 | -- | -- | -- | -- | -- | -- | 86.1
2013 | -- | -- | -- | -- | -- | -- | 37.6
Subtotal | -- | -- | -- | -- | -- | -- | 785.3
Annual Funding BY$ Missile
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2004 $M | Non End Item Recurring Flyaway BY 2004 $M | Non Recurring Flyaway BY 2004 $M | Total Flyaway BY 2004 $M | Total Support BY 2004 $M | Total Program BY 2004 $M
2004 | -- | -- | -- | -- | -- | -- | 107.4
2005 | -- | -- | -- | -- | -- | -- | 82.9
2006 | -- | -- | -- | -- | -- | -- | 75.2
2007 | -- | -- | -- | -- | -- | -- | 101
2008 | -- | -- | -- | -- | -- | -- | 47.4
2009 | -- | -- | -- | -- | -- | -- | 27.1
2010 | -- | -- | -- | -- | -- | -- | 56.1
2011 | -- | -- | -- | -- | -- | -- | 102.6
2012 | -- | -- | -- | -- | -- | -- | 71.5
2013 | -- | -- | -- | -- | -- | -- | 30.7
Subtotal | -- | -- | -- | -- | -- | -- | 701.9
Annual Funding TY$ - Missile
2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2012 | -- | -- | -- | 75 | 75 | -- | 75
2013 | -- | -- | -- | 8.2 | 8.2 | -- | 8.2
2014 | 86 | 603.4 | -- | -- | 603.4 | 87 | 690.4
2015 | 70 | 336.1 | -- | -- | 336.1 | 48.5 | 384.6
2016 | 76 | 377.8 | -- | -- | 377.8 | 42 | 419.8
2017 | 80 | 382 | -- | -- | 382 | 40.6 | 422.6
2018 | 88 | 414.7 | -- | -- | 414.7 | 44 | 458.7
2019 | 94 | 449.8 | -- | -- | 449.8 | 47.8 | 497.6
2020 | 90 | 467.8 | -- | -- | 467.8 | 35.2 | 503
2021 | 90 | 466 | -- | -- | 466 | 36.7 | 502.7
2022 | 90 | 465.8 | -- | -- | 465.8 | 36.7 | 502.5
2023 | 90 | 465.3 | -- | -- | 465.3 | 36.7 | 502
2024 | 90 | 464.7 | -- | -- | 464.7 | 36.7 | 501.4
2025 | 90 | 464.1 | -- | -- | 464.1 | 36.7 | 500.8
2026 | 90 | 463.5 | -- | -- | 463.5 | 36.7 | 500.2
2027 | 90 | 464.5 | -- | -- | 464.5 | 35 | 499.5
2028 | 90 | 464.1 | -- | -- | 464.1 | 34.9 | 499
2029 | 90 | 463.7 | -- | -- | 463.7 | 34.9 | 498.6
2030 | 90 | 463.3 | -- | -- | 463.3 | 34.9 | 498.2
2031 | 44 | 213 | -- | -- | 213 | 16 | 229
2032 | -- | -- | -- | -- | -- | 12.4 | 12.4
2033 | -- | -- | -- | -- | -- | 12.4 | 12.4
Subtotal | 1528 | 7889.6 | -- | 83.2 | 7972.8 | 745.8 | 8718.6
Annual Funding BY$ - Missile
2032 ¦ Procurement ¦ Missile Procurement, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2004 $M | Non End Item Recurring Flyaway BY 2004 $M | Non Recurring Flyaway BY 2004 $M | Total Flyaway BY 2004 $M | Total Support BY 2004 $M | Total Program BY 2004 $M
2012 | -- | -- | -- | 61.8 | 61.8 | -- | 61.8
2013 | -- | -- | -- | 6.6 | 6.6 | -- | 6.6
2014 | 86 | 477.6 | -- | -- | 477.6 | 68.8 | 546.4
2015 | 70 | 261.4 | -- | -- | 261.4 | 37.7 | 299.1
2016 | 76 | 288.1 | -- | -- | 288.1 | 32 | 320.1
2017 | 80 | 285.5 | -- | -- | 285.5 | 30.4 | 315.9
2018 | 88 | 303.9 | -- | -- | 303.9 | 32.3 | 336.2
2019 | 94 | 323.2 | -- | -- | 323.2 | 34.3 | 357.5
2020 | 90 | 329.5 | -- | -- | 329.5 | 24.8 | 354.3
2021 | 90 | 321.8 | -- | -- | 321.8 | 25.3 | 347.1
2022 | 90 | 315.4 | -- | -- | 315.4 | 24.8 | 340.2
2023 | 90 | 308.8 | -- | -- | 308.8 | 24.4 | 333.2
2024 | 90 | 302.4 | -- | -- | 302.4 | 23.9 | 326.3
2025 | 90 | 296.1 | -- | -- | 296.1 | 23.4 | 319.5
2026 | 90 | 289.9 | -- | -- | 289.9 | 23 | 312.9
2027 | 90 | 284.8 | -- | -- | 284.8 | 21.5 | 306.3
2028 | 90 | 279 | -- | -- | 279 | 21 | 300
2029 | 90 | 273.3 | -- | -- | 273.3 | 20.6 | 293.9
2030 | 90 | 267.7 | -- | -- | 267.7 | 20.2 | 287.9
2031 | 44 | 120.7 | -- | -- | 120.7 | 9 | 129.7
2032 | -- | -- | -- | -- | -- | 6.9 | 6.9
2033 | -- | -- | -- | -- | -- | 6.8 | 6.8
Subtotal | 1528 | 5329.1 | -- | 68.4 | 5397.5 | 511.1 | 5908.6

## Unit Cost
Fire Unit, Unit Cost Report
BY2002 $M
Unit Cost | Current UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 16530.5 | 2708.8
Quantity | 48 | 0
Unit Cost | 344.385 | -- | --
Average Procurement Unit Cost (APUC)
Cost | 11999.1 | 0
Quantity | 48 | 0
Unit Cost | 249.981 | -- | --
BY2002 $M
Unit Cost | Original UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 16530.5 | 2708.8
Quantity | 48 | 0
Unit Cost | 344.385 | -- | --
Average Procurement Unit Cost (APUC)
Cost | 11999.1 | 0
Quantity | 48 | 0
Unit Cost | 249.981 | -- | --
Missile, Unit Cost Report
BY2002 $M
Unit Cost | Current UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 6220.9 | 6610.5
Quantity | 1528 | 1528
Unit Cost | 4.071 | 4.326 | 6.26
Average Procurement Unit Cost (APUC)
Cost | 5760 | 5908.6
Quantity | 1528 | 1528
Unit Cost | 3.77 | 3.867 | 2.57
BY2002 $M
Unit Cost | Original UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 6220.9 | 6610.5
Quantity | 1528 | 1528
Unit Cost | 4.071 | 4.326 | 6.26
Average Procurement Unit Cost (APUC)
Cost | 5760 | 5908.6
Quantity | 1528 | 1528
Unit Cost | 3.77 | 3.867 | 2.57

## Unit Cost History
Fire Unit
|  | BY2004 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2004-08-01 | 344.385 | 249.981 | 454.988 | 345.508
APB as of January 2006 | 2004-08-01 | 344.385 | 249.981 | 454.988 | 345.508
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | N/A | N/A | N/A | N/A | N/A
Current APB | 2004-08-01 | 344.385 | 249.981 | 454.988 | 345.508
Prior Annual SAR | 2012-12-01 | N/A | N/A | N/A | N/A
Current Estimate | 2013-12-01 | N/A | N/A | N/A | N/A
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY$M)
Initial PAUC Dev Est | Changes | [7 empty] | PAUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
454.988 | 2.956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Current SAR Baseline to Current Estimate (TY$M)
Initial APUC Dev Est | Changes | [7 empty] | APUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
345.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Missile
|  | BY2004 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2004-08-01 | 4.071 | 3.77 | 5.272 | 4.957
APB as of January 2006 | 2004-08-01 | 4.071 | 3.77 | 5.272 | 4.957
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | N/A | N/A | N/A | N/A | N/A
Current APB | 2004-08-01 | 4.071 | 3.77 | 5.272 | 4.957
Prior Annual SAR | 2012-12-01 | 4.442 | 3.984 | 6.327 | 5.813
Current Estimate | 2013-12-01 | 4.326 | 3.867 | 6.22 | 5.706
SAR Unit Cost History
Current SAR Baseline to Current Estimate (TY$M)
Initial PAUC Dev Est | Changes | [7 empty] | PAUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
5.272 | 0.189 | 0 | 0.309 | 0 | 0.408 | 0 | 0.042 | 0.948 | 6.22
Current SAR Baseline to Current Estimate (TY$M)
Initial APUC Dev Est | Changes | [7 empty] | APUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
4.957 | 0.178 | 0 | 0.309 | 0 | 0.22 | 0 | 0.042 | 0.749 | 5.706

## Cost Variance
Fire Unit
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 5255 | 16584.4 | -- | 21839.4
Previous Changes
Economic | 127.2 | -193.6 | -- | -66.4
Quantity | -- | -25434.9 | -- | -12555.5
Schedule | -- | -86.5 | -- | -86.5
Engineering | -- | -- | -- | --
Estimating | -2217.2 | -706.7 | -- | 2923.8
Other | -- | -- | -- | --
Support | -- | -3042.1 | -- | -3042.1
Subtotal | -2089.9 | -16584.4 | -- | -18674.3
Current Changes
Economic | -7 | -- | -- | -7
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -45.7 | 24106 | -- | -45.7
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -52.7 | -- | -- | -52.7
Total Changes | -2142.6 | -16584.4 | -- | -18727
CE - Cost Variance | 3112.4 | -- | -- | 3112.4
CE - Cost & Funding | 3112.4 | -- | -- | 3112.4
Summary Base Year 2004 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 4531.4 | 11999.1 | -- | 16530.5
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -8875.5 | -- | -8875.5
Schedule | -- | -148 | -- | -148
Engineering | -- | -- | -- | --
Estimating | -1785.5 | -795.4 | -- | -2580.9
Other | -- | -- | -- | --
Support | -- | -2180.2 | -- | -2180
Subtotal | -1785.5 | -11999.1 | -- | -13784.6
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -37.1 | -- | -- | -37.1
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -37.1 | -- | -- | -37.1
Total Changes | -1822.6 | -11999.1 | -- | -13821.7
CE - Cost Variance | 2708.8 | -- | -- | 2708.8
CE - Cost & Funding | 2708.8 | -- | -- | 2708.8
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices (Economic) | N/A | -7
Adjustment for current and prior escalation (Estimating) | 5.9 | 7
Decrease in FY 2013 funding due to Congressional reduction (Estimating) | -43 | -52.7
RDT&E | -37.1 | -52.7
Missile
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 482 | 7574 | -- | 8056
Previous Changes
Economic | 18.5 | 325.9 | -- | 344.4
Quantity | -- | -- | -- | --
Schedule | -- | 634.8 | -- | 634.8
Engineering | -- | -- | -- | --
Estimating | 284.8 | 335.2 | -- | 620
Other | -- | -- | -- | --
Support | -- | 11.7 | -- | 11.7
Subtotal | 303.3 | 1307.6 | -- | 1610.9
Current Changes
Economic | -1.1 | -54.2 | -- | -55.3
Quantity | -- | -- | -- | --
Schedule | -- | -162.6 | -- | -162.6
Engineering | -- | -- | -- | --
Estimating | 1.1 | 1.1 | -- | 2.2
Other | -- | -- | -- | --
Support | -- | -- | -- | 52.7
Subtotal | -- | -163 | -- | -163
Total Changes | 303.3 | 1144.6 | -- | 1447
CE - Cost Variance | 785.3 | 8718.6 | -- | 9503.9
CE - Cost & Funding | 785.3 | 8718.6 | -- | 9503.9
Summary Base Year 2004 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 460.9 | 5760 | -- | 6220.9
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | -- | d
Schedule | -- | 48.6 | -- | 48.6
Engineering | -- | -- | -- | --
Estimating | 240.1 | 302.9 | -- | 543
Other | -- | -- | -- | --
Support | -- | -24.6 | -- | -24.6
Subtotal | 240.1 | 326.9 | -- | 567
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -208.2 | -- | -208.2
Engineering | -- | -- | -- | --
Estimating | 0.9 | 1.3 | -- | 2.2
Other | -- | -- | -- | --
Support | -- | 28.6 | -- | 28.6
Subtotal | 0.9 | -178.3 | -- | -177.4
Total Changes | 241 | 148.6 | -- | 389.6
CE - Cost Variance | 701.9 | 5908.6 | -- | 6610.5
CE - Cost & Funding | 701.9 | 5908.6 | -- | 6610.5
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices (Economic) | N/A | -1.1
Adjustment for current and prior escalation (Estimating) | 0.9 | 1.1
RDT&E Subtotal | 0.9 | 0
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalatio indicies (Economic) | N/A | -54.2
Stretch-out of procurement buy profile in FY 2020 through FY 2033. (Schedule) | 0 | 93.3
Adjustment for current and prior escalation. (Estimating) | 4.8 | 5.8
Additional Schedule Variance due to the acceleration of 30 missiles in FY 2014 (procurement changed from 56 to 86 missiles). (Schedule) | -208.2 | -255.9
Decrease in FY 2013 funding due to Congressional reduction (Estimating) | -3.5 | -4.7
Adjustment for current and prior escalation. (Support) | 0.5 | 0.8
Increase in Other Support due to stretch-out of procurement buy profile (Support) | 28.1 | 51.9
Procurement Subtotal | -178.3 | -163

## Deliveries and Expenditures
Fire Unit
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 0 | --
Total Program Quantities Delivered | 0 | 0 | 0 | --
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 3112.4 | Years Appropriated | 10
Expenditures To Date | 3149.9 | Percent Years Appropriated | 100
Percent Expended | 101.2 | Appropriated to Date | 3112.4
Total Funding Years | 10 | Percent Appropriated | 100
Missile
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 1528 | 0
Total Program Quantities Delivered | 0 | 0 | 1528 | 0
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 9503.9 | Years Appropriated | 11
Expenditures To Date | 726.2 | Percent Years Appropriated | 36.67
Percent Expended | 7.64 | Appropriated to Date | 1558.9
Total Funding Years | 30 | Percent Appropriated | 16.4

## Operating and Support Cost
Fire Unit
Total O&S Cost $M
| Current Development APB Objective/Threshold |  | Current Estimate
| Fire Unit |  | Fire Unit | No Antecedent System (Antecedent)
Base Year | 33094.4 | 36403.8 | 0 | N/A
Then Year | 61902.2 | N/A | 0 | N/A
Missile
Unitized O&S Costs BY2004 $M
Cost Element | Missile Average Annual Cost of All Missiles | No Antecedent System (Antecedent)
Unit-Level Manpower | 0 | 0
Unit Operations | 0 | 0
Maintenance | 50.7 | 0
Sustaining Support | 5.5 | 0
Continuing System Improvements | 7.2 | 0
Indirect Support | 13.3 | 0
Other | 0 | 0
Total | 76.7 | --
Total O&S Cost $M
| Current Development APB Objective/Threshold |  | Current Estimate
| Missile |  | Fire Unit | No Antecedent System (Antecedent)
Base Year | 4582.6 | 5040.9 | 3373.9 | N/A
Then Year | 8571.8 | N/A | 7169.9 | N/A