## Schedule
1996-12-01
Milestones | Planning Estimate (SAR) | Approved Program (APB) | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1996-11-01
Milestone II | 2001-03-01 | 2001-03-01 | 2001-03-01
Milestone III | TBD | TBD | TBD
IOC | TBD | TBD | TBD
2003-12-01
Milestones | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1997-05-01 | 1996-11-01
Milestone B | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-10-01 | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2004-04-01 | 2005-10-01 | 2006-04-01 | 2005-10-01
CDR (STOVL&Common) | 2004-10-01 | 2006-05-01 | 2006-11-01 | 2006-05-01
CDR (CV&Common) | 2005-07-01 | 2007-01-01 | 2007-07-01 | 2007-06-01
DAE (IPR 1) | 2005-04-01 | 2006-01-01 | 2006-07-01 | 2006-01-01
1st Flt CTOL | 2005-11-01 | 2006-07-01 | 2007-01-01 | 2006-07-01
1st Flt STOVL | 2006-04-01 | 2007-05-01 | 2007-11-01 | 2008-08-01
1st Flt CV | 2007-01-01 | 2008-08-01 | 2009-03-01 | 2008-08-01
DAE (IPR 2) | 2006-04-01 | 2007-01-01 | 2007-07-01 | 2007-01-01
1st Operational Aircraft Delivered | 2008-06-01 | N/A | N/A | 2009-06-01
USMC IOC | 2010-04-01 | 2012-03-01 | 2012-09-01 | 2012-03-01
USAF IOC | 2011-06-01 | 2013-03-01 | 2013-09-01 | 2013-03-01
Completed IOT&E | 2012-03-01 | 2013-10-01 | 2014-04-01 | 2013-10-01
USN IOC | 2012-04-01 | 2013-03-01 | 2013-09-01 | 2013-03-01
DAB Milestone C | 2012-04-01 | 2013-10-01 | 2014-04-01 | 2013-10-01
1st Production Aircraft Delivered | N/A | 2009-06-01 | 2009-12-01 | N/A
APB Breach
2006-12-01
Milestones | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1997-05-01 | 1996-11-01
Milestone B | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-10-01 | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2004-04-01 | 2005-10-01 | 2006-04-01 | 2006-02-01
CDR (STOVL&Common) | 2004-10-01 | 2006-05-01 | 2006-11-01 | 2006-02-01
CDR (CV&Common) | 2005-07-01 | 2007-01-01 | 2007-07-01 | 2007-06-01
DAE (IPR 1) | 2005-04-01 | 2006-01-01 | 2006-07-01 | 2006-03-01
1st Flt CTOL | 2005-11-01 | 2006-07-01 | 2007-01-01 | 2006-12-01
1st Flt STOVL | 2006-04-01 | 2008-03-01 | 2008-09-01 | 2008-06-01
1st Flt CV | 2007-01-01 | 2009-04-01 | 2009-10-01 | 2009-03-01
DAE (IPR 2) | 2006-04-01 | 2007-01-01 | 2007-07-01 | 2007-03-01
1st Production Aircraft Delivered | N/A | 2010-01-01 | 2010-07-01 | 2010-01-01
1st Operational Aircraft Delivered | 2008-06-01 | N/A | N/A | N/A
USMC IOC | 2010-04-01 | 2012-03-01 | 2012-09-01 | 2012-03-01
USAF IOC | 2011-06-01 | 2013-03-01 | 2013-09-01 | 2013-03-01
Completed IOT&E | 2012-03-01 | 2013-10-01 | 2014-04-01 | 2013-10-01
USN IOC | 2012-04-01 | 2015-03-01 | 2015-09-01 | 2015-03-01
DAB Milestone C | 2012-04-01 | 2013-10-01 | 2014-04-01 | 2013-10-01
2009-12-01
Milestones | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1997-05-01 | 1996-11-01
Milestone B | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-10-01 | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2004-04-01 | 2005-10-01 | 2006-04-01 | 2006-02-01
CDR (STOVL&Common) | 2004-10-01 | 2006-05-01 | 2006-11-01 | 2006-02-01
CDR (CV&Common) | 2005-07-01 | 2007-01-01 | 2007-07-01 | 2007-06-01
DAE (IPR 1) | 2005-04-01 | 2006-01-01 | 2006-07-01 | 2006-03-01
1st Flt CTOL | 2005-11-01 | 2006-07-01 | 2007-01-01 | 2006-12-01
1st Flt STOVL | 2006-04-01 | 2008-03-01 | 2008-09-01 | 2008-06-01
1st Flt CV | 2007-01-01 | 2009-04-01 | 2009-10-01 | MAY 2010 1
DAE (IPR 2) | 2006-04-01 | 2007-01-01 | 2007-07-01 | 2007-04-01
1st Production Aircraft Delivered | N/A | 2010-01-01 | 2010-07-01 | OCT 2010 1
1st Operational Aircraft Delivered | 2008-06-01 | N/A | N/A | N/A
USMC IOC | 2010-04-01 | 2012-03-01 | 2012-09-01 | 2012-03-01
USAF IOC | 2011-06-01 | 2013-03-01 | 2013-09-01 | 2013-03-01
Completed IOT&E | 2012-03-01 | 2013-10-01 | 2014-04-01 | APR 2016 1
USN IOC | 2012-04-01 | 2015-03-01 | 2015-09-01 | 2015-03-01
DAB Milestone C | 2012-04-01 | 2013-10-01 | 2014-04-01 | APR 2016 1
APB Breach
2010-12-01
Milestones | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | N/A | N/A | 1996-11-01
Milestone B | 2001-10-01 | N/A | N/A | 2001-10-01
EMD Contract Award | 2001-10-01 | N/A | N/A | 2001-10-01
Preliminary Design Review | 2003-04-01 | N/A | N/A | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2004-04-01 | N/A | N/A | 2006-02-01
CDR (STOVL&Common) | 2004-10-01 | N/A | N/A | 2006-02-01
CDR (CV&Common) | 2005-07-01 | N/A | N/A | 2007-06-01
DAE (IPR 1) | 2005-04-01 | N/A | N/A | 2006-03-01
1st Flt CTOL | 2005-11-01 | N/A | N/A | 2006-12-01
1st Flt STOVL | 2006-04-01 | N/A | N/A | 2008-06-01
1st Flt CV | 2007-01-01 | N/A | N/A | 2010-06-01
DAE (IPR 2) | 2006-04-01 | N/A | N/A | 2007-04-01
1st Production Aircraft Delivered | N/A | N/A | N/A | 2011-04-01
1st Operational Aircraft Delivered | 2008-06-01 | N/A | N/A | N/A
USMC IOC | 2010-04-01 | N/A | N/A | TBD
USAF IOC | 2011-06-01 | N/A | N/A | TBD
Completed IOT&E | 2012-03-01 | N/A | N/A | TBD
USN IOC | 2012-04-01 | N/A | N/A | TBD
DAB Milestone C | 2012-04-01 | N/A | N/A | TBD
2011-12-01
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1997-05-01 | 1996-11-01
Milestone B | 2010-11-01 | 2011-11-01 | 2012-05-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-10-01 | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2005-10-01 | 2005-10-01 | 2006-04-01 | 2006-02-01
CDR (STOVL&Common) | 2006-05-01 | 2006-05-01 | 2006-11-01 | 2006-02-01
CDR (CV&Common) | 2007-01-01 | 2007-01-01 | 2007-07-01 | 2007-06-01
DAE (IPR 1) | 2006-01-01 | 2006-01-01 | 2006-07-01 | 2006-03-01
1st Flt CTOL | 2006-07-01 | 2006-07-01 | 2007-01-01 | 2006-12-01
DAE (IPR 2) | 2007-01-01 | 2007-01-01 | 2007-07-01 | 2007-04-01
1st Flt STOVL | 2008-03-01 | 2008-03-01 | 2008-09-01 | 2008-06-01
1st Flt CV | 2010-05-01 | 2010-05-01 | 2010-11-01 | 2010-06-01
1st Production Aircraft Delivered | 2010-12-01 | 2010-12-01 | 2011-06-01 | 2011-05-01
Block 2B Fleet Release | N/A | 2015-03-01 | 2015-09-01 | 2015-03-01
Block 3F Fleet Release | N/A | 2017-08-01 | 2018-02-01 | 2017-08-01
Completed IOT&E | 2016-04-01 | 2019-02-01 | 2019-08-01 | 2019-02-01
Full Rate Production Decision | N/A | 2019-04-01 | 2019-10-01 | 2019-04-01
DAB Milestone C | 2016-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
USMC IOC | 2012-12-01 | TBD | TBD | TBD
USAF IOC | 2016-04-01 | TBD | TBD | TBD
USN IOC | 2016-04-01 | TBD | TBD | TBD
2012-12-01
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1997-05-01 | 1996-11-01
Milestone B | 2011-11-01 | 2011-11-01 | 2012-05-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-10-01 | 2003-04-01
Critical Design Review
CDR (CTOL&Common) | 2005-10-01 | 2005-10-01 | 2006-04-01 | 2006-02-01
CDR (STOVL&Common) | 2006-05-01 | 2006-05-01 | 2006-11-01 | 2006-02-01
CDR (CV&Common) | 2007-01-01 | 2007-01-01 | 2007-07-01 | 2007-06-01
DAE (IPR 1) | 2006-01-01 | 2006-01-01 | 2006-07-01 | 2006-03-01
1st Flt CTOL | 2006-07-01 | 2006-07-01 | 2007-01-01 | 2006-12-01
DAE (IPR 2) | 2007-01-01 | 2007-01-01 | 2007-07-01 | 2007-04-01
1st Flt STOVL | 2008-03-01 | 2008-03-01 | 2008-09-01 | 2008-06-01
1st Flt CV | 2010-05-01 | 2010-05-01 | 2010-11-01 | 2010-06-01
1st Production Aircraft Delivered | 2010-12-01 | 2010-12-01 | 2011-06-01 | 2011-05-01
Block 2B Fleet Release | 2015-03-01 | 2015-03-01 | 2015-09-01 | 2015-06-01
Block 3F Fleet Release | 2017-08-01 | 2017-08-01 | 2018-02-01 | 2017-08-01
Completed IOT&E | 2019-02-01 | 2019-02-01 | 2019-08-01 | 2019-02-01
Full Rate Production Decision | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
DAB Milestone C | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
USMC IOC | TBD | TBD | TBD | TBD
USAF IOC | TBD | TBD | TBD | TBD
USN IOC | TBD | TBD | TBD | TBD
2013-12-01
Milestones | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1996-11-01 | 1996-11-01
Milestone B | 2001-10-01 | 2001-10-01 | 2001-10-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2001-10-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-04-01 | 2003-04-01 | 2003-04-01
CDR
CDR (CTOL&Common) | 2006-02-01 | 2006-02-01 | 2006-02-01 | 2006-02-01
CDR (STOVL&Common) | 2006-02-01 | 2006-02-01 | 2006-02-01 | 2006-02-01
CDR (CV&Common) | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-01
DAE (IPR 1) | 2006-03-01 | 2006-03-01 | 2006-03-01 | 2006-03-01
1st Flt CTOL | 2006-12-01 | 2006-12-01 | 2006-12-01 | 2006-12-01
DAE (IPR 2) | 2007-04-01 | 2007-04-01 | 2007-04-01 | 2007-04-01
1st Flt STOVL | 2008-06-01 | 2008-06-01 | 2008-06-01 | 2008-06-01
1st Flt CV | 2010-06-01 | 2010-06-01 | 2010-06-01 | 2010-06-01
1st Production Aircraft Delivered | 2011-05-01 | 2011-05-01 | 2011-05-01 | 2011-05-01
Milestone B Re-approval | 2012-03-01 | 2012-03-01 | 2012-03-01 | 2012-03-01
Block 2B Fleet Release | 2015-03-01 | 2015-03-01 | 2015-09-01 | 2015-06-01
USMC IOC | TBD | TBD | TBD | 2015-07-01
USAF IOC | TBD | TBD | TBD | 2016-08-01
Block 3F Fleet Release | 2017-08-01 | 2017-08-01 | 2018-02-01 | 2017-08-01
USN IOC | TBD | TBD | TBD | 2018-08-01
Completed IOT&E | 2019-02-01 | 2019-02-01 | 2019-08-01 | 2019-02-01
Full Rate Production Decision | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
DAB Milestone C | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
2014-12-01
Events | SAR Baseline Development Estimate | Current APB Development Objective/Threshold |  | Current Estimate
Concept Demonstration Contract Award | 1996-11-01 | 1996-11-01 | 1996-11-01 | 1996-11-01
Milestone B | 2001-10-01 | 2001-10-01 | 2002-04-01 | 2001-10-01
EMD Contract Award | 2001-10-01 | 2001-10-01 | 2001-10-01 | 2001-10-01
Preliminary Design Review | 2003-04-01 | 2003-03-01 | 2003-03-01 | 2003-03-01
CDR
CDR (CTOL&Common) | 2006-02-01 | 2006-02-01 | 2006-02-01 | 2006-02-01
CDR (STOVL&Common) | 2006-02-01 | 2006-02-01 | 2006-02-01 | 2006-02-01
CDR (CV&Common) | 2007-06-01 | 2007-06-01 | 2007-06-01 | 2007-06-01
DAE (IPR 1) | 2006-03-01 | 2006-03-01 | 2006-03-01 | 2006-03-01
1st Flt CTOL | 2006-12-01 | 2006-12-01 | 2006-12-01 | 2006-12-01
DAE (IPR 2) | 2007-04-01 | 2007-04-01 | 2007-04-01 | 2007-04-01
1st Flt STOVL | 2008-06-01 | 2008-06-01 | 2008-06-01 | 2008-06-01
1st Flt CV | 2010-06-01 | 2010-05-01 | 2010-05-01 | 2010-05-01
1st Production Aircraft Delivered | 2011-05-01 | 2011-05-01 | 2011-05-01 | 2011-05-01
Milestone B Re-approval | 2012-03-01 | 2011-11-01 | 2012-05-01 | 2012-03-01
Block 2B Fleet Release | 2015-03-01 | 2015-03-01 | 2015-09-01 | 2015-06-01
USMC IOC | TBD | 2015-07-01 | 2015-12-01 | 2015-07-01
USAF IOC | TBD | 2016-08-01 | 2016-12-01 | 2016-08-01
Block 3F Fleet Release | 2017-08-01 | 2017-08-01 | 2018-02-01 | 2017-08-01
USN IOC | TBD | 2018-08-01 | 2019-02-01 | 2018-08-01
Completed IOT&E | 2019-02-01 | 2019-02-01 | 2019-08-01 | 2019-02-01
Full Rate Production Decision | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01
DAB Milestone C | 2019-04-01 | 2019-04-01 | 2019-10-01 | 2019-04-01