## Schedule
1998 USMC
| FY 1996 | FY 1997 | FY 1998 | FY 1999 | FY 2000 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | To Complete | Total
IOC | FY 2002: Q3-Q4
1999 USMC
| FY 1999 | FY 2000 | FY 2001 | FY 2002 | FY 2003
IOC | bar: FY 2000
2000 USMC
| FY 1999 | FY 2000 | FY 2001 | FY 2002 | FY 2003
IOC | bar: FY 2000
2001 USMC
| FY 1999 | FY 2000 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005
IOC | bar: FY 2001
2002 USMC
| FY 1999 | FY 2000 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005
IOC | bar: FY 2002
Full Rate Production Decision | bar: FY 2002
2003 USMC
| FY 2002 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009
Complete Development Testing (EMD Guns) | bar: FY 2002
Operational Assessment | bar: FY 2002
Pilot Production (PP) Guns (Qty 2) | bar: FY 2002 to FY 2003
Milestone C | bar: FY 2003
LRIP Contract Award | bar: FY 2003
Complete Development Testing (PP Guns) | bar: FY 2003
MOT&E | bar: FY 2004
Full Rate Production Decision | bar: FY 2005
IOC | bar: FY 2005
FOC | bar: FY 2008
1997 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2002: FY 1996; FY 2003: FY 1997; FY 2004: FY 1998; FY 2005: FY 1999
P3I Integration Efforts on the LW155 | bar: FY 2003
Perform Laser Ignition Integration | bar: FY 2003
Initiate/Develop Component Simulations | bar: FY 2003
Conduct Trade Off Study | bar: FY 2003
Initiate Evaluation of Automated FC | bar: FY 2005
1999 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 1996 | FY 1997 | FY 1998 | FY 1999 | FY 2000 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005
MS I/II | FY 2000: 1st Qtr
Contract Awar | FY 2000: 2nd Qtr
Developmental Testing Begins | FY 2001: 1st Qtr
Developmental Testing Ends | FY 2002: 4th Qtr
Multi-service Operational Testing Begins | FY 2003: 1st Qtr
Multi-Service Operational Testing Ends | FY 2003: 2nd Qtr
Milestone III | FY 2003: 4th Qtr
Production | FY 2004: 1st Qtr
2000 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 1996 | FY 1997 | FY 1998 | FY 1999 | FY 2000 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005
Towed Artillery Digitization (TAD) Milestone I/II | FY 2000: 1st Qtr
TAD System Contract Award | FY 2000: 3rd Qtr
TAD System Developmental Testing Begins | FY 2001: 2nd Qtr
TAD System Developmental Testing Ends | FY 2002: 4th Qtr
TAD Milti-service Operational Testing Begins | FY 2003: 1st Qtr
TAD Milti-service Operational Testing Ends | FY 2003: 2nd Qtr
TAD System Milestone III | FY 2003: 4th Qtr
Production of LW155 Howitzer with TAD System | FY 2004: 1st Qtr
2001 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2000 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007
Towed Artillery Digitization (TAD) Milestone I/II | 1Q |  |  | 0 | 0 | 0 | 0 | 0
TAD Contract Award | 2Q |  |  | 0 | 0 | 0 | 0 | 0
TAD Developmental Testing Begins |  | 4Q |  | 0 | 0 | 0 | 0 | 0
TAD Developmental Testing Ends |  |  | 4Q | 0 | 0 | 0 | 0 | 0
TAD Multi-service Operational Test |  |  |  | 0 | 0 | 0 | 0 | 0
TAD Milestone III |  |  |  | 0 | 0 | 0 | 0 | 0
2002 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2001 | FY 2002 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007
TAD Design | FY 2000: 1-4Q; FY 2001: 1-4Q; FY 2002: 1-2Q
TAD Technical Testing | FY 2002: 2-4Q
Begin Technical Testing and Conduct Logistics Demonstration | FY 2003: 1-2Q
TAD Multi-service Operational Test | bar: FY 2003
TAD Milestone C | bar: FY 2003
2003 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2002 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009
Novated TAD Contract (General Dynamics) to M777E1 Contract (BAE Systems) | bar: FY 2002
Design Verification and Testing | FY 2003: 1-4Q; FY 2004: 1-3Q
Operational Test | bar: FY 2004
Full Rate Production Decision | bar: FY 2005
Initial Operational Capability | bar: FY 2006
2004 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009
System Development and Demonstration | FY 2002: 1-3Q
Design Verification and Test / Technical Testing | FY 2002: 2-4Q; FY 2003: 1-3Q
Artic Operational Test and Evaluation (M777E1) | bar: FY 2003
Joint Operational Test and Evaluation (M777E1) | bar: FY 2003
Milestone C | bar: FY 2004
Full Rate Production Decision | bar: FY 2004
Initial Operational Capability | bar: FY 2005
2007 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011
IBR | bar: FY 2004
Trade Study / Downselect | bar: FY 2004
Software Requirements Definition | bar: FY 2004
Preliminary Design | FY 2004: 2Q - 4Q
Preliminary Design Review | bar: FY 2005
Detailed Design | FY 2005: 1Q - 4Q
Component Qualification Testing | FY 2006: 1Q - 2Q
Coding and Unit Test | FY 2006: 2Q - 3Q
Coding Complete | bar: FY 2006
Integration and Engineering Evaluation Test | FY 2006: 3Q - 4Q
Software Formal Qualification Test | bar: FY 2006
2008 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011
IBR | bar: FY 2003
Trade Study / Downselect | bar: FY 2003
Software Requirements Definition | bar: FY 2003
Preliminary Design | FY 2003: 2Q - 4Q
Preliminary Design Review | bar: FY 2004
Detailed Design | FY 2004: 1Q - 4Q
Component Qualification Testing | FY 2005: 1Q - 2Q
Coding and Unit Test | FY 2005: 2Q - 3Q
Coding Complete | bar: FY 2005
Integration and Engineering Evaluation Test | FY 2005: 3Q - 4Q
Software Formal Qualification Test | bar: FY 2005
2009 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2002: FY 2008; FY 2003: FY 2009; FY 2004: FY 2010; FY 2005: FY 2011
IBR | bar: FY 2002
Trade Study / Downselect | bar: FY 2002
Software Requirements Definition | bar: FY 2002
Preliminary Design | FY 2002: 2Q - 4Q
Preliminary Design Review | bar: FY 2003
Detailed Design | FY 2003: 1Q - 4Q
Component Qualification Testing | FY 2004: 1Q - 2Q
Coding and Unit Test | FY 2004: 2Q - 3Q
Coding Complete | bar: FY 2004
Integration and Engineering Evaluation Test | FY 2004: 3Q - 4Q
Software Formal Qualification Test | bar: FY 2004
2010 - Army
Budget Activity 5 - Engineering and Manufacturing Development
Schedule Profile - Project D509 | FY 2002: FY 2009; FY 2003: FY 2010; FY 2004: FY 2011; FY 2005: FY 2012
Component Qualification Testing | bar: FY 2002 to FY 2003
Coding and Unit Test | FY 2003: Q1-Q2
Coding Complete | bar: FY 2003
Integration and Engineering Evaluation Test | FY 2003: Q2-Q3
Software Formal Qualification Test | bar: FY 2003
2015 - Army | FY 2002: Start; FY 2004: End
Budget Activity 5 - Engineering and Manufacturing Development | FY 2002: Quarter; FY 2003: Year; FY 2004: Quarter; FY 2005: Year
Schedule Profile - Project D509
Feasibility and Concept Studies | FY 2002: 1; FY 2003: 2015; FY 2004: 2; FY 2005: 2016
Preliminary Designs | FY 2002: 2; FY 2003: 2016; FY 2004: 1; FY 2005: 2018
Fabrication Prototypes | FY 2002: 2; FY 2003: 2018; FY 2004: 2; FY 2005: 2019
Technology Demonstrator | FY 2002: 3; FY 2003: 2019; FY 2004: 2; FY 2005: 2020
Test and Evaluation | FY 2002: 3; FY 2003: 2020; FY 2004: 2; FY 2005: 2021
2016 - Army | FY 2002: Start; FY 2004: End
Budget Activity 5 - Engineering and Manufacturing Development | FY 2002: Quarter; FY 2003: Year; FY 2004: Quarter; FY 2005: Year
Schedule Profile - Project D509
M777 Engineering Tools Development & Validation | FY 2002: 1; FY 2003: 2015; FY 2004: 2; FY 2005: 2016
XM907 Common Cannon Assembly Support | FY 2002: 1; FY 2003: 2015; FY 2004: 2; FY 2005: 2019
Objective M777ER Design, Analysis & Drawings | FY 2002: 1; FY 2003: 2015; FY 2004: 2; FY 2005: 2018
Objective M777ER Component Fabrication | FY 2002: 2; FY 2003: 2018; FY 2004: 2; FY 2005: 2019
Integration | FY 2002: 2; FY 2003: 2019; FY 2004: 2; FY 2005: 2020