## Schedule
2002
Performance against approved in-service date
Date
Current forcase ISD | 2010-06-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 6
In-year changes in 2001/2002 | 16
Reasons for variations from approved ISD
Factor | Increase (months) | Decrease (months) | Explanation
Changed Budgetary Priorities | 16 |  | Change in the customers' requirement flowing from changed budgetary priorities
Risk Differential |  | 10 | Difference between the risk allowed for in the msot likely (50%) and highest acceptable (90%) estimates at Main Gate (-10 months)
Total | 16 | -10
Net Variation | 6
Duration of Assessment Phase
Date
Date of Main Gate Approval | 2000-05-01
Target Date for Main Gate Approval at Initial Gate | 1999-06-01
Variation (months) | 11
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Most Likely | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Forecast ISD at Initial Gate | - | 2007-12-01 | -
2003
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2002/2003 | 9
Reasons for variations from approved ISD
Factor | Increase (months) | Decrease (months) | Explanation
Changed Budgetary Priorities | 16 |  | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Procurement Strategy | 9 |  | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Risk Differential | 16 | 10 | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Total | 25 | -10
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Most Likely | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Forecast ISD at Initial Gate | - | 2007-12-01 | -
2004
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2003/2004 | 0
Reasons for variations from approved ISD
Factor | Increase (months) | Decrease (months) | Explanation
Changed Budgetary Priorities | 16 |  | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Procurement Strategy | 9 |  | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Risk Differential | 16 | 10 | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Total | 25 | -10
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Most Likely | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Forecast ISD at Initial Gate | - | 2007-12-01 | -
2005
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2004/2005 | 0
Reasons for Variation from approved ISD
Date | Variation (months) | Factor | Explanation
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Most Likely | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Forecast ISD at Initial Gate | - | 2007-12-01 | -
2006
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2004/2005 | 0
Reasons for Variation from approved ISD
Date | Variation (months) | Factor | Explanation
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Budgeted For | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Envelope within which capability was expected to be available at Initial Gate | - | - | 2007-12-01
2007
Performance against approved in-service date
Date
Current forcase ISD | 2011-03-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 15
In-year changes in 2004/2005 | 0
Reasons for Variation from approved ISD
Date | Variation (months) | Factor | Explanation
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 15
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Budgeted For | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Envelope within which capability was expected to be available at Initial Gate | - | 2007-12-01 | -
2008
Performance against approved in-service date
Date
Current forcase ISD | 2011-12-01
Approved ISD at Main Gate | 2009-12-01
Variation (months) | 24
In-year changes in 2004/2005 | 9
Reasons for Variation from approved ISD
Date | Variation (months) | Factor | Explanation
2008-02-01 | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 24
ISD boundaries at Initial Gate and Main Gate Approvals
| Earliest | Budgeted For | Latest Acceptable
Forecast ISD at Main Gate | - | 2009-02-01 | 2009-12-01
Envelope within which capability was expected to be available at Initial Gate | - | 2007-12-01 | -
2009
Planned/Actual Boundaries for introduction of the capability
Description | Earliest Forecast / Approved | Budgeted For (Post-Main Investment Decision Projects only) | Latest Forecast / Approved
A400M |  | 2009-02-01 | 2009-12-01
Progress against approved Dates
Description | Approved Date | Actual / Forecast Date | Variation | In-Year Variation
A400M | 2009-12-01 | 2015-12-01 | 72 | 48
Timescale Variation
Date | Variation (months) | Factor | Explanation
2009-03-01 | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
2009-01-01 | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
2008-10-01 | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
2008-09-01 | *** | Technical Factors | Reflects lateste delay and risk assessment beyond first flight
2008-02-01 | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 24
2010
Duration of the Assessment Phase
Description | Forecast / Actual Date of Main Gate Approval | Date of Initial Gate Approval | Length of Assessment Phase (Months)
A400m | 2000-05-01 | 1997-07-01 | 35
Planned/Actual Boundaries for introduction of the capability
Description | Earliest Forecast / Approved | Budgeted For (Post-Main Investment Decision Projects only) | Latest Forecast / Approved
A400M |  | 2009-02-01 | 2009-12-01
Progress against approved Dates
Description | Approved Date | Actual / Forecast Date | Variation | In-Year Variation
A400M | 2009-12-01 | 2015-03-01 | 63 | -9
Timescale Variation
Date | Variation (months) | Factor | Explanation
2010-03-01 | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
2009-03-01 | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects lateste delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Changed Budgetary Priorities | Change in the customers' requirement flowing from changed budgetary priorities (16 months)
Historic | 9 | Procurement Strategy | Delay in brining contract into effect as a result of delayed approvals in Germany (9 months)
Historic | -10 | Risk Differential | Difference between the most likely and highest acceptable dates dates at Main Gate (-10 months)
Net Variation | 24
2011
Duration of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Planned/Actual Boundaries for introduction of the capability
Description | Earliest Forecast / Approved | Budgeted For (Post-Main Investment Decision Projects only) | Latest Forecast / Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic | 9 | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation | 73
2012
Length of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Actual Boundaries for In Service Date or Initial Operating Capability
Project/Increment Title | Earliest Approved | Budgeted For | Latest Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic | 9 | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation | 73
2013
Length of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Actual Boundaries for In Service Date or Initial Operating Capability
Project/Increment Title | Earliest Approved | Budgeted For | Latest Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic | 9 | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation | 73
2014
Length of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Actual Boundaries for In Service Date or Initial Operating Capability
Project/Increment Title | Earliest Approved | Budgeted For | Latest Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic | 9 | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation
2015
Length of the Assessment Phase
Project/Increment Title | Date of Initial Investment Decision Approval | Forecast / Actual Date of Main Investment Decision Approval | Length of Assessment Phase (Months)
A400m | 1997-07-01 | 2000-05-01 | 34
Actual Boundaries for In Service Date or Initial Operating Capability
Project/Increment Title | Earliest Approved | Budgeted For | Latest Approved
A400M |  | 2009-02-01 | 2009-12-01
Timescale Variation
Date | Variation (months) | Factor | Explanation
2015-01-01 | 6 | Technical Factors | Updated programme estimate based on an assessment of the Airbus Defence & Space revised delivery schedule
Historic | *** | Procurement Processes (International Collaboration) | A change due to programme rebalancing
Historic | *** | Technical Factors | Updated programme estimate based upon A400M Task Force outputs and Air Support Cluster assessment
Historic | *** | Technical Factors | Updated programme proposal received from Airbus Military, including revised production approach
Historic | *** | Technical Factors | Programme delays affecting engine and aircraft first flight
Historic | *** | Technical Factors | Reflects latestet delay and risk assessment beyond first flight
Historic | 9 | Technical Factors | Contract delay to aircraft delivery
Historic | 16 | Budgetary Factors | Change in the customers' requirement flowing from changed budgetary priorities
Historic |  | Procurement Processes | Delay in brining contract into effect as a result of delayed approvals in Germany
Net Variation | 79