## Pg 75
F-35 Aircraft
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -65.4
Adjustment for current and prior escalation. (Estimating) | +26.9 | +28.1
Increase due to additional scope to Initial Operational Test and Evaluation International Program. (Estimating) | +45.0 | +50.9
Realignment of costs between Aircraft subprogram and Engine subprogram. (Air Force) (Estimating) | +18.0 | +18.5
Realignment of costs between Aircraft subprogram and Engine subprogram. (Navy) (Estimating) | +119.4 | +124.9
Decrease due to realignment of program funding, Congressional reductions, and actual funding investment. (Air Force) (Estimating) | -4.2 | -3.6
Increase due to realignment of program funding and actual funding investment. (Navy) (Estimating) | -1.7 | +0.8
RDT&E Subtotal | +203.4 | +154.2
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -3417.6
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended Department of the Navy program from FY 2033 to FY 2034. (Air Force) (Schedule) | 0 | +548.1
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended Department of the Navy program from FY 2033 to FY 2034. (Navy) (Schedule) | 0 | +351.7
Adjustment for current and prior escalation. (Estimating) | +120.1 | 127.5
Decrease due to revised International procurement quantity profile. (Air Force) (Estimating) | -123.7 | -167.8
Decrease due to revised International procurement quantity profile. (Navy) (Estimating) | -83.7 | -96.2
Revised estimate of subcontractor cost due to the incorporation of the latest actuals from early LRIP lots. (Air Force) (Estimating) | -501.5 | -715.2
Revised estimate of subcontractor cost due to the incorporation of the latest actuals from early LRIP lots. (Navy) (Estimating) | +197.8 | +238.2
Revised estimate of Airframe cost due to the incorporation of the latest actuals from early LRIP lots. (Air Force) (Estimating) | +2701.6 | +3526.0
Revised estimate of Airframe cost due to the incorporation of the latest actuals from early LRIP lots. (Navy) (Estimating) | +333.3 | +395.2
Revised estimate of Airframe cost due to the incorporation of the latest Prime and subcontractor Labor/Exchange Rates. (Air Force) (Estimating) | -2531.9 | -3455.5
Revised estimate of Airframe cost due to the incorporation of the latest Prime and subcontractor Labor/Exchange Rates. (Navy) (Estimating) | -803 | -982
Adjustment for current and prior escalation. (Support) | +29.6 | +31.1
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Air Force) (Support) | -713 | -959.5
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Navy) (Support) | -414.9 | -527
Decrease in Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Air Force) (Support) | -61.1 | -32.1
Decrease in Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Navy) (Support) | -887.2 | -1068
Procurement Subtotal | -2737.6 | -6203.1
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -70.4
Adjustment for current and prior escalation. (Estimating) | 3.1 | 3.2
Increase due to revised estimate of MILCON requirements. (Air Force) (Estimating) | 150 | 165.3
Increase due to revised estimate of MILCON requirements. (Navy) (Estimating) | 74.4 | 108
MILCON Subtotal | 227.5 | 206.1
F-35 Engine
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -9.5
Adjustment for current and prior escalation. (Estimating) | +5.8 | +6.1
Realignment of cost between Aircraft subprogram and Engine subprogram. (Air Force) (Estimating) | -18 | -18.5
Increase due to realignment of program funding and actual funding investment. (Air Force) (Estimating) | 1.1 | 1.1
Realignment of cost between Aircraft subprogram and Engine subprogram. (Navy) (Estimating) | -119.2 | -124.9
Increase due to realignment of program funding and actual funding investment. (Navy) (Estimating) | 2.1 | 2.3
RDT&E Subtotal | -128.2 | -143.4
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -689.8
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended Department of the Navy program from FY 2033 to FY 2034. (Air Force) (Schedule) | 0 | +108.9
Increase for revised DoD procurement profile (i.e. lower near-term ramp rate) and extended Department of the Navy program from FY 2033 to FY 2034. (Navy) (Schedule) | 0 | +69.3
Adjustment for current and prior escalation. (Estimating) | +16.5 | 17.3
Decrease due to revised International procurement quantity profile. (Air Force) (Estimating) | -36.2 | -59.2
Decrease due to revised International procurement quantity profile. (Navy) (Estimating) | -8.5 | -13.6
Revised estimate due to the incorporation of the latest actuals from early LRIP lots. (Air Force) (Estimating) | -130.5 | -220.1
Revised estimate due to the incorporation of the latest actuals from early LRIP lots. (Navy) (Estimating) | -24.1 | -42.2
Adjustment for current and prior escalation. (Support) | +5.9 | +6.4
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Air Force) (Support) | -80.6 | -109.1
Decrease in Other Support due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Navy) (Support) | -48.7 | -61.3
Decrease in Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Air Force) (Support) | -35.1 | -22.4
Decrease in Initial Spares due to maturation of technical baseline, definition of customer requirements, and further definition of Service beddown plans. (Navy) (Support) | -372.2 | -447.9
Procurement Subtotal | -713.5 | -1463.7