## Pg 43
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | +63.0
Adjustment for current and prior escalation. (Estimating) | -53.1 | -59.2
Increase due to revised estimate of required risk funding based on OSD lead Independent program assessments. (Navy) (Estimating) | +2327.0 | +2976.4
Increase due to revised estimate of required risk funding based on OSD lead Independent program assessments. (Air Force) (Estimating) | +975.9 | +1248.4
RDT&E Subtotal | +3249.8 | +4228.6
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -1449.8
Increase for revised DoD procurement profile, (i.e. lower near-term ramp). (Air Force) (Schedule) | 0 | +1755.9
Increase for revised DoD procurement profile, (i.e. lower near-term ramp and procurement completion extended one year to FY 2027). (Navy) (Schedule) | 0 | +1395.1
Adjustment for current and prior escalation. (Estimating) | +33.8 | +40.8
Increase to Airframe due to incorporation of latest actual costs for LRIP lots. (Air Force) (Estimating) | +6099.2 | +9730.1
Increase to Airframe due to incorporation of latest actual costs for LRIP lots. (Navy) (Estimating) | +1878.0 | +2910.1
Increase to Mission Systems due to incorporation of latest actual costs for LRIP lots. (Air Force) (Estimating) | +593.5 | +947.3
Increase to Mission Systems due to incorporation of latest actual costs for LRIP lots. (Navy) (Estimating) | +178.2 | +276.0
Decrease to Vehicle Systems due to incorporation of latest actual costs for LRIP lots. (Air Force) (Estimating) | -20.8 | -32.7
Increase to Vehicle Systems due to incorporation of latest actual costs for LRIP lots. (Navy) (Estimating) | +124.5 | +193
Increase due to incorporation of latest prime and subcontractor labor rates. (Air Force) (Estimating) | +1357.3 | +2165.5
Increase due to incorporation of latest prime and subcontractor labor rates. (Navy) (Estimating) | +393.1 | +609.1
Increase due to revised estimate of required risk funding based on OSD led Independent program assessments for Air Vehicle and Propulsion. (Air Force) (Estimating) | +8835.8 | +14095.2
Increase due to revised estimate of required risk funding based on OSD led Independent program assessments for Air Vehicle and Propulsion. (Navy) (Estimating) | +1486.7 | +2301.8
Increase for revised, slower International Partner procurement quantity profile. (Air Force) (Estimating) | +1039 | +1657.2
Increase for revised, slower International Partner procurement quantity profile. (Navy) (Estimating) | +238.5 | +369.4
Increase to Propulsion due to incorporation of latest actual costs for LRIP lots. (Air Force) (Estimating) | +266.3 | +425.1
Increase to Propulsion due to incorporation of latest actual costs for LRIP lots. (Navy) (Estimating) | +1349.0 | +2090.1
Decrease to Propulsion due to changes in estimating assumptions based on latest data from analogous engine. (Air Force) (Estimating) | -1509.3 | -2407.7
Decrease to Propulsion due to changes in estimating assumptions based on latest data from analogous engine. (Navy) (Estimating) | -836.7 | -1294.5
Multi-Year start changed from FY 2016 to 2018. (Air Force) (Estimating) | +579.9 | +924.9
Multi-Year start changed from FY 2016 to 2018. (Navy) (Estimating) | +267.5 | +414.7
Adjustment for current and prior escalation. (Support) | +8.6 | +10.6
Increase due to cost maturity, definition of customer requirements, and further definition of Service beddown plans. (Air Force) (Support) | +3247.5 | +4558.4
Increase in Initial Spares due to revised estimate. (Air Force) (Support) | +1251.6 | +2094.5
Increase due to cost maturity, definition of customer requirements, and further definition of Service beddown plans. (Navy) (Support) | +1548.2 | +2465.6
Initial spares increase due to revised estimate. (Navy) (Support) | 341.9 | 665.6
Procurement Subtotal | 28751.3 | 46911.3