## Pg 38
Fire Unit
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 20.1
Adjustment for current and prior escalation. (Estimating) | -11.8 | -14
Decrease in FY 2011 and FY 2012 due to Congressional reductions. (Estimating) | -28 | -33.5
Revised estimate to reflect change in dollar value in FY 2013. (Estimating) | -1.9 | -2.3
RDT&E Subtotal | -41.7 | -29.7
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | +1.7
Decrease in FY 2013 due to U.S. DoD decision to end Medium Extended Air Defense System program after the Design and Development phase. (Estimating) | -79 | -98.4
Procurement Subtotal | -79 | -96.7
Missile
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 2.8
Adjustment for current and prior escalation. (Estimating) | -1.9 | -2.3
Increase due to Omnibus reprogramming in FY 2011 to support Missile Segment Enhancement follow-on tests. (Estimating) | +49.4 | +58.5
RDT&E Subtotal | +47.5 | +59.0
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 219.6
Stretch-out of production program in FY 2013 to FY 2031. (Subtotal) | 59.4 | 239.5
Production delay by one year from FY 2013 to FY 2014. (Schedule) (QR) | 0 | -150
Additional Schedule Variance due to stretch-out of procurement buy profile from FY 2015 - FY 2031. (Schedule) (QR) | +48.6 | +75.4
Refinement of cost estimate associated with production delay of one year (FY 2013 to FY2014). (Estimating) (QR) | +10.8 | +14.1
Adjustment for current and prior escalation. (Estimating) | -0.7 | -0.9
Reallocation of funds from support to non-recurring flyaway for Initial Production Facilitization in FY 2013, due to production schedule slip from FY 2013 to FY 2014. (Support) | -12.8 | -1.9
Procurement Subtotal | +45.9 | +456.3
(QR) Quantity Related