## Table 1
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Increase due to escalation indices (Economic) | N/A | 236.3
Increase for multiple earmarks for technical scope in FY07 Appropriation (Engineering) | 8 | 9.2
Increase for F-136 funds restoration in FY07 Appropriation (Engineering) | 294.8 | 340
Increase for scope additions for Joint Reprogramming Center, Small Diameter Bomb-I and Net Ready Key Performance Parameter (Engineering) | 280.8 | 345.5
Adjustment for Current and Prior Inflation (Estimating) | -0.2 | -0.2
Decrease for reserve Award Fee funds reduction in FY07 Appropriation (Estimating) | -55.5 | -64
Decrease due to adjustments for prior years accounting updates (Estimating) | -33 | -33.7
Decrease due to revised assessment of required risk funding (Estimating) | -895.5 | -1141.6
RDT&E Subtotal | -400.6 | -308.5
Procurement | $M
Current Change Explanations | Base Year | Then Year
Decrease due to revised escalation indices (Economic) | N/A | -81.6
Increase due to lowered DoD annual procurement quantities which extended procurement completion from FY27 to FY34 (Schedule) | +589.2 | +11207
Increase for design maturation to reflect government assesssment based on LM 240-4.3,4,5 configuration (Engineering) | +824.3 | +1326.4
Adjustment for Current and Prior Inflation (Estimating) | -14.5 | -16.6
Revised estimate for increased cost of materials for airframe largely due to metals commodity markets increases (Estimating) | +3611.5 | +5472.8
Decrease due to revised assumptions for prime and subcontractor labor rates (Estimating) | -2341.2 | -3576.3
Decrease due to revised assumptions for subcontractor cost (Estimating) | -3414.7 | -5201.4
Increase due to revised assumptions based on contractor LRIP I proposals and methodology refinements (Estimating) | +5412.8 | +8307.1
Increase due to aircraft configuration update, revised procurement profiles, and methodology changes (Support) | +3164.2 | +6423.2
Procurement Subtotal | +7831.6 | +23361.4
MILCON | $M
Current Change Explanations | Base Year | Then Year
Increase due to revised escalation indices (Economic) | N/A | 3.2
Adjustment for Current and Prior Inflation (Estimating) | -0.1 | -0.1
Decrease for revised USAF estimates for planned sites (Estimating) | -25 | -30
Increase due to USAF estimates for additional sites (Estimating) | 266.3 | 339.2
MILCON Subtotal | 241.2 | 312.3