## CostSummary
Cost Summary
Total Acquisition Cost and Quantity - Total Program
| BY 2012 $M |  |  | BY2012 | TY $M
$M
Appropriation | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
[5 empty] | SAR Baseline Dev Est | Current APB Objective | Current Estimate
RDT&E | 59677.3 | 59677.3 | -- | 59172.9 | 55233.8 | 55233.8 | 54897.6
Procurement | 266665.8 | 266665.8 | -- | 260618.7 | 335680.7 | 335680.7 | 339266
Flyaway | -- | -- | -- | 226212.1 | -- | -- | 296396.3
Recurring | -- | -- | -- | 202475 | -- | -- | 266574
Non Recurring | -- | -- | -- | 23741.1 | -- | -- | 29822.3
Support | -- | -- | -- | 34402.6 | -- | -- | 42869.7
Other Support | -- | -- | -- | 18030.9 | -- | -- | 21775.2
Initial Spares | -- | -- | -- | 16371.7 | -- | -- | 21094.5
MILCON | 1468 | 4168 | -- | 3701.9 | 4797.3 | 4797.3 | 4421
Acq O&M | 0 | 0 | -- | 0 | 0 | -- | 0
Total | 330511.1 | 330511.1 | -- | 323493.5 | 395711.8 | 395711.8 | 398584.6
Total Acquisition Cost and Quantity - F-35 Aircraft
| BY 2012 $M |  |  | BY2012 | TY $M
$M
Appropriation | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
[5 empty] | SAR Baseline Dev Est | Current APB Objective | Current Estimate
RDT&E | 47982.1 | 47982.1 | 52780.9 | 45908.7 | 44410.1 | 44410.1 | 42772.6
Procurement | 224332.9 | 224332.9 | 246767.1 | 217450 | 282647.8 | 282647.8 | 282770.5
Flyaway | -- | -- | -- | 189815.1 | -- | -- | 248504.2
Recurring | -- | -- | -- | 168479.4 | -- | -- | 221638.9
Non Recurring | -- | -- | -- | 21335.7 | -- | -- | 26865.3
Support | -- | -- | -- | 27634.9 | -- | -- | 34266.3
Other Support | -- | -- | -- | 16129.3 | -- | -- | 19485.8
Initial Spares | -- | -- | -- | 11505.6 | -- | -- | 14780.5
MILCON | 4168 | 4168 | 4582.5 | 3701.9 | 4797.3 | 4797.3 | 4421
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 276483 | 276483 | N/A | 267060.6 | 331885.2 | 331885.2 | 329964.1
| SAR Baseline | Current APB Development | Current Estimate
Quantity | Dev Est
RDT&E | 14 | 14 | 14
Procurement | 2443 | 2443 | 2443
Total | 2457 | 2457 | 2457
Total Acquisition Cost and Quantity - F-35 Engine
| BY 2012 $M |  |  | BY2012 | TY $M
$M
Appropriation | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
[5 empty] | SAR Baseline Dev Est | Current APB Objective | Current Estimate
RDT&E | 11695.2 | 11695.2 | 12741.9 | 13264.2 | 10823.7 | 10823.7 | 12125
Procurement | 42322.9 | 42322.9 | 26566.2 | 43168.9 | 53032.9 | 53032.9 | 56495.5
Flyaway | -- | -- | -- | 36401 | -- | -- | 47892.1
Recurring | -- | -- | -- | 33995.6 | -- | -- | 44935.1
Non Recurring | -- | -- | -- | 2405.4 | -- | -- | 2957
Support | -- | -- | -- | 6767.7 | -- | -- | 8603.4
Other Support | -- | -- | -- | 1901.6 | -- | -- | 2289.4
Initial Spares | -- | -- | -- | 4866.1 | -- | -- | 6314
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 54028.1 | 54028.1 | N/A | 56432.9 | 63856.6 | 63856.6 | 68620.5
| SAR Baseline | Current APB Development | Current Estimate
Quantity | Dev Est
RDT&E | 14 | 14 | 14
Procurement | 2443 | 2443 | 2443
Total | 2457 | 2457 | 2457

## Funding Summary
Appropriation and Quantity Summary
Funding Summary - Total Program
FY 2015 President's Budget / December 2013 SAR (TY$ M)
To
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | Complete | Total
RDT&E | 48972 | 1454 | 1514.1 | 1587.4 | 1131.3 | 221.5 | 17.3 | 0 | 54897.6
Procurement | 33111.9 | 6057 | 6673.2 | 8883.5 | 10289.1 | 12039.7 | 12665.2 | 249546.4 | 339266
MILCON | 1235 | 56 | 207 | 66.7 | 228.6 | 328.5 | 175.7 | 2123.5 | 4421
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2012 Total | 83318.9 | 7567 | 8394.3 | 10537.6 | 11649 | 12589.7 | 12858.2 | 251669.9 | 398584.6
PB 2011 Total | 85004.3 | 8577.1 | 10087.5 | 11578.2 | 12220.3 | 13394.9 | 12417.3 | 237931.9 | 391211.5
Delta | -1685.4 | -1010.1 | -1693.2 | -1040.6 | -571.3 | -805.2 | 440.9 | 13738 | 7373.1
Funding Summary - F-35 Aircraft
FY 2015 President's Budget / December 2013 SAR (TY$ M)
To
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | Complete | Total
RDT&E | 37646.9 | 1170.4 | 1255.3 | 1375.1 | 1086.8 | 220.8 | 17.3 | 0 | 42772.6
Procurement | 27969.8 | 5305.1 | 5848.5 | 7658 | 8771.1 | 10143.8 | 10543.3 | 206530.9 | 282770.5
MILCON | 1235 | 56 | 207 | 66.7 | 228.6 | 328.5 | 175.7 | 2123.5 | 4421
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2012 Total | 66851.7 | 6531.5 | 7310.8 | 9099.8 | 10086.5 | 10693.1 | 10736.3 | 208654.4 | 329964.1
PB 2011 Total | 68494.9 | 7303.6 | 8891.2 | 10093.3 | 10528.7 | 11316.2 | 10355.3 | 199929.6 | 326912.8
Delta | -1643.2 | -772.1 | -1580.4 | -993.5 | -442.2 | -623.1 | 381 | 8724.8 | 3051.3
Quantity | Undistributed | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | To Complete | Total
Development | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Production | 0 | 150 | 29 | 34 | 55 | 68 | 90 | 96 | 1921 | 2443
PB 2012 Total | 14 | 150 | 29 | 34 | 55 | 68 | 90 | 96 | 1921 | 2457
PB 2011 Total | 14 | 150 | 29 | 42 | 62 | 76 | 100 | 100 | 1921 | 2457
Delta | 0 | 0 | 0 | -8 | -7 | -8 | -10 | -4 | 37 | 0
Funding Summary - F-35 Engine
FY 2015 President's Budget / December 2013 SAR (TY$ M)
To
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | Complete | Total
RDT&E | 11325.1 | 283.6 | 258.8 | 212.3 | 44.5 | 0.7 | 0 | 0 | 12125
Procurement | 5142.1 | 751.9 | 824.7 | 1225.5 | 1518 | 1895.9 | 2121.9 | 43015.5 | 56495.5
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2012 Total | 16467.2 | 1035.5 | 1083.5 | 1437.8 | 1562.5 | 1896.6 | 2121.9 | 43015.5 | 68620.5
PB 2011 Total | 16509.4 | 1273.5 | 1196.3 | 1484.9 | 1691.6 | 2078.7 | 2062 | 38002.3 | 64298.7
Delta | -42.2 | -238 | -112.8 | -47.1 | -129.1 | -182.1 | 59.9 | 5013.2 | 4321.8
Quantity | Undistributed | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | To Complete | Total
Development | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Production | 0 | 150 | 29 | 34 | 55 | 68 | 90 | 96 | 1921 | 2443
PB 2012 Total | 14 | 150 | 29 | 34 | 55 | 68 | 90 | 96 | 1921 | 2457
PB 2011 Total | 14 | 150 | 29 | 42 | 62 | 76 | 100 | 100 | 1921 | 2457
Delta | 0 | 0 | 0 | -8 | -7 | -8 | -10 | -4 | 37 | 0
Annual Funding TY$, RDT&E, F-35 Aircraft, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 23.2
1997 | -- | -- | -- | -- | -- | -- | 54.8
1998 | -- | -- | -- | -- | -- | -- | 16.9
Subtotal | -- | -- | -- | -- | -- | -- | 94.9
Annual Funding BY$, RDT&E, F-35 Aircraft, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
1996 | -- | -- | -- | -- | -- | -- | 30.1
1997 | -- | -- | -- | -- | -- | -- | 70.2
1998 | -- | -- | -- | -- | -- | -- | 21.5
Subtotal | -- | -- | -- | -- | -- | -- | 121.8
Annual Funding TY$, RDT&E, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | -- | -- | -- | -- | -- | -- | 67.5
1996 | -- | -- | -- | -- | -- | -- | 65.4
1997 | -- | -- | -- | -- | -- | -- | 202.3
1998 | -- | -- | -- | -- | -- | -- | 357.2
1999 | -- | -- | -- | -- | -- | -- | 366.5
2000 | -- | -- | -- | -- | -- | -- | 200.3
2001 | -- | -- | -- | -- | -- | -- | 274.3
2002 | -- | -- | -- | -- | -- | -- | 302.6
2003 | -- | -- | -- | -- | -- | -- | 1210.1
2004 | -- | -- | -- | -- | -- | -- | 1584.1
2005 | -- | -- | -- | -- | -- | -- | 1465.8
2006 | -- | -- | -- | -- | -- | -- | 1678.6
2007 | -- | -- | -- | -- | -- | -- | 1632.4
2008 | -- | -- | -- | -- | -- | -- | 1359
2009 | -- | -- | -- | -- | -- | -- | 1197.5
2010 | -- | -- | -- | -- | -- | -- | 1567.4
2011 | -- | -- | -- | -- | -- | -- | 715.4
2012 | -- | -- | -- | -- | -- | -- | 1262.2
2013 | -- | -- | -- | -- | -- | -- | 958.2
2014 | -- | -- | -- | -- | -- | -- | 550.2
2015 | -- | -- | -- | -- | -- | -- | 435.3
2016 | -- | -- | -- | -- | -- | -- | 438.3
2017 | -- | -- | -- | -- | -- | -- | 325.2
2018 | -- | -- | -- | -- | -- | -- | 115.2
2019 | -- | -- | -- | -- | -- | -- | 5.3
Subtotal | 5 | -- | -- | -- | -- | -- | 18336.3
Annual Funding BY$, RDT&E, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
1995 | -- | -- | -- | -- | -- | -- | 89.1
1996 | -- | -- | -- | -- | -- | -- | 84.9
1997 | -- | -- | -- | -- | -- | -- | 259.5
1998 | -- | -- | -- | -- | -- | -- | 454.5
1999 | -- | -- | -- | -- | -- | -- | 460.9
2000 | -- | -- | -- | -- | -- | -- | 248.3
2001 | -- | -- | -- | -- | -- | -- | 335.4
2002 | -- | -- | -- | -- | -- | -- | 366.3
2003 | -- | -- | -- | -- | -- | -- | 1443.6
2004 | -- | -- | -- | -- | -- | -- | 1838.4
2005 | -- | -- | -- | -- | -- | -- | 1657.5
2006 | -- | -- | -- | -- | -- | -- | 1840.8
2007 | -- | -- | -- | -- | -- | -- | 1747.3
2008 | -- | -- | -- | -- | -- | -- | 1428.6
2009 | -- | -- | -- | -- | -- | -- | 1242.9
2010 | -- | -- | -- | -- | -- | -- | 1602.8
2011 | -- | -- | -- | -- | -- | -- | 714.1
2012 | -- | -- | -- | -- | -- | -- | 1238.3
2013 | -- | -- | -- | -- | -- | -- | 925.5
2014 | -- | -- | -- | -- | -- | -- | 522.5
2015 | -- | -- | -- | -- | -- | -- | 405.8
2016 | -- | -- | -- | -- | -- | -- | 400.7
2017 | -- | -- | -- | -- | -- | -- | 291.5
2018 | -- | -- | -- | -- | -- | -- | 101.2
2019 | -- | -- | -- | -- | -- | -- | 4.6
Subtotal | 5 | -- | -- | -- | -- | -- | 19705
Annual Funding TY$, RDT&E, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 23.7
1995 | -- | -- | -- | -- | -- | -- | 78.7
1996 | -- | -- | -- | -- | -- | -- | 64.6
1997 | -- | -- | -- | -- | -- | -- | 195.6
1998 | -- | -- | -- | -- | -- | -- | 360.4
1999 | -- | -- | -- | -- | -- | -- | 378.9
2000 | -- | -- | -- | -- | -- | -- | 191.7
2001 | -- | -- | -- | -- | -- | -- | 274.3
2002 | -- | -- | -- | -- | -- | -- | 367.1
2003 | -- | -- | -- | -- | -- | -- | 1089.5
2004 | -- | -- | -- | -- | -- | -- | 1548.2
2005 | -- | -- | -- | -- | -- | -- | 1510.3
2006 | -- | -- | -- | -- | -- | -- | 1657.3
2007 | -- | -- | -- | -- | -- | -- | 1470.7
2008 | -- | -- | -- | -- | -- | -- | 1285
2009 | -- | -- | -- | -- | -- | -- | 1271.2
2010 | -- | -- | -- | -- | -- | -- | 1440.5
2011 | -- | -- | -- | -- | -- | -- | 989.9
2012 | -- | -- | -- | -- | -- | -- | 960.1
2013 | -- | -- | -- | -- | -- | -- | 1079.4
2014 | -- | -- | -- | -- | -- | -- | 602.1
2015 | -- | -- | -- | -- | -- | -- | 813.6
2016 | -- | -- | -- | -- | -- | -- | 934.2
2017 | -- | -- | -- | -- | -- | -- | 753.5
2018 | -- | -- | -- | -- | -- | -- | 102.5
2019 | -- | -- | -- | -- | -- | -- | 12
Subtotal | 9 | -- | -- | -- | -- | -- | 19455
Annual Funding BY$, RDT&E, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
1994 | -- | -- | -- | -- | -- | -- | 31.9
1995 | -- | -- | -- | -- | -- | -- | 103.9
1996 | -- | -- | -- | -- | -- | -- | 83.9
1997 | -- | -- | -- | -- | -- | -- | 250.9
1998 | -- | -- | -- | -- | -- | -- | 458.6
1999 | -- | -- | -- | -- | -- | -- | 476.5
2000 | -- | -- | -- | -- | -- | -- | 237.6
2001 | -- | -- | -- | -- | -- | -- | 335.4
2002 | -- | -- | -- | -- | -- | -- | 444.4
2003 | -- | -- | -- | -- | -- | -- | 1299.7
2004 | -- | -- | -- | -- | -- | -- | 1796.8
2005 | -- | -- | -- | -- | -- | -- | 1707.8
2006 | -- | -- | -- | -- | -- | -- | 1817.4
2007 | -- | -- | -- | -- | -- | -- | 1574.3
2008 | -- | -- | -- | -- | -- | -- | 1350.8
2009 | -- | -- | -- | -- | -- | -- | 1319.4
2010 | -- | -- | -- | -- | -- | -- | 1473
2011 | -- | -- | -- | -- | -- | -- | 988.1
2012 | -- | -- | -- | -- | -- | -- | 941.9
2013 | -- | -- | -- | -- | -- | -- | 1042.5
2014 | -- | -- | -- | -- | -- | -- | 571.8
2015 | -- | -- | -- | -- | -- | -- | 758.4
2016 | -- | -- | -- | -- | -- | -- | 854
2017 | -- | -- | -- | -- | -- | -- | 675.3
2018 | -- | -- | -- | -- | -- | -- | 90.1
2019 | -- | -- | -- | -- | -- | -- | 10.3
Subtotal | 9 | -- | -- | -- | -- | -- | 20694.7
Annual Funding TY$, RDT&E, F-35 Aircraft, Non Treasury Friends
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 11.3
1997 | -- | -- | -- | -- | -- | -- | 67.1
1998 | -- | -- | -- | -- | -- | -- | 72.1
1999 | -- | -- | -- | -- | -- | -- | 49
2000 | -- | -- | -- | -- | -- | -- | 25.2
2001 | -- | -- | -- | -- | -- | -- | 9.5
2002 | -- | -- | -- | -- | -- | -- | 255.8
2003 | -- | -- | -- | -- | -- | -- | 298.7
2004 | -- | -- | -- | -- | -- | -- | 484.1
2005 | -- | -- | -- | -- | -- | -- | 734.3
2006 | -- | -- | -- | -- | -- | -- | 801.3
2007 | -- | -- | -- | -- | -- | -- | 635.3
2008 | -- | -- | -- | -- | -- | -- | 574
2009 | -- | -- | -- | -- | -- | -- | 236
2010 | -- | -- | -- | -- | -- | -- | 143.2
2011 | -- | -- | -- | -- | -- | -- | 171.9
2012 | -- | -- | -- | -- | -- | -- | 130.8
2013 | -- | -- | -- | -- | -- | -- | 148.5
2014 | -- | -- | -- | -- | -- | -- | 18.1
2015 | -- | -- | -- | -- | -- | -- | 6.4
2016 | -- | -- | -- | -- | -- | -- | 2.6
2017 | -- | -- | -- | -- | -- | -- | 8.1
2018 | -- | -- | -- | -- | -- | -- | 3.1
Subtotal | 9 | -- | -- | -- | -- | -- | 20694.7
Annual Funding BY$, RDT&E, F-35 Aircraft, Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
1996 | -- | -- | -- | -- | -- | -- | 14.7
1997 | -- | -- | -- | -- | -- | -- | 86.1
1998 | -- | -- | -- | -- | -- | -- | 91.7
1999 | -- | -- | -- | -- | -- | -- | 61.6
2000 | -- | -- | -- | -- | -- | -- | 31.2
2001 | -- | -- | -- | -- | -- | -- | 11.6
2002 | -- | -- | -- | -- | -- | -- | 309.6
2003 | -- | -- | -- | -- | -- | -- | 356.3
2004 | -- | -- | -- | -- | -- | -- | 561.8
2005 | -- | -- | -- | -- | -- | -- | 830.3
2006 | -- | -- | -- | -- | -- | -- | 878.7
2007 | -- | -- | -- | -- | -- | -- | 680
2008 | -- | -- | -- | -- | -- | -- | 603.4
2009 | -- | -- | -- | -- | -- | -- | 244.9
2010 | -- | -- | -- | -- | -- | -- | 146.4
2011 | -- | -- | -- | -- | -- | -- | 171.6
2012 | -- | -- | -- | -- | -- | -- | 128.3
2013 | -- | -- | -- | -- | -- | -- | 143.4
2014 | -- | -- | -- | -- | -- | -- | 17.2
2015 | -- | -- | -- | -- | -- | -- | 6
2016 | -- | -- | -- | -- | -- | -- | 2.4
2017 | -- | -- | -- | -- | -- | -- | 7.3
2018 | -- | -- | -- | -- | -- | -- | 2.7
Subtotal | -- | -- | -- | -- | -- | -- | 5387.2
Annual Funding TY$, Procurement, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | 107.6 | -- | -- | 107.6 | -- | 107.6
2007 | 2 | 428.5 | -- | 80.8 | 509.3 | 91.1 | 600.4
2008 | 6 | 983.1 | -- | 172.3 | 1155.4 | 131.5 | 1286.9
2009 | 7 | 1009.2 | -- | 277.6 | 1286.8 | 175.8 | 1462.6
2010 | 10 | 1471.2 | -- | 355.7 | 1826.9 | 277.7 | 2104.6
2011 | 22 | 2751.2 | -- | 569.1 | 3320.3 | 679.6 | 3999.9
2012 | 18 | 2041.5 | -- | 369.6 | 2411.1 | 773.5 | 3184.6
2013 | 19 | 2074.6 | -- | 98.3 | 2172.9 | 532.6 | 2705.5
2014 | 19 | 2034.6 | -- | 616.6 | 2651.2 | 433 | 3084.2
2015 | 26 | 2526.8 | -- | 711.5 | 3238.3 | 537.2 | 3775.5
2016 | 44 | 4041.1 | -- | 617.8 | 4658.9 | 648 | 5306.9
2017 | 48 | 4078.9 | -- | 746.4 | 4825.3 | 665.7 | 5491
2018 | 60 | 4762.1 | -- | 650.2 | 5412.3 | 707.3 | 6119.6
2019 | 60 | 4657.9 | -- | 594.1 | 5252 | 732.7 | 5984.7
2020 | 60 | 4585.3 | -- | 465.3 | 5050.6 | 771.5 | 5822.1
2021 | 80 | 5843.8 | -- | 578.7 | 6422.5 | 893.9 | 7316.4
2022 | 80 | 5942.6 | -- | 588.8 | 6531.4 | 896.7 | 7428.1
2023 | 80 | 6089 | -- | 604.2 | 6693.2 | 969.2 | 7662.4
2024 | 80 | 6206.5 | -- | 612.2 | 6818.7 | 890.6 | 7709.3
2025 | 80 | 6348.5 | -- | 622.7 | 6971.2 | 880.6 | 7851.8
2026 | 80 | 6509.7 | -- | 639.4 | 7149.1 | 921.3 | 8070.4
2027 | 80 | 6632.9 | -- | 650.2 | 7283.1 | 938.8 | 8221.9
2028 | 80 | 6763 | -- | 656.6 | 7419.6 | 770.9 | 8190.5
2029 | 80 | 6900.5 | -- | 647 | 7547.5 | 932.8 | 8480.3
2030 | 80 | 7052.6 | -- | 656.7 | 7709.3 | 922.8 | 8632.1
2031 | 80 | 7243 | -- | 679.1 | 7922.1 | 989 | 8911.1
2032 | 80 | 7342.4 | -- | 686.1 | 8028.5 | 738.2 | 8766.7
2033 | 80 | 7636.3 | -- | 707.1 | 8343.4 | 647.6 | 8991
2034 | 80 | 7875.1 | -- | 727.9 | 8603 | 411.1 | 9014.1
2035 | 80 | 8059.1 | -- | 742.4 | 8801.5 | 414.8 | 9216.3
2036 | 80 | 8294.6 | -- | 731.8 | 9026.4 | 360.7 | 9387.1
2037 | 80 | 7468.2 | -- | 720.1 | 8188.3 | 374.1 | 8562.4
2038 | 2 | 556.3 | -- | 34.2 | 590.5 | 48 | 638.5
Subtotal | 1763 | 156317.7 | -- | 17610.5 | 173928.2 | 20158.3 | 194086.5
Annual Funding BY$, Procurement, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
2006 | -- | 116.3 | -- | -- | 116.3 | -- | 116.3
2007 | 2 | 452.5 | -- | 85.4 | 537.9 | 96.2 | 634.1
2008 | 6 | 1022.9 | -- | 179.3 | 1202.2 | 136.8 | 1339
2009 | 7 | 1035.6 | -- | 284.9 | 1320.5 | 180.4 | 1500.9
2010 | 10 | 1478.3 | -- | 357.5 | 1835.8 | 279 | 2114.8
2011 | 22 | 2707.2 | -- | 560 | 3267.2 | 668.7 | 3935.9
2012 | 18 | 1977.7 | -- | 358 | 2335.7 | 749.3 | 3085
2013 | 19 | 1976.5 | -- | 93.7 | 2070.2 | 507.3 | 2577.5
2014 | 19 | 1904 | -- | 577 | 2481 | 405.2 | 2886.2
2015 | 26 | 2320 | -- | 653.3 | 2973.3 | 493.2 | 3466.5
2016 | 44 | 3638.1 | -- | 556.2 | 4194.3 | 583.4 | 4777.7
2017 | 48 | 3600.2 | -- | 658.8 | 4259 | 587.5 | 4846.5
2018 | 60 | 4120.8 | -- | 562.6 | 4683.4 | 612 | 5295.4
2019 | 60 | 3951.6 | -- | 504 | 4455.6 | 621.6 | 5077.2
2020 | 60 | 3813.7 | -- | 387 | 4200.7 | 641.7 | 4842.4
2021 | 80 | 4765.1 | -- | 471.9 | 5237 | 728.9 | 5965.9
2022 | 80 | 4750.7 | -- | 470.6 | 5221.3 | 716.9 | 5938.2
2023 | 80 | 4772.3 | -- | 473.5 | 5245.8 | 759.6 | 6005.4
2024 | 80 | 4769 | -- | 470.3 | 5239.3 | 684.4 | 5923.7
2025 | 80 | 4782.4 | -- | 469.2 | 5251.6 | 663.3 | 5914.9
2026 | 80 | 4807.7 | -- | 472.3 | 5280 | 680.4 | 5960.4
2027 | 80 | 4802.6 | -- | 470.9 | 5273.5 | 679.7 | 5953.2
2028 | 80 | 4800.8 | -- | 466.2 | 5267 | 547.2 | 5814.2
2029 | 80 | 4802.4 | -- | 450.2 | 5252.6 | 649.2 | 5901.8
2030 | 80 | 4812 | -- | 448.1 | 5260.1 | 629.6 | 5889.7
2031 | 80 | 4845 | -- | 454.2 | 5299.2 | 661.6 | 5960.8
2032 | 80 | 4815.2 | -- | 450 | 5265.2 | 484.1 | 5749.3
2033 | 80 | 4909.7 | -- | 454.6 | 5364.3 | 416.4 | 5780.7
2034 | 80 | 4964 | -- | 458.9 | 5422.9 | 259.1 | 5682
2035 | 80 | 4980.4 | -- | 458.7 | 5439.1 | 256.4 | 5695.5
2036 | 80 | 5025.4 | -- | 443.4 | 5468.8 | 218.5 | 5687.3
2037 | 80 | 4436 | -- | 427.6 | 4863.6 | 222.3 | 5085.9
2038 | 2 | 324 | -- | 19.9 | 343.9 | 27.9 | 371.8
Subtotal | 1763 | 116280.1 | -- | 13648.2 | 129928.3 | 15847.8 | 145776.1
Cost Quantity Information, Procurement, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2012 $M
2006 | -- | --
2007 | 2 | 452.5
2008 | 6 | 1022.9
2009 | 7 | 1035.6
2010 | 10 | 1478.3
2011 | 22 | 2707.2
2012 | 18 | 1977.7
2013 | 19 | 1976.5
2014 | 19 | 1904
2015 | 26 | 2320
2016 | 44 | 3638.1
2017 | 48 | 3600.2
2018 | 60 | 4120.8
2019 | 60 | 3951.6
2020 | 60 | 3813.7
2021 | 80 | 4765.1
2022 | 80 | 4790.7
2023 | 80 | 4772.3
2024 | 80 | 4769
2025 | 80 | 4782.4
2026 | 80 | 4807.7
2027 | 80 | 4802.6
2028 | 80 | 4800.8
2029 | 80 | 4802.4
2030 | 80 | 4812
2031 | 80 | 4845
2032 | 80 | 4815.2
2033 | 80 | 4909.7
2034 | 80 | 4964
2035 | 80 | 4980.4
2036 | 80 | 5064.2
2037 | 80 | 4434.8
2038 | 2 | 362.7
Subtotal | 1763 | 116280.1
Annual Funding TY$, Procurement, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2007 | -- | 96.9 | -- | -- | 96.9 | -- | 96.9
2008 | 6 | 923.2 | -- | 38.6 | 961.8 | 10.7 | 972.5
2009 | 7 | 1062 | -- | 182 | 1244 | 206.1 | 1450.1
2010 | 20 | 2681.2 | -- | 304.7 | 2985.9 | 560.9 | 3546.8
2011 | 10 | 1494.8 | -- | 251.6 | 1746.4 | 431.8 | 2178.2
2012 | 13 | 1477.7 | -- | 333.1 | 1810.8 | 746.7 | 2557.5
2013 | 10 | 1107.3 | -- | 51.1 | 1158.4 | 557.3 | 1715.7
2014 | 10 | 1205.5 | -- | 439.7 | 1645.2 | 575.7 | 2220.9
2015 | 8 | 883.5 | -- | 762.3 | 1645.8 | 427.2 | 2073
2016 | 11 | 1196.2 | -- | 547.7 | 1743.9 | 607.2 | 2351.1
2017 | 20 | 2012 | -- | 672.1 | 2684.1 | 596 | 3280.1
2018 | 30 | 2769.5 | -- | 568.9 | 3338.4 | 685.8 | 4024.2
2019 | 36 | 3332.3 | -- | 523.8 | 3856.1 | 702.5 | 4558.6
2020 | 40 | 3419.2 | -- | 350.2 | 3769.4 | 967.1 | 4736.5
2021 | 40 | 3394.8 | -- | 361.6 | 3756.4 | 1101.8 | 4858.2
2022 | 40 | 3420.3 | -- | 359.8 | 3780.1 | 932.7 | 4712.8
2023 | 40 | 3434 | -- | 365.2 | 3799.2 | 815.1 | 4614.3
2024 | 40 | 3493.4 | -- | 357.8 | 3851.2 | 867.2 | 4718.4
2025 | 40 | 3543 | -- | 366.7 | 3909.7 | 770.2 | 4679.9
2026 | 40 | 3605.4 | -- | 369.2 | 3974.6 | 636.9 | 4611.5
2027 | 40 | 3660.9 | -- | 390 | 4050.9 | 430.5 | 4481.4
2028 | 40 | 3722.4 | -- | 399.9 | 4122.3 | 381.2 | 4503.5
2029 | 40 | 3786.7 | -- | 374.1 | 4160.8 | 326.1 | 4486.9
2030 | 40 | 3620.5 | -- | 380.1 | 4000.6 | 313.8 | 4314.4
2031 | 21 | 2171.5 | -- | 189 | 2360.5 | 217 | 2577.5
2032 | 20 | 2084.6 | -- | 162.5 | 2247.1 | 127.6 | 2374.7
2033 | 18 | 1722.4 | -- | 153.1 | 1875.5 | 112.9 | 1988.4
Subtotal | 680 | 65321.2 | -- | 9254.8 | 74576 | 14108 | 88684
Annual Funding BY$, Procurement, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
2007 | -- | 102.3 | -- | -- | 102.3 | -- | 102.3
2008 | 6 | 960.6 | -- | 40.2 | 1000.8 | 11.1 | 1011.9
2009 | 7 | 1089.8 | -- | 186.8 | 1276.6 | 211.5 | 1488.1
2010 | 20 | 2694.2 | -- | 306.2 | 3000.4 | 563.6 | 3564
2011 | 10 | 1470.9 | -- | 247.6 | 1718.5 | 424.9 | 2143.4
2012 | 13 | 1431.5 | -- | 322.7 | 1754.2 | 723.3 | 2477.5
2013 | 10 | 1054.9 | -- | 48.7 | 1103.6 | 530.9 | 1634.5
2014 | 10 | 1128.1 | -- | 411.5 | 1539.6 | 538.7 | 2078.3
2015 | 8 | 811.2 | -- | 699.9 | 1511.1 | 392.2 | 1903.3
2016 | 11 | 1076.9 | -- | 493.2 | 1570.1 | 546.6 | 2116.7
2017 | 20 | 1775.9 | -- | 593.2 | 2369.1 | 526 | 2895.1
2018 | 30 | 2396.5 | -- | 492.3 | 2888.8 | 593.4 | 3482.2
2019 | 36 | 2827 | -- | 444.3 | 3271.3 | 596 | 3867.3
2020 | 40 | 2843.8 | -- | 291.3 | 3135.1 | 804.3 | 3939.4
2021 | 40 | 2768.2 | -- | 294.9 | 3063.1 | 898.3 | 3961.4
2022 | 40 | 2734.3 | -- | 287.6 | 3021.9 | 745.6 | 3767.5
2023 | 40 | 2691.4 | -- | 286.2 | 2977.6 | 638.9 | 3616.5
2024 | 40 | 2684.3 | -- | 274.9 | 2959.2 | 666.3 | 3625.5
2025 | 40 | 2669 | -- | 276.2 | 2945.2 | 580.2 | 3525.4
2026 | 40 | 2662.7 | -- | 272.7 | 2935.4 | 470.4 | 3405.8
2027 | 40 | 2650.7 | -- | 282.4 | 2933.1 | 311.7 | 3244.8
2028 | 40 | 2642.4 | -- | 283.9 | 2926.3 | 270.6 | 3196.9
2029 | 40 | 2635.3 | -- | 260.3 | 2895.6 | 227 | 3122.6
2030 | 40 | 2470.3 | -- | 259.3 | 2729.6 | 214.1 | 2943.7
2031 | 21 | 1452.6 | -- | 126.3 | 1578.9 | 145.2 | 1724.1
2032 | 20 | 1367.1 | -- | 106.5 | 1473.6 | 83.7 | 1557.3
2033 | 18 | 1107.4 | -- | 98.4 | 1205.8 | 72.6 | 1278.4
Subtotal | 680 | 52199.3 | -- | 7687.5 | 59886.8 | 11787.1 | 71673.9
Cost Quantity Information, Procurement, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2012 $M
2007 | -- | --
2008 | 6 | 960.6
2009 | 7 | 1089.8
2010 | 20 | 2694.2
2011 | 10 | 1470.9
2012 | 13 | 1431.5
2013 | 10 | 1054.9
2014 | 10 | 1128.1
2015 | 8 | 811.2
2016 | 11 | 1076.9
2017 | 20 | 1775.9
2018 | 30 | 2396.5
2019 | 36 | 2827
2020 | 40 | 2843.8
2021 | 40 | 2768.2
2022 | 40 | 2734.3
2023 | 40 | 2691.4
2024 | 40 | 2684.3
2025 | 40 | 2669
2026 | 40 | 2662.7
2027 | 40 | 2650.7
2028 | 40 | 2642.4
2029 | 40 | 2635.3
2030 | 40 | 2470.3
2031 | 21 | 1486.7
2032 | 20 | 1401.2
2033 | 18 | 1141.5
Subtotal | 680 | 52199.3
Annual Funding TY $, F-35 Aircraft, Military Construction, Navy and Marine Corps
Fiscal Year | Total Program TY $M
2004 | 24.4
2005 | --
2006 | 0.1
2007 | --
2008 | 0.2
2009 | 0.7
2010 | 34.1
2011 | 377.9
2012 | 172.2
2013 | 94.9
2014 | --
2015 | 140.3
2016 | 16.3
2017 | 213.9
2018 | 192.6
2019 | 84.2
2020 | 175.8
2021 | 105.2
2022 | 79.8
2023 | --
2024 | 300.1
Subtotal | 2012.7
Annual Funding BY $, F-35 Aircraft, Military Construction, Navy and Marine Corps
Fiscal Year | Total Program TY $M
2004 | 27.8
2005 | --
2006 | 0.1
2007 | --
2008 | 0.2
2009 | 0.7
2010 | 34.1
2011 | 368.5
2012 | 165.2
2013 | 89.5
2014 | --
2015 | 127.4
2016 | 14.5
2017 | 186.6
2018 | 164.8
2019 | 70.6
2020 | 144.5
2021 | 84.8
2022 | 63.1
2023 | --
2024 | 228
Subtotal | 1770.4
Annual Funding TY $, F-35 Aircraft, Military Construction, Air Force
Fiscal Year | Total Program TY $M
2004 | 1.7
2005 | 10
2006 | --
2007 | --
2008 | 100.3
2009 | 116
2010 | 125.1
2011 | 139.6
2012 | 24.3
2013 | 13.5
2014 | 56
2015 | 66.7
2016 | 50.4
2017 | 14.7
2018 | 135.9
2019 | 91.5
2020 | 134.6
2021 | 66.6
2022 | 73.1
2023 | 167
2024 | 142.3
2025 | 122.1
2026 | 118.4
2027 | 129.9
2028 | 101.8
2029 | 102.7
2030 | 94.6
2031 | 71.7
2032 | 71.2
2033 | 37.5
2034 | 24.8
2035 | 4.3
Subtotal | 2408.3
Annual Funding BY$, F-35 Aircraft, Military Construction, Air Force
Fiscal Year | Total Program TY $M
2004 | 1.9
2005 | 11.1
2006 | --
2007 | --
2008 | 104.1
2009 | 118.8
2010 | 125
2011 | 136.1
2012 | 23.3
2013 | 12.7
2014 | 51.8
2015 | 60.5
2016 | 44.9
2017 | 12.8
2018 | 80.4
2019 | 76.7
2020 | 110.7
2021 | 53.7
2022 | 57.8
2023 | 129.4
2024 | 108.1
2025 | 90.9
2026 | 86.4
2027 | 93
2028 | 71.4
2029 | 70.7
2030 | 63.8
2031 | 47.4
2032 | 46.2
2033 | 23.8
2034 | 15.5
2035 | 2.6
Subtotal | 1931.5
Annual Funding TY$, RDT&E, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | -- | -- | -- | -- | -- | -- | 16.4
1996 | -- | -- | -- | -- | -- | -- | 15.9
1997 | -- | -- | -- | -- | -- | -- | 49.3
1998 | -- | -- | -- | -- | -- | -- | 87.1
1999 | -- | -- | -- | -- | -- | -- | 89.4
2000 | -- | -- | -- | -- | -- | -- | 48.8
2001 | -- | -- | -- | -- | -- | -- | 66.9
2002 | -- | -- | -- | -- | -- | -- | 409.8
2003 | -- | -- | -- | -- | -- | -- | 400.5
2004 | -- | -- | -- | -- | -- | -- | 435.8
2005 | -- | -- | -- | -- | -- | -- | 614.3
2006 | -- | -- | -- | -- | -- | -- | 586.3
2007 | -- | -- | -- | -- | -- | -- | 441.6
2008 | -- | -- | -- | -- | -- | -- | 596
2009 | -- | -- | -- | -- | -- | -- | 544.6
2010 | -- | -- | -- | -- | -- | -- | 466.1
2011 | -- | -- | -- | -- | -- | -- | 216.2
2012 | -- | -- | -- | -- | -- | -- | 101.8
2013 | -- | -- | -- | -- | -- | -- | 157.5
2014 | -- | -- | -- | -- | -- | -- | 62.1
2015 | -- | -- | -- | -- | -- | -- | 100.1
2016 | -- | -- | -- | -- | -- | -- | 84.3
2017 | -- | -- | -- | -- | -- | -- | 1.9
2018 | -- | -- | -- | -- | -- | -- | 0.2
Subtotal | 5 | -- | -- | -- | -- | -- | 5592.9
Annual Funding BY$, RDT&E, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
1995 | -- | -- | -- | -- | -- | -- | 21.7
1996 | -- | -- | -- | -- | -- | -- | 20.6
1997 | -- | -- | -- | -- | -- | -- | 63.2
1998 | -- | -- | -- | -- | -- | -- | 110.8
1999 | -- | -- | -- | -- | -- | -- | 112.4
2000 | -- | -- | -- | -- | -- | -- | 60.5
2001 | -- | -- | -- | -- | -- | -- | 81.8
2002 | -- | -- | -- | -- | -- | -- | 496
2003 | -- | -- | -- | -- | -- | -- | 477.8
2004 | -- | -- | -- | -- | -- | -- | 505.8
2005 | -- | -- | -- | -- | -- | -- | 694.7
2006 | -- | -- | -- | -- | -- | -- | 643
2007 | -- | -- | -- | -- | -- | -- | 472.7
2008 | -- | -- | -- | -- | -- | -- | 626.5
2009 | -- | -- | -- | -- | -- | -- | 565.2
2010 | -- | -- | -- | -- | -- | -- | 476.6
2011 | -- | -- | -- | -- | -- | -- | 215.8
2012 | -- | -- | -- | -- | -- | -- | 99.9
2013 | -- | -- | -- | -- | -- | -- | 152.1
2014 | -- | -- | -- | -- | -- | -- | 59
2015 | -- | -- | -- | -- | -- | -- | 93.3
2016 | -- | -- | -- | -- | -- | -- | 77.1
2017 | -- | -- | -- | -- | -- | -- | 1.7
2018 | -- | -- | -- | -- | -- | -- | 0.2
Subtotal | 5 | -- | -- | -- | -- | -- | 6128.4
Annual Funding TY$, RDT&E, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 5.8
1995 | -- | -- | -- | -- | -- | -- | 19.3
1996 | -- | -- | -- | -- | -- | -- | 15.8
1997 | -- | -- | -- | -- | -- | -- | 47.7
1998 | -- | -- | -- | -- | -- | -- | 87.8
1999 | -- | -- | -- | -- | -- | -- | 92.4
2000 | -- | -- | -- | -- | -- | -- | 46.7
2001 | -- | -- | -- | -- | -- | -- | 66.9
2002 | -- | -- | -- | -- | -- | -- | 350.4
2003 | -- | -- | -- | -- | -- | -- | 550.8
2004 | -- | -- | -- | -- | -- | -- | 533.2
2005 | -- | -- | -- | -- | -- | -- | 573.5
2006 | -- | -- | -- | -- | -- | -- | 528.1
2007 | -- | -- | -- | -- | -- | -- | 639.1
2008 | -- | -- | -- | -- | -- | -- | 563.9
2009 | -- | -- | -- | -- | -- | -- | 433.1
2010 | -- | -- | -- | -- | -- | -- | 445.7
2011 | -- | -- | -- | -- | -- | -- | 250.9
2012 | -- | -- | -- | -- | -- | -- | 187.6
2013 | -- | -- | -- | -- | -- | -- | 202
2014 | -- | -- | -- | -- | -- | -- | 221.5
2015 | -- | -- | -- | -- | -- | -- | 158.7
2016 | -- | -- | -- | -- | -- | -- | 128
2017 | -- | -- | -- | -- | -- | -- | 42.6
2018 | -- | -- | -- | -- | -- | -- | 0.5
Subtotal | 9 | -- | -- | -- | -- | -- | 6192
Annual Funding BY$, RDT&E, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
1994 | -- | -- | -- | -- | -- | -- | 7.8
1995 | -- | -- | -- | -- | -- | -- | 25.5
1996 | -- | -- | -- | -- | -- | -- | 20.5
1997 | -- | -- | -- | -- | -- | -- | 61.2
1998 | -- | -- | -- | -- | -- | -- | 111.7
1999 | -- | -- | -- | -- | -- | -- | 116.2
2000 | -- | -- | -- | -- | -- | -- | 57.9
2001 | -- | -- | -- | -- | -- | -- | 81.8
2002 | -- | -- | -- | -- | -- | -- | 424.1
2003 | -- | -- | -- | -- | -- | -- | 657.1
2004 | -- | -- | -- | -- | -- | -- | 618.8
2005 | -- | -- | -- | -- | -- | -- | 648.5
2006 | -- | -- | -- | -- | -- | -- | 579.1
2007 | -- | -- | -- | -- | -- | -- | 684.1
2008 | -- | -- | -- | -- | -- | -- | 592.8
2009 | -- | -- | -- | -- | -- | -- | 449.5
2010 | -- | -- | -- | -- | -- | -- | 455.8
2011 | -- | -- | -- | -- | -- | -- | 250.4
2012 | -- | -- | -- | -- | -- | -- | 184.1
2013 | -- | -- | -- | -- | -- | -- | 195.1
2014 | -- | -- | -- | -- | -- | -- | 210.3
2015 | -- | -- | -- | -- | -- | -- | 147.9
2016 | -- | -- | -- | -- | -- | -- | 117
2017 | -- | -- | -- | -- | -- | -- | 38.2
2018 | -- | -- | -- | -- | -- | -- | 0.4
Subtotal | 9 | -- | -- | -- | -- | -- | 6735.8
Annual Funding TY$, RDT&E, F-35 Engine, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 5.7
1995 | -- | -- | -- | -- | -- | -- | 13.4
1996 | -- | -- | -- | -- | -- | -- | 4
Subtotal | -- | -- | -- | -- | -- | -- | 23.1
Annual Funding BY$, RDT&E, F-35 Engine, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
1994 | -- | -- | -- | -- | -- | -- | 7.7
1995 | -- | -- | -- | -- | -- | -- | 17.7
1996 | -- | -- | -- | -- | -- | -- | 5.2
Subtotal | -- | -- | -- | -- | -- | -- | 30.6
Annual Funding TY$, RDT&E, F-35 Engine, Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 2.7
1997 | -- | -- | -- | -- | -- | -- | 3.9
1998 | -- | -- | -- | -- | -- | -- | 5.1
1999 | -- | -- | -- | -- | -- | -- | 5.7
2000 | -- | -- | -- | -- | -- | -- | 1.8
2001 | -- | -- | -- | -- | -- | -- | 0.5
2002 | -- | -- | -- | -- | -- | -- | 43.3
2003 | -- | -- | -- | -- | -- | -- | 124.3
2004 | -- | -- | -- | -- | -- | -- | 54.1
2005 | -- | -- | -- | -- | -- | -- | 0.3
2006 | -- | -- | -- | -- | -- | -- | --
2007 | -- | -- | -- | -- | -- | -- | 75
2008 | -- | -- | -- | -- | -- | -- | --
2009 | -- | -- | -- | -- | -- | -- | --
2010 | -- | -- | -- | -- | -- | -- | --
2011 | -- | -- | -- | -- | -- | -- | --
2012 | -- | -- | -- | -- | -- | -- | --
2013 | -- | -- | -- | -- | -- | -- | 0.3
Subtotal | -- | -- | -- | -- | -- | -- | 317
Annual Funding BY$, RDT&E, F-35 Engine, Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
1996 | -- | -- | -- | -- | -- | -- | 3.5
1997 | -- | -- | -- | -- | -- | -- | 5
1998 | -- | -- | -- | -- | -- | -- | 6.5
1999 | -- | -- | -- | -- | -- | -- | 7.2
2000 | -- | -- | -- | -- | -- | -- | 2.2
2001 | -- | -- | -- | -- | -- | -- | 0.6
2002 | -- | -- | -- | -- | -- | -- | 52.4
2003 | -- | -- | -- | -- | -- | -- | 148.3
2004 | -- | -- | -- | -- | -- | -- | 62.8
2005 | -- | -- | -- | -- | -- | -- | 0.3
2006 | -- | -- | -- | -- | -- | -- | --
2007 | -- | -- | -- | -- | -- | -- | 80.3
2008 | -- | -- | -- | -- | -- | -- | --
2009 | -- | -- | -- | -- | -- | -- | --
2010 | -- | -- | -- | -- | -- | -- | --
2011 | -- | -- | -- | -- | -- | -- | --
2012 | -- | -- | -- | -- | -- | -- | --
2013 | -- | -- | -- | -- | -- | -- | 0.3
Subtotal | -- | -- | -- | -- | -- | -- | 369.4
Annual Funding TY$, Procurement, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | 9.8 | -- | -- | 9.8 | -- | 9.8
2007 | 2 | 47.5 | -- | 6.9 | 54.4 | 27.7 | 82.1
2008 | 6 | 123.6 | -- | 35 | 158.6 | 30.9 | 189.5
2009 | 7 | 127 | -- | 63.9 | 190.9 | 33.3 | 224.2
2010 | 10 | 176.7 | -- | 72.6 | 249.3 | 59.1 | 308.4
2011 | 22 | 353.2 | -- | 91.6 | 444.8 | 136.6 | 581.4
2012 | 18 | 275.3 | -- | 65.7 | 341 | 123 | 464
2013 | 19 | 262.5 | -- | 11.9 | 274.4 | 89.6 | 364
2014 | 19 | 282.1 | -- | 31.2 | 313.3 | 47.5 | 360.8
2015 | 26 | 359.9 | -- | 17.4 | 377.3 | 116.2 | 493.5
2016 | 44 | 600.9 | -- | 25.2 | 626.1 | 136.6 | 762.7
2017 | 48 | 640.6 | -- | 47.3 | 687.9 | 140.7 | 828.6
2018 | 60 | 772.4 | -- | 39.5 | 811.9 | 169.2 | 981.1
2019 | 60 | 775.3 | -- | 38.1 | 813.4 | 190.2 | 1003.6
2020 | 60 | 814.3 | -- | 32.5 | 846.8 | 175.6 | 1022.4
2021 | 80 | 1046.6 | -- | 41.8 | 1088.4 | 244.2 | 1332.6
2022 | 80 | 1075.9 | -- | 42.1 | 1118 | 215.5 | 1333.5
2023 | 80 | 1114.8 | -- | 43.8 | 1158.6 | 267.4 | 1426
2024 | 80 | 1143.7 | -- | 43.7 | 1187.4 | 247.9 | 1435.3
2025 | 80 | 1175.5 | -- | 44.1 | 1219.6 | 214.9 | 1434.5
2026 | 80 | 1213.3 | -- | 45.8 | 1259.1 | 264.5 | 1523.6
2027 | 80 | 1242.1 | -- | 45.5 | 1287.6 | 275.4 | 1563
2028 | 80 | 1272.8 | -- | 45.7 | 1318.5 | 216.3 | 1534.8
2029 | 80 | 1304.8 | -- | 48.3 | 1353.1 | 262.1 | 1615.2
2030 | 80 | 1339.5 | -- | 48.7 | 1388.2 | 280.8 | 1669
2031 | 80 | 1388.8 | -- | 50.9 | 1439.7 | 294.6 | 1734.3
2032 | 80 | 1431.3 | -- | 49.6 | 1480.9 | 202.7 | 1683.6
2033 | 80 | 1482.5 | -- | 50.9 | 1533.4 | 197.6 | 1731
2034 | 80 | 1548 | -- | 51.7 | 1599.7 | 174.6 | 1774.3
2035 | 80 | 1590.9 | -- | 52.8 | 1643.7 | 178.8 | 1822.5
2036 | 80 | 1635.1 | -- | 51.7 | 1686.8 | 154.7 | 1841.5
2037 | 80 | 1494.4 | -- | 51.2 | 1545.6 | 161.6 | 1707.2
2038 | 2 | 49.5 | -- | 2.7 | 52.2 | 20.7 | 72.9
Subtotal | 1763 | 28170.6 | -- | 1389.8 | 29560.4 | 5350.5 | 34910.9
Annual Funding BY$, Procurement, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
2006 | -- | 10.6 | -- | -- | 10.6 | -- | 10.6
2007 | 2 | 50.2 | -- | 7.3 | 57.5 | 29.2 | 86.7
2008 | 6 | 128.6 | -- | 36.4 | 165 | 32.2 | 197.2
2009 | 7 | 130.3 | -- | 65.6 | 195.9 | 34.2 | 230.1
2010 | 10 | 177.6 | -- | 72.9 | 250.5 | 59.4 | 309.9
2011 | 22 | 347.6 | -- | 90.1 | 437.7 | 134.4 | 572.1
2012 | 18 | 266.7 | -- | 63.6 | 330.3 | 119.2 | 449.5
2013 | 19 | 250.1 | -- | 11.3 | 261.4 | 85.4 | 346.8
2014 | 19 | 264 | -- | 29.2 | 293.2 | 44.4 | 337.6
2015 | 26 | 330.4 | -- | 16 | 346.4 | 106.7 | 453.1
2016 | 44 | 541 | -- | 22.7 | 563.7 | 122.9 | 686.6
2017 | 48 | 565.4 | -- | 41.7 | 607.1 | 124.2 | 731.3
2018 | 60 | 668.4 | -- | 34.2 | 702.6 | 146.4 | 849
2019 | 60 | 657.7 | -- | 32.3 | 690 | 161.4 | 851.4
2020 | 60 | 677.3 | -- | 27 | 704.3 | 146.1 | 850.4
2021 | 80 | 853.4 | -- | 34.1 | 887.5 | 199.1 | 1086.6
2022 | 80 | 860.1 | -- | 33.7 | 893.8 | 172.2 | 1066
2023 | 80 | 873.7 | -- | 34.3 | 908 | 209.6 | 1117.6
2024 | 80 | 878.8 | -- | 33.6 | 912.4 | 190.5 | 1102.9
2025 | 80 | 885.5 | -- | 33.2 | 918.7 | 161.9 | 1080.6
2026 | 80 | 896.1 | -- | 33.8 | 929.9 | 195.3 | 1125.2
2027 | 80 | 899.4 | -- | 32.9 | 932.3 | 199.4 | 1131.7
2028 | 80 | 903.5 | -- | 32.4 | 935.9 | 153.6 | 1089.5
2029 | 80 | 908.1 | -- | 33.6 | 941.7 | 182.4 | 1124.1
2030 | 80 | 913.9 | -- | 33.2 | 947.1 | 191.7 | 1138.8
2031 | 80 | 929 | -- | 34 | 963 | 197.1 | 1160.1
2032 | 80 | 938.7 | -- | 32.5 | 971.2 | 132.9 | 1104.1
2033 | 80 | 953.2 | -- | 32.7 | 985.9 | 127 | 1112.9
2034 | 80 | 975.8 | -- | 32.6 | 1008.4 | 110 | 1118.4
2035 | 80 | 983.1 | -- | 32.6 | 1015.7 | 110.6 | 1126.3
2036 | 80 | 990.6 | -- | 31.3 | 1021.9 | 93.8 | 1115.7
2037 | 80 | 887.7 | -- | 30.4 | 918.1 | 96 | 1014.1
2038 | 2 | 28.8 | -- | 1.6 | 30.4 | 12.1 | 42.5
Subtotal | 1763 | 20625.3 | -- | 1112.8 | 21738.1 | 4081.3 | 25819.4
Cost Quantity Information, Procurement, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2012 $M
2006 | -- | --
2007 | 2 | 50.2
2008 | 6 | 128.6
2009 | 7 | 130.3
2010 | 10 | 177.2
2011 | 22 | 347.6
2012 | 18 | 266.7
2013 | 19 | 250.1
2014 | 19 | 264
2015 | 26 | 330.4
2016 | 44 | 541
2017 | 48 | 565.4
2018 | 60 | 668.4
2019 | 60 | 657.7
2020 | 60 | 677.3
2021 | 80 | 853.4
2022 | 80 | 860.1
2023 | 80 | 873.7
2024 | 80 | 878.8
2025 | 80 | 885.5
2026 | 80 | 896.1
2027 | 80 | 899.4
2028 | 80 | 903.5
2029 | 80 | 908.1
2030 | 80 | 913.9
2031 | 80 | 929
2032 | 80 | 938.7
2033 | 80 | 953.2
2034 | 80 | 975.8
2035 | 80 | 983.1
2036 | 80 | 994.1
2037 | 80 | 891.2
2038 | 2 | 32.8
Subtotal | 1763 | 20625.3
Annual Funding TY$, Procurement, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2007 | -- | 27.4 | -- | -- | 27.4 | -- | 27.4
2008 | 6 | 246.1 | -- | 1.3 | 247.4 | 1.2 | 248.6
2009 | 7 | 298 | -- | 54.3 | 352.3 | 65.6 | 417.9
2010 | 20 | 599 | -- | 118.4 | 717.4 | 127.6 | 845
2011 | 10 | 400.5 | -- | 112.6 | 513.1 | 122.3 | 635.4
2012 | 13 | 191.4 | -- | 57.7 | 249.1 | 62 | 311.1
2013 | 10 | 236.9 | -- | 26.6 | 263.5 | 169.8 | 433.3
2014 | 10 | 227.1 | -- | 21.6 | 248.7 | 142.4 | 391.1
2015 | 8 | 225.5 | -- | 32.2 | 257.7 | 73.5 | 331.2
2016 | 11 | 342 | -- | 20.3 | 362.3 | 100.5 | 462.8
2017 | 20 | 545.5 | -- | 31.5 | 577 | 112.4 | 689.4
2018 | 30 | 752.3 | -- | 28.1 | 780.4 | 134.4 | 914.8
2019 | 36 | 850.9 | -- | 127.6 | 978.5 | 139.8 | 1118.3
2020 | 40 | 891.8 | -- | 80.8 | 972.6 | 215 | 1187.6
2021 | 40 | 895.9 | -- | 72.2 | 968.1 | 257.5 | 1225.6
2022 | 40 | 917.5 | -- | 74.3 | 991.8 | 186.9 | 1178.7
2023 | 40 | 932.8 | -- | 73.5 | 1006.3 | 212.6 | 1218.9
2024 | 40 | 960.9 | -- | 87.1 | 1048 | 200.7 | 1248.7
2025 | 40 | 982.5 | -- | 82.8 | 1065.3 | 203.7 | 1269
2026 | 40 | 1010.8 | -- | 86.6 | 1097.4 | 174.4 | 1271.8
2027 | 40 | 1032 | -- | 66.9 | 1098.9 | 108.2 | 1207.1
2028 | 40 | 1055.2 | -- | 63 | 1118.2 | 102.5 | 1220.7
2029 | 40 | 1079.5 | -- | 63.7 | 1143.2 | 97.1 | 1240.3
2030 | 40 | 1019.3 | -- | 56.7 | 1076 | 96.8 | 1172.8
2031 | 21 | 389.3 | -- | 41.7 | 431 | 57.6 | 488.6
2032 | 20 | 358.9 | -- | 43.7 | 402.6 | 46 | 448.6
2033 | 18 | 295.5 | -- | 42 | 337.5 | 42.4 | 379.9
Subtotal | 680 | 16764.5 | -- | 1567.2 | 18331.7 | 3252.9 | 21584.6
Annual Funding BY$, Procurement, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2012 $M | Non End Item Recurring Flyaway BY 2012 $M | Non Recurring Flyaway BY 2012 $M | Total Flyaway BY 2012 $M | Total Support BY 2012 $M | Total Program BY 2012 $M
2007 | -- | 28.9 | -- | -- | 28.9 | -- | 28.9
2008 | 6 | 256.1 | -- | 1.4 | 257.5 | 1.2 | 258.7
2009 | 7 | 305.8 | -- | 55.7 | 361.5 | 67.3 | 428.8
2010 | 20 | 601.9 | -- | 119 | 720.9 | 128.2 | 849.1
2011 | 10 | 394.1 | -- | 110.8 | 504.9 | 120.3 | 625.2
2012 | 13 | 185.4 | -- | 56 | 241.4 | 60 | 301.4
2013 | 10 | 225.7 | -- | 25.3 | 251 | 161.8 | 412.8
2014 | 10 | 212.5 | -- | 20.2 | 232.7 | 133.3 | 366
2015 | 8 | 207 | -- | 29.6 | 236.6 | 67.5 | 304.1
2016 | 11 | 307.9 | -- | 18.3 | 326.2 | 90.5 | 416.7
2017 | 20 | 481.5 | -- | 27.8 | 509.3 | 99.2 | 608.5
2018 | 30 | 651 | -- | 24.3 | 675.3 | 116.3 | 791.6
2019 | 36 | 721.9 | -- | 108.2 | 830.1 | 118.6 | 948.7
2020 | 40 | 741.7 | -- | 67.2 | 808.9 | 178.9 | 987.8
2021 | 40 | 730.5 | -- | 58.9 | 789.4 | 210 | 999.4
2022 | 40 | 733.5 | -- | 59.4 | 792.9 | 149.4 | 942.3
2023 | 40 | 731.1 | -- | 57.6 | 788.7 | 166.6 | 955.3
2024 | 40 | 738.3 | -- | 66.9 | 805.2 | 154.3 | 959.5
2025 | 40 | 740.1 | -- | 62.4 | 802.5 | 153.5 | 956
2026 | 40 | 746.5 | -- | 64 | 810.5 | 128.8 | 939.3
2027 | 40 | 747.2 | -- | 48.4 | 795.6 | 78.4 | 874
2028 | 40 | 749.1 | -- | 44.7 | 793.8 | 72.7 | 866.5
2029 | 40 | 751.3 | -- | 44.3 | 795.6 | 67.6 | 863.2
2030 | 40 | 695.5 | -- | 38.7 | 734.2 | 66 | 800.2
2031 | 21 | 260.4 | -- | 27.9 | 288.3 | 38.5 | 326.8
2032 | 20 | 235.4 | -- | 28.6 | 264 | 30.2 | 294.2
2033 | 18 | 190 | -- | 27 | 217 | 27.3 | 244.3
Subtotal | 680 | 13370.3 | -- | 1292.6 | 14662.9 | 2686.4 | 17349.3
Cost Quantity Information, Procurement, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2012 $M
2007 | -- | --
2008 | 6 | 256.1
2009 | 7 | 305.8
2010 | 20 | 601.9
2011 | 10 | 394.1
2012 | 13 | 185.4
2013 | 10 | 225.7
2014 | 10 | 212.5
2015 | 8 | 207
2016 | 11 | 307.9
2017 | 20 | 481.5
2018 | 30 | 651
2019 | 36 | 721.9
2020 | 40 | 741.7
2021 | 40 | 730.5
2022 | 40 | 733.5
2023 | 40 | 731.1
2024 | 40 | 738.3
2025 | 40 | 740.1
2026 | 40 | 746.5
2027 | 40 | 747.2
2028 | 40 | 749.1
2029 | 40 | 751.3
2030 | 40 | 695.5
2031 | 21 | 270
2032 | 20 | 245
2033 | 18 | 199.7
Subtotal | 680 | 13370.3

## Low Rate Initial Production
Low Rate Initial Production, F-35 Aircraft
| Initial LRIP Decision | Current Total LRIP
Approval Date | 2001-10-26 | 2010-02-24
Approved Quantity | 465 | 336
Reference | ADM | ADM
Start Year | 2006 | 2006
End Year | 2015 | 2018
Low Rate Initial Production, F-35 Engine
| Initial LRIP Decision | Current Total LRIP
Approval Date | 2001-10-26 | 2010-02-24
Approved Quantity | 465 | 336
Reference | ADM | ADM
Start Year | 2006 | 2006
End Year | 2015 | 2018

## Foreign Military Sales
Foreign Military Sales, F-35 Aircraft
Country | Date of Sale | Quantity | Total Cost $M | Memo
Japan | 2013-09-02 | 6 | 1300
Israel (IS) | 2010-10-07 | 19 | 2750

## Unit Cost
Unit Cost - F-35 Aircraft
Unit Cost Report | BY 2012 $M | BY 2012 $M
Unit Cost | Current UCR Baseline (MAR 2012 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 276482.2 | 267060.6
Quantity | 2458 | 2457
Unit Cost | 112.483 | 108.694 | -3.37
Average Procurement Unit Cost (APUC)
Cost | 224333.7 | 217450
Quantity | 2443 | 2443
Unit Cost | 91.827 | 89.009 | -3.07
| BY 2012 $M | BY 2012 $M
Unit Cost | Revised Original UCR Baseline (MAR 2012 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 276482.2 | 267060.6
Quantity | 2458 | 2457
Unit Cost | 112.483 | 108.694 | -3.37
Average Procurement Unit Cost (APUC)
Cost | 224333.7 | 217450
Quantity | 2443 | 2443
Unit Cost | 91.827 | 89.009 | -3.07
Unit Cost History, F-35 Aircraft
|  | BY 2012 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2001-10-01 | 74.567 | 60.632 | 81.298 | 68.934
APB as of JAN 2006 | 2004-03-01 | 94.837 | 73.845 | 100.407 | 81.826
Revised Original APB | 2012-03-01 | 112.529 | 91.827 | 135.065 | 115.697
Prior APB | 2007-03-01 | 104.363 | 83.467 | 113.318 | 94.857
Current APB | 2012-03-01 | 112.529 | 91.827 | 135.065 | 115.697
Prior Annual SAR | 2012-12-01 | 108.235 | 88.244 | 133.054 | 114.184
Current Estimate | 2013-12-01 | 108.694 | 89.009 | 134.296 | 115.747
SAR Unit Cost History | Changes | [7 empty] | PAUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial PAUC Dev Est
135.065 | 2.643 | 0 | 1.028 | 0 | -3.427 | 0 | -1.013 | -0.769 | 134.296
| Changes Econ: Changes | APUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial APUC Dev Est
115.697 | 2.58 | 0 | 1.034 | 0 | -2.545 | 0 | -1.019 | 0.05 | 115.747
SAR Baseline History | bar: Changes Econ to Changes Eng
Item/Event | Changes Econ: SAR Planning Estimate (PE); Changes Qty: SAR Development Estimate (DE); Changes Sch: SAR Production Estimate (PdE); Changes Eng: Current Estimate
Milestone I | Changes Econ: N/A; Changes Qty: 1996-11-01; Changes Sch: N/A; Changes Eng: 1996-11-01
Milestone B | Changes Econ: 2001-03-01; Changes Qty: 2011-11-01; Changes Sch: N/A; Changes Eng: 2012-03-01
Milestone C | Changes Econ: TBD; Changes Qty: 2019-04-01; Changes Sch: N/A; Changes Eng: 2019-04-01
IOC | Changes Econ: TBD; Changes Qty: TBD; Changes Sch: N/A; Changes Eng: 2015-07-01
Total Cost (TY $M) | Changes Econ: 24800; Changes Qty: 331855.2; Changes Sch: N/A; Changes Eng: 329964.1
Total Quantity | Changes Econ: N/A; Changes Qty: 2457; Changes Sch: N/A; Changes Eng: 2457
Prog. Acq. Unit Cost (PAUC) | Changes Econ: N/A; Changes Qty: 135.065; Changes Sch: N/A; Changes Eng: 134.296
Unit Cost - F-35 Engine
Unit Cost Report | Changes Econ: BY 2012 $M; Changes Qty: BY 2012 $M
Unit Cost | Changes Econ: Current UCR Baseline (MAR 2012 APB); Changes Qty: Current Estimate (DEC 2013 SAR); Changes Sch: BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | Changes Econ: 53916.4; Changes Qty: 56432.9
Quantity | Changes Econ: 2458; Changes Qty: 2457
Unit Cost | Changes Econ: 21.935; Changes Qty: 22.968; Changes Sch: +4.71
Average Procurement Unit Cost (APUC)
Cost | Changes Econ: 42332.9; Changes Qty: 43168.7
Quantity | Changes Econ: 2443; Changes Qty: 2443
Unit Cost | Changes Econ: 17.328; Changes Qty: 17.67; Changes Sch: +1.97
| BY 2012 $M | BY 2012 $M
Unit Cost | Changes Econ: Revised Original UCR Baseline (MAR 2012 APB); Changes Qty: Current Estimate (DEC 2013 SAR); Changes Sch: BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | Changes Econ: 53916.4; Changes Qty: 56432.9
Quantity | Changes Econ: 2458; Changes Qty: 2457
Unit Cost | Changes Econ: 21.935; Changes Qty: 22.968; Changes Sch: +4.71
Average Procurement Unit Cost (APUC)
Cost | Changes Econ: 42332.9; Changes Qty: 43168.7
Quantity | Changes Econ: 2443; Changes Qty: 2443
Unit Cost | Changes Econ: 17.328; Changes Qty: 17.67; Changes Sch: +1.97
Unit Cost History, F-35 Aircraft
|  | BY 2012 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2012-03-01 | 21.989 | 17.328 | 25.99 | 21.708
APB as of JAN 2006 | N/A | N/A | N/A | N/A | N/A
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | N/A | N/A | N/A | N/A | N/A
Current APB | 2012-03-01 | 21.989 | 17.328 | 25.99 | 21.708
Prior Annual SAR | 2012-12-01 | 21.771 | 16.599 | 26.17 | 21.48
Current Estimate | 2013-12-01 | 22.968 | 17.67 | 27.929 | 23.125
SAR Unit Cost History | Changes Econ: Changes | PAUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial PAUC Dev Est
25.99 | 0.492 | 0 | 0.19 | 0 | 1.337 | 0 | -0.08 | 1.939 | 27.929
| Changes Econ: Changes | APUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial APUC Dev Est
21.708 | 0.483 | 0 | 0.191 | 0 | 0.824 | 0 | -0.081 | 1.417 | 23.125
SAR Baseline History | bar: Changes Econ to Changes Eng
Item/Event | Changes Econ: SAR Planning Estimate (PE); Changes Qty: SAR Development Estimate (DE); Changes Sch: SAR Production Estimate (PdE); Changes Eng: Current Estimate
Milestone I | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
Milestone B | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
Milestone C | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
IOC | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
Total Cost (TY $M) | Changes Econ: N/A; Changes Qty: 63856.6; Changes Sch: N/A; Changes Eng: 68620.5
Total Quantity | Changes Econ: N/A; Changes Qty: 2457; Changes Sch: N/A; Changes Eng: 2457
Prog. Acq. Unit Cost (PAUC) | Changes Econ: N/A; Changes Qty: 25.99; Changes Sch: N/A; Changes Eng: 27.929

## Cost Variance
Cost Variance - F-35 Aircraft
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 44410.1 | 282647.8 | 4797.3 | 331855.2
Previous Changes
Economic | 172.3 | 6729.8 | 114.3 | 7016.4
Quantity | -- | -- | -- | --
Schedule | -- | 1486.6 | -- | 1486.6
Engineering | -- | -- | -- | --
Estimating | -1221.7 | -10131.1 | -311.4 | -11664.2
Other | -- | -- | -- | --
Support | -- | -1781.2 | -- | -1781.2
Subtotal | -1049.4 | -3695.9 | -197.1 | -4942.4
Current Changes
Economic | -82.3 | -426 | -14.4 | -522.7
Quantity | -- | -- | -- | --
Schedule | -- | 1039.1 | -- | 1039.1
Engineering | -- | -- | -- | --
Estimating | -505.8 | 3912.5 | -164.8 | 3241.9
Other | -- | -- | -- | --
Support | -- | -707 | -- | -707
Subtotal | -588.1 | 3818.6 | -179.2 | 3051.3
Adjustments | -- | -- | -- | --
Total Changes | -1637.5 | 122.7 | -376.3 | -1891.1
CE - Cost Variance | -1637.5 | 122.7 | -376.3 | -1891.1
CE - Cost & Funding | 42772.6 | 282770.5 | 4421 | 329964.1
Summary Base Year 2012 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 47982.1 | 224332.9 | 4168 | 276483
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -1524.6 | -7016.7 | -270.2 | -8811.5
Other | -- | -- | -- | --
Support | -- | -1737.2 | -- | -1737.2
Subtotal | -1524.6 | -8753.9 | -270.2 | -10548.7
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -548.8 | 2590.1 | -195.9 | 1845.4
Other | -- | -- | -- | --
Support | -- | -719.1 | -- | -719.1
Subtotal | -548.8 | 1871 | -195.9 | 1126.3
Adjustments | -- | -- | -- | --
Total Changes | -2073.4 | -6882.9 | -466.1 | -9422.4
CE - Cost Variance | 45908.7 | 217450 | 3701.9 | 267060.6
CE - Cost & Funding | 45908.7 | 217450 | 3701.9 | 267060.6
Cost Variance - F-35 Engine
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 10823.7 | 53032.9 | -- | 63856.6
Previous Changes
Economic | 4204 | 1258.9 | -- | 1301.3
Quantity | -- | -- | -- | --
Schedule | -- | 271.3 | -- | 271.3
Engineering | -- | -- | -- | --
Estimating | 956.1 | 1593.4 | -- | 637.3
Other | -- | -- | -- | --
Support | -- | -493.2 | -- | -493.2
Subtotal | -- | -493.2 | -- | -493.2
Current Changes
Economic | -11.7 | -79.8 | -- | -91.5
Quantity | -- | -- | -- | --
Schedule | -- | 196.1 | -- | 196.1
Engineering | -- | -- | -- | --
Estimating | 314.5 | 3606.9 | -- | 3921.4
Other | -- | -- | -- | --
Support | -- | 295.8 | -- | 295.8
Subtotal | 302.8 | 4019 | -- | 4321.8
Total Changes | 1301.3 | 3462.6 | -- | 4763.9
CE - Cost Variance | 12125 | 56495.5 | -- | 68620.5
CE - Cost & Funding | 12125 | 56495.5 | -- | 68620.5
Summary Base Year 2012 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 11695.2 | 42332.9 | -- | 54028.1
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 1245.4 | -1446.4 | -- | -201
Other | -- | -- | -- | --
Support | -- | -335.4 | -- | -335.4
Subtotal | 1245.4 | -1781.8 | -- | -536.4
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 323.6 | 2517.8 | -- | 2841.4
Other | -- | -- | -- | --
Support | -- | 99.8 | -- | 99.8
Subtotal | 323.6 | 2617.6 | -- | 2941.2
Total Changes | 1569 | 835.8 | -- | 2404.8
CE - Cost Variance | 13264.2 | 43168.7 | -- | 56432.9
CE - Cost & Funding | 13264.2 | 43168.7 | -- | 56433.9

## Contracts
Contract Name: JSF Air System SDD
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
18981.9 | N/A | 14 | 20029.8 | N/A | 14 | 34139 | 33631.6
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -433.6 | -245.5
Previous Cumulative Variances | -392.6 | -221
Net Change | -41 | -24.5
Contract Name: Propulsion JSF F135 SDD
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
4827.8 | N/A | 33 | 6610.1 | N/A | 33 | 8211.8 | 8234
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | 19.5 | -40.1
Previous Cumulative Variances | -20 | -26.8
Net Change | 39.5 | -13.3
Contract Name: JSF Air System LRIP 4
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1133.9 | 1229.9 | 37 | 1156.3 | 1231.6 | 37 | 1161.4 | 1171.4
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | 41.6 | -4.6
Previous Cumulative Variances | -40 | -56.4
Net Change | -1.6 | 51.8
Contract Name: JSF Air System LRIP 5
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
3949.6 | N/A | 32 | 4772.8 | N/A | 32 | 5027.4 | 0
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -130.5 | -185.9
Previous Cumulative Variances | -62.1 | -339.1
Net Change | -68.4 | 153.2
Contract Name: JSF Propulsion F135 LRIP 5
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1122.3 | 1122.3 | 36 | 1016.4 | 1026.4 | 36 | 1008.5 | 1016.4
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -26.7 | -19.4
Previous Cumulative Variances | -- | --
Net Change | -26.7 | -19.4

## Deliveries and Expenditures
F-35 Aircraft
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 14 | 14 | 14 | 100%
Production | 82 | 71 | 2443 | 2.91%
Total Program Quantities Delivered | 96 | 85 | 2457 | 3.46%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 329964.1 | Years Appropriated | 21
Expenditures to Date | 55985.7 | Percent Years Appropriated | 46.67%
Precent Expended | 16.97% | Appropriated to Date | 73383.2
Total Funding Years | 45 | Percent Appropriated | 22.24%
F-35 Engine
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 14 | 14 | 14 | 100%
Production | 82 | 71 | 2443 | 2.91%
Total Program Quantities Delivered | 96 | 85 | 2457 | 3.46%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 68620.5 | Years Appropriated | 21
Expenditures to Date | 14896.4 | Percent Years Appropriated | 46.67%
Precent Expended | 21.71% | Appropriated to Date | 17502.7
Total Funding Years | 45 | Percent Appropriated | 25.51%

## Operating and Support Cost
F-35 Aircraft
Unitized O&S Costs BY 2012 $K
Cost Element | F-35 Aircraft Cost per Flying Hour ($) | F-16C/D Cost per Flying Hour ($)
Unit-Level Manpower | 8.792 | 10.042
Unit Operations | 7.275 | 5.632
Maintenance | 10.019 | 5.501
Sustaining Support | 3.132 | 2.075
Continuing System Improvements | 3.336 | 2.291
Indirect Support | 0 | 0
Other | 0 | 0
Total Unitized Cost (Base Year 2002 $) | 32.554 | 25.541
| Current Development APB Objective/Threshold |  | Current Estimate
Total O&S Costs $M | F-35 Aircraft |  | F-35 Aircraft | F-16C/D
Base Year | 617000 | 678700 | 597773.6 | N/A
Then Year | 1113272.6 | N/A | 1016516 | N/A