## 2015
Cost of Assessment Phase
Project/Increment Name | Approved Cost (£m) | Actual /Forecast Cost | Variation (£m)
A400M | 2 | 1 | -1
Training Service | 1 | 1 | 0
In Service Support | 1 | 1 | 0
Total (£m) | 4 | 3 | -1
Cost Boundaries for Demonstration and Manufacture Phase / PFI
Project/Increment Name | Lowest Approved (£m) | Budgeted For (£m) | Highest Approved (£m)
A400M | - | 2238 | 2339
Cost of the Demonstration and Manufacture Phase
Project/Increment Name | Budgeted for Cost (£m) | Forecast cost (£m) | Variation (£m) | In-Year Variation (£m)
A400M | 2238 | 2710 | 472 | -42
Cost Variation against approved Cost of the Demonstration & Manufacture Phase
Date | Variation (£m) | Category | Reason for Variation
2015-03-01 | -35 | Exchange Rate | An in year gain due to an increase in the value of £ vs € as a result of the difference between the set planning exchange rate and the actual outturn.
2015-03-01 | -3 | Budgetary Factors | A reduction to in year provision due to a deferral of a decision on requirements linked to future capability milestones. Financial liability for any subsequent requirement is owned by HQ Air.
2015-02-01 | -4 | Procurement Processes | A reduction as a result of the actual contract cost of equipment being less than forecast.
Historic | -4 | Inflation | A reduction to the future provision for variation of price due to the delivery of two aircraft earlier than previously scheduled.
Historic | -51 | Exchange Rate | A reduction due to changes in the MoD central planning assumption on the £ : € exchange rate.
Historic | -10 | Technical Factors | An increase due to an increased requirement for UK specific trials and evaluation work in support of aircraft entry into service
Historic | 575 | Procurement Processes | UK contribution to the multinational Export Levy Facility provided to EADS by A400M partner nations. Reduction in umber of aircraft to be equipped with Defenseive Aids Sub-System from 25 to 9. Increased costs due to contract slippage.
Historic | *** | Changed Capability Requirements | A Planning Round 2011 Option to swap an early delivery aircraft with one due to be delivered later to ensure that the whole fleet has the same specification.
Historic | *** | Procurement Processes - International Collaboration | A Planning Round 2011 Option to reprofile payments to align them with the revised delivery schedule agreed in the six nation international collaborative contract (***) and associated risk (***).
Historic | *** | Procurement Processes - International Collaboration | A change due to a realignment of payments with the revised programme schedule agreed in the six nation international collaborative contract.
Historic | *** | Exchange Rate | Foreign Exchange increases due to changes in plannings assumptions
Historic | *** | Inflation | An increase due to changes in inflation assumptions in the 22011 Planning Round.
Historic | *** | Accounting Adjustments and Redefinitions | Removal of Indirect RDEL (Foreign Exchagnge) in accordance with a change in Departmental Policy
Historic | *** | Accounting Adjustments and Redefinitions | Removal of Cost of Captial due to Clear line of Sight poicy implemeneted by HM Treasury
Historic | *** | Exchange Rate | An In Year gain due to the increase in the value of £ vs € due to the difference between the set planning exchange rate and actual outturn.
Historic | *** | Procurement Processes - International Collaboration | A change due to programme rebalancing as a result of work undertaken in support of concluding an amended contract.
Historic | *** | Exchange Rate | Loss due to the difference between the set planning exchange rate and forecast outturn.
Historic | *** | Procurement Process | Revised cost for Mission Planning System due to change from acquisition only to also include support.
Historic | *** | Exchange Rate | A loss in 2008/2009 due to the fall in value £ vs €
Historic | *** | Changed Capability Requirements | Portable Removable On-Board Inert Gas Generation System fuel tank inerting system
Historic | *** | Inflation | An increase based on latest delivery schedule
Historic | *** | Exchange Rate | An in crase in 2008/2009
Historic | *** | Technical Factors | Inclusion of additional airworthiness support to cover aircraft release to service
Historic | *** | Exchange Rate | Variation in 2008/2009
Historic | *** | Inflation | An increase in 2008/2009
Historic | -77 | Budgetary Factors | Departmental Reviews have identified savings to programme risks (-£20m). Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of Organisation Conjointe de Coopération en matière d'ARmement (OCCAR) Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Realism reprofile of Development Production Phase contract together with Directed Infra-Red Counter Measures and Cargo Hold Mock-up costs (-£3m)
Historic | *329 | Changed Capability Requirements | Fuel Tank Inertion System Pipe work (+£6m). Deletion of Centralised Crypto Management Unit requirement (-£12m). Deletion of Civil Pallets Configuration Item (-£5m). Addition of Propeller Brake (+£6m). Programme measure to move deferred configuration Items back into aircraft delivery profile (-£2m). Reduction in number of aircraft to be equipped with Defensive Aids Sub- System from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months. (-£81m). Delay of programme by 9 months (-£12m), Option bringing the Defensive Aids Sub-System forward onto aircraft 1-9 (+£9m).
In Service Support
Date | Variation (£m) | Category | Reason for Variation
2015-03-01 | -6 | Technical Factors | A reduction due to the non-materialisation of risk
2015-03-01 | -11 | Exchange Rate | An in year gain due to the increase in the value of the £ vs € due to the difference between the forecast exchange rate and actual outturn.
2015-03-01 | -1 | Technical Factors | A reduction in the final contract cost as a result of a gainshare clause
2014-12-01 | -2 | Technical Factors | A reduction in the forecast cost of in service support as a result of late aircraft deliveries
2014-10-01 | 5 | Technical Factors | The provision of interim maintenance infrastrucutre prior to the construction of the new A400M hangar
2014-09-01 | -35 | Procurement Processes | A reduction in the final value of the contract as a result of negotations.
Net Variation (£m) | -50
Expenditure to date
Description | Previous expenditure to 31 March 2014 (£m) | In-year expenditure (£m) | Total expenditure to 31 March 2015 (£m)
Assessment Phase | 1 | 0 | 1
Demonstration & Manufacture Phase | 1230 | 519 | 1750
Support Phase (Training) | 147 | 29 | 176
Support Phase (In Service Support) | 52 | 158 | 210
Total Expenditure | 1430 | 706 | 2136

## 2014
Cost of the Assessment Phase
Project/Increment Name | Approved Cost (£m) | Actual /Forecast Cost | Variation (£m)
A400M | 2 | 1 | -1
Training Service | 1 | 1 | 0
Total (£m) | 3 | 2 | -1
Cost Boundaries for Demonstration and Manufacture Phase / PFI
Project/Increment Name | Lowest Approved (£m) | Budgeted For (£m) | Highest Approved (£m)
A400M | - | 2238 | 2339
Cost of the Demonstration and Manufacture Phase
Project/Increment Name | Budgeted for Cost (£m) | Forecast cost (£m) | Variation (£m) | In-Year Variation (£m)
A400M | 2238 | 2752 | 514 | -57
Cost Variation against approved Cost of the Demonstration & Manufacture Phase
Date | Variation (£m) | Category | Reason for Variation
41548 | -14 | Inflation | A reduction to the future provision for variation of price due to the delivery of two aircraft ealier than previously scheduled
2013-07-01 | -43 | Exchange Rate | A reduction due to changes in the MoD central planing assumption on £ : € exchange rate
Historic | -2 | Procurement Process | A reduction in the cost of the design and development work required to enable UK A400M aircraft to operate the defensive aids systems
Historic | -8 | Technical Factors | A reduction in the forecast cost of the fuel tank inerting system
Historic | 2 | Technical Factors | An increase due to the refinement of mission planning system requirement
Historic | 3 | Technical Factors | An incease due to the need to ensure future interoperability of cryptographic components
Historic | 30 | Technical Factors | An increase due to an increased requirement for UK specific trials and evaluation work in support of aircraft entry into service
Historic | -8 | Procurement Process | A reductio ndue to re-pricing
Historic | -10 | Technical Factors | Reduced Defensive Aids hardward device procurement following the drawdown of other aircraft platforms in the 2010 Strategic Defence and Security Review
Historic | -5 | Technical Factors | Changes to Integration contingency
Historic | 1 | Technical Factors | Increased cost of OCCAR management agency
Historic | 3 | Technical Factors | Increased cost of integrating equipment to the A400M Platform. (+£3M) DASS (-£3M) Mission Planning System, Technical Support (+£3M)
Historic | 175 | Procurement Process - International Collaboration | UK contribution to the multinational Export Levy Facility provided to EADS by A400M partner nations
Historic | *** | Changed Capability Requirements | A Planning Round 2011 Option to swap an early delivery aircraft with oen due to be delivered
Historic | *** | Procurement Process - International Collaboration | A Planning Round 2011 Option to reprofile payments to align them with the revised delivery schedule agreed in the six nationa international collaborative contract (***) and associated risk (***)
Historic | *** | Procurement Process - International Collaboration | A change due to a realignment of payments with the revised programme schedule agreed in the six nationa international collaborative contract
Historic | *** | Exchange Rate | Foreign Exchange increase due to changes in planning assumptions
Historic | *** | Inflation | An increase due to chagnes in inflation assumption in the 2011 Planning Round
Historic | *** | Accounting Adjustments and Redefinitions | Removal of Indirect RDEL (Foreign Exchange) in accordance with a change in Departmental policy
Historic | *** | Accounting Adjustments and Redefinitions | Removal of Cost of Capital due to Clear line of Sigh policy implemented by HM Treasury
Historic | *** | Exchange Rate | An In Year gain due to the increase in the value of £ vs € due to the difference between the set planning exchange rate and actual outturn
Historic | *** | Procurement Processes - International Collaboration | A change due to the programme reblaancing as a result of work undertaken in support of concluding an amended contract
Historic | *** | Exchange Rate | Loss due to the difference between the set planning exchange rate and the forecast outturn
Historic | *** | Procurement Process | Revised costing for Mission Planning System due to change from acquisition only to also include support
Historic | *** | Exchange Rate | A loss in 2008/2009 due to the fall in the value of £ vs €
Historic | *** | Changed Capability Requirements | Portable Removable On-Board Inert Gas Generation System fuel tank inerting system
Historic | *** | Inflation | An increase based on latest delivery schedule
Historic | *** | Exchange Rate | An increase in 2008/2009
Historic | *** | Technical Factors | Inclusion of additional airworthiness support to cover aircraft release to service.
Historic | *** | Exchange Rate | Variation in 2008/2009
Historic | *** | Inflation | An increase in 2008/2009
Historic | -77 | Budgetary Factors | Departmental Reviews have identified savings to programme risks (-£20m). Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of Organisation Conjointe de Coopération en matière d'ARmement (OCCAR) Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Realism re-profile of Development Production Phase contract together with Directed Infra- Red Counter Measures and Cargo Hold Mock-up costs (-£3m)
Historic | -329 | Changed Capability Requirements | Fuel Tank Inertion System Pipe work (+£6m). Deletion of Centralised Crypto Management Unit requirement (-£12m). Deletion of Civil Pallets Configuration Item (-£5m). Addition of Propeller Brake (+£6m). Programme measure to move deferred configuration Items back into aircraft delivery profile (-£2m). Reduction in number of aircraft to be equipped with Defensive Aids Sub-System from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months. (-£81m). Delay of programme by 9 months (-£12m), Option bringing the Defensive Aids Sub-System forward onto aircraft 1-9 (+£9m).
Historic | 345 | Procurement Processes | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date slipped from November 2001 - October 2002 (+£149m). Contract Effectivity Date slipped from October 2002 - April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£58m). Contract Effectivity Date slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | -8 | Exchange Rate | A decrease in 2005/2006 (-£21m). Variation in 2004/2005 (+£35m). Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£206m). Variation in 2003/04 (+£198m). Exchange rate changes (-£14m)
Historic | 10 | Inflation | An increase in 2005/2006 (+£12m). An increase in 2004/2005 (+£7m). Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£9m).
Historic | 65 | Procurement Processes | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in Unit Production Cost (- £65m). Subsequent contract renegotiation due to German reduction in off take (+£130m).
Historic | 1 | Technical Factors | Programme realism with regard to costing Technical Publications (-£5m); Identification of UK only certification requirements (+£6m).
Historic | -27 | Technical Factors | Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m). Costing re-adjusted with understanding of future programme – Certification (-£15m), Government Furnished Equipment (+£4m), Mission Planning & Restitution System (-£10m)
Expenditure to date
Description | Previous expenditure to 31 March 2013 (£m) | In-year expenditure (£m) | Total expenditure to 31 March 2014 (£m)
Assessment Phase | 1 | 0 | 1
Demonstration & Manufacture Phase | 942 | 288 | 1230
Support Phase / Phase Service /PFI Cost | 76 | 71 | 147
Total Expenditure | 1019 | 360 | 1378

## 2013
Cost of the Assessment Phase
Project/Increment Name | Approved Cost (£m) | Actual /Forecast Cost | Variation (£m) | Approved cost as a proportion of total estimated procurement expenditure (%) | Actual Cost as a proportion of total estaitmed procurement expenditure (%)
A400M | 2 | 1 | -1 | 0 | 0
Training Service | 1 | 1 | 0 | 0 | 0
Total (£m) | 3 | 2 | -1 | 0 | 0
Actual cost boundaries for Demonstration and Manufacture Phase / PFI
Project/Increment Name | Lowest Approved (£m) | Budgeted For (£m) | Highest Approved (£m)
A400M | - | 2238 | 2339
Cost of the Demonstration and Manufacture Phase
Project/Increment Name | Budgeted for Cost (£m) | Forecast cost (£m) | Variation (£m) | In-Year Variation (£m)
A400M | 2238 | 2809 | 571 | 25
Total (£m) | 2238 | 2809 | 571 | 25
Cost variation against approved cost of the Demonstration and Manufacture Phase
Date | Variation (£m) | Category | Reason for Variation
2013-03-01 | -2 | Procurement Processes | A reduction in the cost of the design and development work required to enable UK A400M aircraft to operate the defensive aids system.
2013-03-01 | -8 | Technical Factors | A reduction in the forecast cost of the fuel tank inerting system
2013-01-01 | 2 | Technical Factors | An increase due to the refinement of the mission planning system requirement
2012-06-01 | 3 | Technical Factors | An increase due to the need to ensure future interoperability of cryptographic components.
2012-04-01 | 30 | Technical Factors | An increase due to an increased requirement for UK specific trials and evaluation work in support of aircraft entry into service
Historic | -8 | Procurement Processes | A reduction due to repricing.
Historic | -10 | Technical Factors | Reduced Defensive Aids hardware device procurement following the drawdown of other aircraft platforms in the 2010 Strategic Defence and Security Review
Historic | -5 | Technical Factors | Changes to Inegration contingency
Historic | 1 | Technical Factors | Increased cost of OCCAR management agency
Historic | 3 | Technical Factors | Increased cost of integrating equipment to the A400M Platform. (+£3M) DASS (-£3M) Mission Planning System, Technical Support (+£3M)
Historic | 175 | Procurement Process - International Collaboration | UK contribution to the multinational Export Levy Facility provided to EADS by A400M partner nations
Historic | *** | Changed Capability Requirements | A Planning Round 2011 Option to swap an early delivery aircraft with oen due to be delivered
Historic | *** | Procurement Process - International Collaboration | A Planning Round 2011 Option to reprofile payments to align them with the revised delivery schedule agreed in the six nationa international collaborative contract (***) and associated risk (***)
Historic | *** | Procurement Process - International Collaboration | A change due to a realignment of payments with the revised programme schedule agreed in the six nationa international collaborative contract
Historic | *** | Exchange Rate | Foreign Exchange increase due to changes in planning assumptions
Historic | *** | Inflation | An increase due to chagnes in inflation assumption in the 2011 Planning Round
Historic | *** | Accounting Adjustments and Redefinitions | Removal of Indirect RDEL (Foreign Exchange) in accordance with a change in Departmental policy
Historic | *** | Accounting Adjustments and Redefinitions | Removal of Cost of Capital due to Clear line of Sigh policy implemented by HM Treasury
Historic | *** | Exchange Rate | An In Year gain due to the increase in the value of £ vs € due to the difference between the set planning exchange rate and actual outturn
Historic | *** | Procurement Processes - International Collaboration | A change due to the programme reblaancing as a result of work undertaken in support of concluding an amended contract
Historic | *** | Exchange Rate | Loss due to the difference between the set planning exchange rate and the forecast outturn
Historic | *** | Procurement Process | Revised costing for Mission Planning System due to change from acquisition only to also include support
Historic | *** | Exchange Rate | A loss in 2008/2009 due to the fall in the value of £ vs €
Historic | *** | Changed Capability Requirements | Portable Removable On-Board Inert Gas Generation System fuel tank inerting system
Historic | *** | Inflation | An increase based on latest delivery schedule
Historic | *** | Exchange Rate | An increase in 2008/2009
Historic | *** | Technical Factors | Inclusion of additional airworthiness support to cover aircraft release to service.
Historic | *** | Exchange Rate | Variation in 2008/2009
Historic | *** | Inflation | An increase in 2008/2009
Historic | *** | Budgetary Factors | Departmental Reviews have identified savings to programme risks (-£20m). Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of Organisation Conjointe de Coopération en matière d'ARmement (OCCAR) Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Realism re-profile of Development Production Phase contract together with Directed Infra- Red Counter Measures and Cargo Hold Mock-up costs (-£3m)
Historic | *** | Changed Capability Requirements | Fuel Tank Inertion System Pipe work (+£6m). Deletion of Centralised Crypto Management Unit requirement (-£12m). Deletion of Civil Pallets Configuration Item (-£5m). Addition of Propeller Brake (+£6m). Programme measure to move deferred configuration Items back into aircraft delivery profile (-£2m). Reduction in number of aircraft to be equipped with Defensive Aids Sub-System from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months. (-£81m). Delay of programme by 9 months (-£12m), Option bringing the Defensive Aids Sub-System forward onto aircraft 1-9 (+£9m).
Historic | *** | Procurement Processes | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date slipped from November 2001 - October 2002 (+£149m). Contract Effectivity Date slipped from October 2002 - April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£58m). Contract Effectivity Date slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | *** | Exchange Rate | A decrease in 2005/2006 (-£21m). Variation in 2004/2005 (+£35m). Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£206m). Variation in 2003/04 (+£198m). Exchange rate changes (-£14m)
Historic | *** | Inflation | An increase in 2005/2006 (+£12m). An increase in 2004/2005 (+£7m). Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£9m).
Historic | *** | Procurement Processes | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in Unit Production Cost (- £65m). Subsequent contract renegotiation due to German reduction in off take (+£130m).
Historic | *** | Technical Factors | Programme realism with regard to costing Technical Publications (-£5m); Identification of UK only certification requirements (+£6m).
Historic | *** | Technical Factors | Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m). Costing re-adjusted with understanding of future programme – Certification (-£15m), Government Furnished Equipment (+£4m), Mission Planning & Restitution System (-£10m)
Expenditure to date
Description | Previous expenditure to 31 March 2012 (£m) | In-year expenditure (£m) | Total expenditure to 31 March 2013 (£m)
Assessment Phase | 1 | 0 | 1
Demonstration & Manufacture Phase | 884 | 58 | 942
Support Phase /PFI Cost | 0 | 76 | 76
Total Expenditure | 885 | 134 | 1019

## 2012
Cost of the Assessment Phase
Project/Increment Name | Approved Cost (£m) | Actual /Forecast Cost | Variation (£m) | Post-Main Investment
|  |  |  | Approved cost as a proportion of total estimated procurement expenditure (%) | Actual Cost as a proportion of total estaitmed procurement expenditure (%)
A400M | 2 | 1 | -1 | 0.06 | 0.03
Total (£m) | 2 | 1 | -1 | 0.06 | 0.03
Actual cost boundaries for Demonstration and Manufacture Phase / PFI
Project/Increment Name | Lowest Approved (£m) | Budgeted For (£m) | Highest Approved (£m)
A400M |  | 2498 | 2614
Cost of the Demonstration and Manufacture Phase
Project/Increment Name | Budgeted for Cost (£m) | Forecast cost (£m) | Variation (£m) | In-Year Variation (£m)
A400M | 2498 | 3268 | 770 | 163
Total (£m) | 2498 | 3269 | 770 | 163
Cost variation against approved cost of the Demonstration and Manufacture Phase
Date | Variation (£m) | Category | Reason for Variation
2012-03-01 | -8 | Procurement Processes | A reduction due to repricing.
2012-03-01 | -10 | Technical Factors | Reduced Defensive Aids hardware device procurement following the drawdown of other aircraft platforms in the 2010 Strategic Defence and Security Review
2012-03-01 | -5 | Technical Factors | Changes to Inegration contingency
2012-03-01 | 1 | Technical Factors | Increased cost of OCCAR management agency
2012-03-01 | 7 | Technical Factors | Revised costing for assuemd set up costs for the A400M training facility including incrased VAT £5m
2012-03-01 | 3 | Technical Factors | Increased cost of integrating equipment to the A400M Platform. (+£3M) DASS (-£3M) Mission Planning System, Technical Support (+£3M)
2011-07-01 | 175 | Procurement Process - International Collaboration | UK contribution to the multinational Export Levy Facility provided to EADS by A400M partner nations
Historic | *** | Changed Capability Requirements | A Planning Round 2011 Option to swap an early delivery aircraft with oen due to be delivered
Historic | *** | Procurement Process - International Collaboration | A Planning Round 2011 Option to reprofile payments to align them with the revised delivery schedule agreed in the six nationa international collaborative contract (***) and associated risk (***)
Historic | *** | Procurement Process - International Collaboration | A change due to a realignment of payments with the revised programme schedule agreed in the six nationa international collaborative contract
Historic | *** | Exchange Rate | Foreign Exchange increase due to changes in planning assumptions
Historic | *** | Inflation | An increase due to chagnes in inflation assumption in the 2011 Planning Round
Historic | *** | Procurement Processes | Increase in estimated cost of Supplier Network Installation for the spares ordering system
Historic | *** | Technical Factors | A reprofiling of initial support spares to align with the revised aircraft delivery programme
Historic | *** | Accounting Adjustments and Redefinitions | Removal of Indirect RDEL (Foreign Exchange) in accordance with a change in Departmental policy
Historic | *** | Accounting Adjustments and Redefinitions | Removal of Cost of Capital due to Clear line of Sigh policy implemented by HM Treasury
Historic | *** | Exchange Rate | An In Year gain due to the increase in the value of £ vs € due to the difference between the set planning exchange rate and actual outturn
Historic | *** | Changed Capability Requirements | A reduction in the need to use the International Training Centre facilities due to programme delays
Historic | *** | Procurement Processes - International Collaboration | A change due to the programme reblaancing as a result of work undertaken in support of concluding an amended contract
Historic | *** | Exchange Rate | Loss due to the difference between the set planning exchange rate and the forecast outturn
Historic | *** | Procurement Process | Revised costing for Mission Planning System due to change from acquisition only to also include support
Historic | *** | Technical Factors | Increase due to the reassessment of the need for capital spares (two long deployment kits
Historic | *** | Exchange Rate | A loss in 2008/2009 due to the fall in the value of £ vs €
Historic | *** | Changed Capability Requirements | A reduction in the need to use the International Training Centre facilities due to programme delays
Historic | *** | Exchange Rate | An increase on payments for training service
Historic | *** | Accounting Adjustments and Redefinitions | Inclusion of VAT on payments for training service
Historic | *** | Technical Factors | Increase due to the reassessment of the need for capital spares
Historic | *** | Changed Capability Requirements | Portable Removable On-Board Inert Gas Generation System fuel tank inerting system
Historic | *** | Inflation | An increase based on latest delivery schedule
Historic | *** | Accounting Adjustments and Redefinitions | Increase due to a revised estimate of the cost of training
Historic | *** | Exchange Rate | An increase in 2008/2009
Historic | *** | Technical Factors | Inclusion of additional airworthiness support to cover aircraft release to service
Historic | *** | Exchange Rate | Variation in 2008/2009
Historic | *** | Inflation | An increase in 2008/2009
Historic | *** | Changed Capability Requirements | Reintroduction of one training simulator
Historic | -94 | Budgetary Factors | Departmental Reviews have identified savings to programme risks (-£23m). Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of Organisation Conjointe de Coopération en matière d'ARmement (OCCAR) Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m). Minor realism changes includes Certification, Special To Type equipment and Training Facilities (+£7m). Realism reprofile of Development Production Phase contract together with Directed Infra-Red Counter Measures and Cargo Hold Mock-up costs (-£4m)
Historic | -355 | Changed Capability Requirements | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date slipped from November 2001 - October 2002 (+£149m). Contract Effectivity Date slipped from October 2002 - April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). Contract Effectivity Date slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | 353 | Procurement Processes | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date slipped from November 2001 - October 2002 (+£149m). Contract Effectivity Date slipped from October 2002 - April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). Contract Effectivity Date slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | -10 | Exchange Rate | A decrease in 2005/2006 (-£24m). Variation in 2004/2005 (+£39m). Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m). Variation in 2003/04 (+£222m). Exchange rate changes (-£15m)
Historic | 12 | Inflation | An increase in 2005/2006 (+£14m). An increase in 2004/2005 (+£8m). Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£10m).
Historic | 65 | Procurement Processes | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in Unit Production Cost (-£65m). Subsequent contract renegotiation due to German reduction in off take (+£130m).
Historic | 34 | Technical Factors | Increase in Training costs, figures from industry indicated a shortfall in costing line (+£32m). Realism decrease to Support activities post aircraft delivery (-£3m). Programme realism with regard to costing Technical Publications (-£5m), Special To Type Equipment (-£5m), Aircraft Ground Equipment (-£4m), Government Furnished Equipment/Facilities (-£7m) and Codification of equipment/spares (-£1m). Training Needs Analysis identified the need for funding increase; Develop & Build Facilities (+£11m), Initial Training (+£7m), Develop & Build Training Devices (+£6m), and Develop & Build Training Facilities (-£3m). Identification of UK only certification requirements (+£6m).
Historic | 50 | Technical Factors | Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m). Costing re- adjusted with understanding of future programme – Certification (-£15m), Government Furnished Equipment (+£4m), Support (+£4m). Re-profiling deliveries for realism Build Facilities (-£1m), Initial Provision Spares (-£5m), Deployment Kits (-£1m). Reduction in the requirement for government procured items (-£46m). Improved understanding of programme requirement for Initial Provision Spares (+£83m), Deployment Kits (-£1m), Initial Training (-£13m) and Mission Planning & Restitution System (-£10m) Growth in estimates for training and Government Furnished Facilities (+£57m)
Net variation | 770
Expenditure to date
Description | Previous expenditure to 31 March 2011 (£m) | In-year expenditure (£m) | Total expenditure to 31 March 2012 (£m)
Assessment Phase | 1 | 0 | 1
Demonstration and Manufacture Phase | 869 | 14 | 883
Support Phase / PFI Cost | 0 | 0 | 0
Total Expenditure | 870 | 14 | 884

## 2011
Cost of the Assessment Phase
Project/Increment Name | Approved Cost (£m) | Actual /Forecast Cost | Variation (£m) | Post-Main Investment
|  |  |  | Approved cost as a proportion of total estimated procurement expenditure (%) | Actual Cost as a proportion of total estaitmed procurement expenditure (%)
A400M | 2 | 1 | -1 | 0.06 | 0.03
Total (£m) | 2 | 1 | -1 | 0.06 | 0.03
Planned/Actual Cost Boundaries for Demonstration and Manufacture Phase / PFI
Project/Increment Name | Lowest Forecast / Approved (£m) | Budgeted For (Post-Main Investment Decisions Projects only) (£m) | Highest Forecast / Approved (£m)
A400M | - | 2498 | 2614
Cost of the Demonstration and Manufacture Phase
Project/Increment Name | Budgeted for Cost (£m) | Forecast cost (£m) | Variation (£m) | In-Year Variation (£m)
A400M | 2498 | 3105 | 607 | 150
Total (£m) | 2498 | 3105 | 607 | 150
Cost Variation against approved Cost of the Demonstration and Manufacture Phase
Date | Variation (£m) | Category | Reason for Variation
2011-04-01 | *** | Changed Capability Requirements | A Planning Round 2011 Option to swap an early delivery aircraft with oen due to be delivered
2011-04-01 | *** | Procurement Process - International Collaboration | A Planning Round 2011 Option to reprofile payments to align them with the revised delivery schedule agreed in the six nationa international collaborative contract (***) and associated risk (***)
2011-03-01 | *** | Procurement Process - International Collaboration | A change due to a realignment of payments with the revised programme schedule agreed in the six nationa international collaborative contract
2011-03-01 | *** | Exchange Rate | Foreign Exchange increase due to changes in planning assumptions
2011-03-01 | *** | Inflation | An increase due to chagnes in inflation assumption in the 2011 Planning Round
2011-03-01 | *** | Procurement Processes | Increase in estimated cost of Supplier Network Installation for the spares ordering system
2011-03-01 | *** | Technical Factors | A reprofiling of initial support spares to align with the revised aircraft delivery programme
2011-03-01 | *** | Accounting Adjustments and Redefinitions | Removal of Indirect RDEL (Foreign Exchange) in accordance with a change in Departmental policy
Historic | *** | Accounting Adjustments and Redefinitions | Removal of Cost of Capital due to Clear line of Sigh policy implemented by HM Treasury
Historic | *** | Exchange Rate | An In Year gain due to the increase in the value of £ vs € due to the difference between the set planning exchange rate and actual outturn
Historic | *** | Changed Capability Requirements | A reduction in the need to use the International Training Centre facilities due to programme delays
Historic | *** | Procurement Processes - International Collaboration | A change due to the programme reblaancing as a result of work undertaken in support of concluding an amended contract
Historic | *** | Exchange Rate | Loss due to the difference between the set planning exchange rate and the forecast outturn
Historic | *** | Procurement Process | Revised costing for Mission Planning System due to change from acquisition only to also include support
Historic | *** | Technical Factors | Increase due to the reassessment of the need for capital spares (two long deployment kits
Historic | *** | Exchange Rate | A loss in 2008/2009 due to the fall in the value of £ vs €
Historic | *** | Changed Capability Requirements | A reduction in the need to use the International Training Centre facilities due to programme delays
Historic | *** | Exchange Rate | An increase on payments for training service
Historic | *** | Accounting Adjustments and Redefinitions | Inclusion of VAT on payments for training service
Historic | *** | Technical Factors | Increase due to the reassessment of the need for capital spares
Historic | *** | Changed Capability Requirements | Portable Removable On-Board Inert Gas Generation System fuel tank inerting system
Historic | *** | Inflation | An increase based on latest delivery schedule
Historic | *** | Accounting Adjustments and Redefinitions | Increase due to a revised estimate of the cost of training
Historic | *** | Exchange Rate | An increase in 2008/2009
Historic | *** | Technical Factors | Inclusion of additional airworthiness support to cover aircraft release to service
Historic | *** | Exchange Rate | Variation in 2008/2009
Historic | *** | Inflation | An increase in 2008/2009
Historic | *** | Changed Capability Requirements | Reintroduction of one training simulator
Historic | -94 | Budgetary Factors | Departmental Reviews have identified savings to programme risks (-£23m). Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of Organisation Conjointe de Coopération en matière d'ARmement (OCCAR) Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m). Minor realism changes includes Certification, Special To Type equipment and Training Facilities (+£7m). Realism reprofile of Development Production Phase contract together with Directed Infra-Red Counter Measures and Cargo Hold Mock-up costs (-£4m)
Historic | -355 | Changed Capability Requirements | Defer UK A400M National Training Facility by 2 years (-£2m). Fuel Tank Inertion System Pipe work (+£6m). Deletion of Centralised Crypto Management Unit requirement (-£12m). Deletion of Civil Pallets Configuration Item (-£5m). Addition of Propeller Brake (+£6m). Option to re-profile Training Facilities for realism(-£1m). Programme measure to move deferred configuration Items back into aircraft delivery profile (-£2m). Reduction in number of aircraft to be equipped with Defensive Aids Sub-System from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months. (-£81m). Option bringing the Defensive Aids Sub- System forward onto aircraft 1-9 (+£9m). Delay of programme by 9 months (-£12m) Deletion of one training simulator (-£23m)
Historic | 353 | Procurement Processes | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date slipped from November 2001 - October 2002 (+£149m). Contract Effectivity Date slipped from October 2002 - April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). Contract Effectivity Date slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | -10 | Exchange Rate | A decrease in 2005/2006 (-£24m). Variation in 2004/2005 (+£39m). Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m). Variation in 2003/04 (+£222m). Exchange rate changes (-£15m)
Historic | 12 | Inflation | An increase in 2005/2006 (+£14m). An increase in 2004/2005 (+£8m). Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£10m).
Historic | 65 | Procurement Process | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in Unit Production Cost (-£65m). Subsequent contract renegotiation due to German reduction in off take (+£130m).
Historic | 34 | Technical Factors | Increase in Training costs, figures from industry indicated a shortfall in costing line (+£32m). Realism decrease to Support activities post aircraft delivery (-£3m). Programme realism with regard to costing Technical Publications (-£5m), Special To Type Equipment (-£5m), Aircraft Ground Equipment (-£4m), Government Furnished Equipment/Facilities (-£7m) and Codification of equipment/spares (-£1m). Training Needs Analysis identified the need for funding increase; Develop & Build Facilities (+£11m), Initial Training (+£7m), Develop & Build Training Devices (+£6m), and Develop & Build Training Facilities (-£3m). Identification of UK only certification requirements (+£6m).
Historic | 50 | Technical Factors | Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m). Costing re- adjusted with understanding of future programme – Certification (-£15m), Government Furnished Equipment (+£4m), Support (+£4m). Re-profiling deliveries for realism Build Facilities (-£1m), Initial Provision Spares (-£5m), Deployment Kits (-£1m). Reduction in the requirement for government procured items (-£46m). Improved understanding of programme requirement for Initial Provision Spares (+£83m), Deployment Kits (-£1m), Initial Training (-£13m) and Mission Planning & Restitution System (-£10m) Growth in estimates for training and Government Furnished Facilities (+£57m)
Net Variation (£m) | 607
Expenditure to date
Description | Previous expenditure to 31 March 2010 (£m) | In-year expenditure (£m) | Total expenditure to 31 March 2011 (£m)
Assessment Phase | 1 | 0 | 1
Demonstration & Manufacture Phase | 849 | 20 | 869
Support Phase / Service / PFI Cost | 0 | 0 | 0
Total Expenditure | 850 | 20 | 870

## 2010
Cost of the Assessment Phase
Description | Approved Cost (£m) | Actual /Forecast Cost | Variation (£m) | Post-Main Investment Decision Projects only
|  |  |  | Approved cost as a proportion of total estimated procurement expenditure (%) | Actual Cost as a proportion of total estaitmed procurement expenditure (%)
A400M | 2 | 1 | -1 | 0.06 | 0.03
Total | 2 | 1 | -1 | 0.06 | 0.03
Planned / Actual cost boundaries for Demonstration and Manufacture Phase / PFI
Description | Lowest Forecast / Approved | Budgeted For (Post-Main Investment Decision Projects only) | Highest Forecast / Approved
A400M | - | 2628 | 2744
Total | - | 2628 | 2744
Cost of the Demonstration and Manufacture Phase
Description | Approved Cost (£m) | Actual /Forecast Cost | Variation (£m) | In-Year Variation (£m)
A400M | 2744 | 3231 | 487 | -54
Total | 2744 | 3231 | 487 | -54
Cost Variation against approved Cost of the Demonstration and Manufacture Phase
Date | Variation (£m) | Factor | Reason for Variation
2010-03-01 | *** | Exchange Rate | An In Year gain due to the increase in the value of £ vs € due to the difference between the set planning exchange rate and actual outturn
2010-03-01 | *** | Changed Capability Requirements | A reduction in the need to use the International Training Centre facilities due to programme delays
2010-03-01 | *** | Procurement Processes (International Collaboration) | A change due to the programme reblaancing as a result of work undertaken in support of concluding an amended contract
2010-03-01 | *** | Exchange Rate | Loss due to the difference between the set planning exchange rate and the forecast outturn
2010-03-01 | *** | Procurement Processes | Revised costing for Mission Planning System due to change from acquisition only to also include support
2010-03-01 | *** | Technical Factors | Increase due to the reassessment of the need for capital spares (two long deployment kits
Historic | *** | Exchange Rate | A loss in 2008/2009 due to the fall in the value of £ vs €
Historic | *** | Accounting Adjustments and Re-definitions | An increase in Cost of Capital Charge as a result of programme delays
Historic | *** | Changed Capability Requirements | A reduction in the need to use the International Training Centre facilities due to programme delays
Historic | *** | Exchange Rate | An increase on payments for training service
Historic | *** | Accounting Adjustments and Redefinitions | Inclusion of VAT on payments for training service
Historic | *** | Technical Factors | Increase due to the reassessment of the need for capital spares
Historic | *** | Changed Capability Requirements | Portable Removable On-Board Inert Gas Generation System fuel tank inerting system
Historic | *** | Inflation | An increase based on latest delivery schedule
Historic | *** | Accounting Adjustments and Redefinitions | Increase due to a revised estimate of the cost of training
Historic | *** | Exchange Rate | An increase in 2008/2009
Historic | *** | Technical Factors | Inclusion of additional airworthiness support to cover aircraft release to service
Historic | *** | Exchange Rate | Variation in 2008/2009
Historic | *** | Inflation | An increase in 2008/2009
Historic | *** | Changed Capability Requirements | Reintroduction of one training simulator
Historic | -77 | Accounting Adjustments and Re-definitions | Variation in Cost of Capital Charge due to a revision of accruals in future forecast costs (-£8m). Changes to Cost of Capital Charge and Sunk Costs (-£1m). Correction of previous years treatment of deliveries (+£1m). Transfer from RDEL to CDEL (-£1m). Difference in variation figures due to revision of Cost of Capital Charge (-£42m). Changes in timing of expenditure leading to a variation in Cost of Capital Charge (-£26m)
Historic | -93 | Changed Budgetary Priorities | Departmental Reviews have identified savings to programme risks (-£23m). Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of Organisation Conjointe de Coopération en matière d'ARmement (OCCAR) Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m). Minor realism changes includes Certification, Special To Type equipment and Training Facilities (+£7m). Realism reprofile of Development Production Phase contract together with Directed Infra-Red Counter Measures and Cargo Hold Mock-up costs (-£4m) and associated Cost Of Capital charges (+£1m)
Historic | -333 | Changed Capability Requirements | Defer UK A400M National Training Facility by 2 years (-£2m). Fuel Tank Inertion System Pipe work (+£6m). Deletion of Centralised Crypto Management Unit requirement (-£12m). Deletion of Civil Pallets Configuration Item (-£5m). Addition of Propeller Brake (+£6m). Option to re-profile Training Facilities for Realism (-£1m). Programme measure to move deferred configuration Items back into aircraft delivery profile (-£2m). Reduction in number of aircraft to be equipped with Defensive Aids Sub-System from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months. (-£81m). Option bringing the Defensive Aids Sub-System forward onto aircraft 1-9 (+£9m). Delay of programme by 9 months (-£12m) and associated Cost Of Capital changes (+£25m) Deletion of one training simulator (-£23m) and associated Cost Of Capital changes (-£3m)
Historic | 353 | Contracting Process | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date slipped from November 2001 - October 2002 (+£149m). Contract Effectivity Date slipped from October 2002 - April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). Contract Effectivity Date slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | -11 | Exchange Rate | A decrease in 2005/2006 (-£24m). Variation in 2004/2005 (+£39m). Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m). Variation in 2003/04 (+£222m). Exchange rate changes (-£15m) and associated Cost Of Capital changes (-£1m)
Historic | 12 | Inflation | An increase in 2005/2006 (+£14m). An increase in 2004/2005 (+£8m). Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£10m).
Historic | 65 | Procurement Strategy | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in Unit Production Cost (-£65m). Subsequent contract renegotiation due to German reduction in offtake (+£130m).
Historic | 88 | Technical Factors | Increase in Training costs, figures from industry indicated a shortfall in costing line (+£32m). Realism decrease to Support activities post aircraft delivery (-£3m). Programme realism with regard to costing Technical Publications (-£5m), Special To Type Equipment (-£5m), Aircraft Ground Equipment (-£4m), Government Furnished Equipment/Facilities (-£7m) and Codification of equipment/spares (-£1m). Training Needs Analysis identified the need for funding increase; Develop & Build Facilities (+£11m), Initial Training (+£7m), Develop & Build Training Devices (+£6m), and Develop & Build Training Facilities (-£3m). Identification of UK only certification requirements (+£6m). Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m). Costing re- adjusted with understanding of future programme – Certification (-£15m), Government Furnished Equipment (+£4m), Support (+£4m). Re-profiling deliveries for realism Build Facilities (-£1m), Initial Provision Spares (-£5m), Deployment Kits (-£1m). Reduction in the requirement for government procured items. (-£46m). Improved understanding of programme requirement for Initial Provision Spares (+£83m), Deployment Kits (-£1m), Initial Training (-£13m) and Mission Planning & Restitution System (-£10m) Growth in estimates for training and Government Furnished Facilities (+£57m) and associated Cost Of Capital changes (+£4m).
Historic | -116 | Risk Differential | Difference between the risk allowed for in the most likely (50%) and the approved figures at Main Gate
Net Variation | 487
Unit Production Cost
Description | Unit production costs (£m) |  | Quantities Required
| At Main Investment Decision | Currently | At Main Investment Decision | Currently
A400M | *** | *** | 25 | 22
Expenditure to date
Description | Previous expenditure to 31 March 2009 | In-year expenditure | Total expenditure to 31 March 2010
Assessment Phase (£m) | 1 | 0 | 1
Demonstration & Manufacture Phase (£m) | 856 | 74 | 930
Support Phase / Service / PFI Cost (£m) | - | - | -
Total Expenditure (£m) | 857 | 74 | 931

## 2009
Cost of the Assessment Phase
Description | Approved Cost (£m) | Actual /Forecast Cost | Variation (£m) | Post-Main Investment Decision Projects only
|  |  |  | Approved cost as a proportion of total estimated procurement expenditure (%) | Actual Cost as a proportion of total estaitmed procurement expenditure (%)
A400M | 2 | 1 | -1 | 0.06 | 0.03
Planned/Actual Cost Boundaries for Demonstration and Manufacture Phase/PFI
Description | Lowest Forecast / Approved | Budgeted For (Post-Main Investment Decision Projects only) | Highest Forecast / Approved
A400M | - | 2628 | 2744
Cost Boundaries of the Demonstration and Manufacture (D&M) Phase
Description | Approved Cost (£m) | Actual /Forecast Cost | Variation (£m) | In-Year Variation (£m)
A400M | 2744 | 3285 | 541 | 653
Cost Variation against approved Cost of the D&M Phase
Date | Variation (£m) | Factor | Explanation
2009-02-01 | *** | Exchange Rate | A loss in 2008/2009 due to the fall in value of £ vs €.
2009-02-01 | *** |  | An increase in Cost of Capital Charge as a result of programme delays
2009-02-01 | *** | Changed Capability Requirements | A reduction in the need to use the International Training Centre facilities due to programme delays
2009-02-01 | *** | Exchange Rate | An increase on payments for the training service
2009-02-01 | *** | Accounting Adjustments and Redefinitions | Inclusion of VAT on payments for training service
2009-02-01 | *** | Technical Factors | Increase due to the reassessment of the need for capital spares
2009-02-01 | *** | Changed Capability Requirements | Portable Removable On-Board Inert Gas Generation System fuel tank inertion system
2009-02-01 | *** | Inflation | An increase based on the latest delivery schedule
2009-02-01 | *** | Accounting Adjustments and Redefinitions | Increase due to a revised estimate of the cost of training
2009-02-01 | *** | Exchange Rate | An increase in 2008/2009
2008-07-01 | *** | Technical Factors | Inclusion of additional airworthiness support to cover aircraft release to service
2008-07-01 | *** | Exchange Rate | Variation in 2008/2009
2008-07-01 | *** | Inflation | An increase in 2008/2009
April | *** | Changed Capability Requirements | Reintroduction of one training simulator
Historic | -77 | Accounting Adjustments and Redefinitions | Variation in Cost of Capital Charge due to a revision of accruals in future forecast costs (-£8m). Changes to Cost of Capital Charge and Sunk Costs (-£1m). Correction of previous years treatment of deliveries (+£1m). Transfer from RDEL to CDEL (-£1m). Difference in variation figures due to revision of Cost of Capital Charge (-£42m). Changes in timing of expenditure leading to a variation in Cost of Capital Charge (-£26m)
Historic | -93 | Budgetary Factors | Departmental Reviews have identified savings to programme risks (-£23m). Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of Organisation Conjointe de Coopération en matière d'ARmement (OCCAR) Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m). Minor realism changes includes Certification, Special To Type equipment and Training Facilities (+£7m). Realism reprofile of Development Production Phase contract together with Directed Infra-Red Counter Measures and Cargo Hold Mock-up costs (-£4m) and associated Cost Of Capital charges (+£1m)
Historic | -333 | Changed Capability Requirements | Defer UK A400M National Training Facility by 2 years (-£2m). Fuel Tank Inertion System Pipe work (+£6m). Deletion of Centralised Crypto Management Unit requirement (-£12m). Deletion of Civil Pallets Configuration Item (-£5m). Addition of Propeller Brake (+£6m). Option to re- profile Training Facilities for realism (-£1m). Programme measure to move deferred configuration Items back into aircraft delivery profile (-£2m). Reduction in number of aircraft to be equipped with Defensive Aids Sub- System from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months. (-£81m). Option bringing the Defensive Aids Sub-System forward onto aircraft 1-9 (+£9m). Delay of programme by 9 months (-£12m) and associated Cost Of Capital changes (+£25m) Deletion of one training simulator (-£23m) and associated Cost Of Capital changes (-£3m)
Historic | 353 | Procurement Process | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date slipped from November 2001 - October 2002 (+£149m). Contract Effectivity Date slipped from October 2002 - April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). Contract Effectivity Date slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | -11 | Exchange Rate | A decrease in 2005/2006 (-£24m). Variation in 2004/2005 (+£39m). Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m). Variation in 2003/04 (+£222m). Exchange rate changes (-£15m) and associated Cost Of Capital changes (-£1m).
Historic | 12 | Inflation | An increase in 2005/2006 (+£14m). An increase in 2004/2005 (+£8m). Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£10m).
Historic | 65 | Procurement Process | Total number of aircraft order by participating nations higher than anticipated, and consequent reduction in Unit Production Cost (-£65m). Subsequent contract renegotiation due to German reduction in offtake (+£130m).
Historic | 88 | Technical Factors | Increase in Training costs, figures from industry indicated a shortfall in costing line (+£32m). Realism decrease to Support activities post aircraft delivery (-£3m). Programme realism with regard to costing Technical Publications (-£5m), Special To Type Equipment (-£5m), Aircraft Ground Equipment (-£4m), Government Furnished Equipment/Facilities (-£7m) and Codification of equipment/spares (-£1m). Training Needs Analysis identified the need for funding increase; Develop & Build Facilities (+£11m), Initial Training (+£7m), Develop & Build Training Devices (+£6m), and Develop & Build Training Facilities (-£3m). Identification of UK only certification requirements (+£6m). Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m). Costing re-adjusted with understanding of future programme – Certification (-£15m), Government Furnished Equipment (+£4m), Support (+£4m). Re-profiling deliveries for realism. Build Facilities (-£1m), Initial Provision Spares (-£5m), Deployment Kits (-£1m). Reduction in the requirement for government procured items. (-£46m). Improved understanding of programme requirement for Initial Provision Spares (+£83m), Deployment Kits (-£1m), Initial Training (-£13m) and Mission Planning & Restitution System (-£10m) Growth in estimates for training and Government Furnished Facilities (+£57m) and associated Cost Of Capital changes (+£4m).
Historic | -116 | Risk Differential | Difference between the risk allowed for in the most likely (50%) and the approved figures at Main Gate
Net Variation | 541
Unit production cost
Description | Unit productions costs (£m) |  | Quantities required
| At Main Investment Decision | Currently | At Main Investmnet Decision | Currently
A400M | *** | *** | 25 | 25

## 2008
Performance against approved cost
£m (outturn prices) | Procurement Cost
Current Forecast Cost | 2632
Approved Cost at Main Gate | 2744
Variation | -112
In-year changes | 3
Reason for variaion from approved
Date | Variation (£m) | Factor | Explanation
2008-03-01 | 13 | Changed Requirement | Delay of programme by 9 months (-£12m) and associated Cost of Capital changes (+£25m)
2007-08-01 | -16 | Exchange Rate | Exchange rate changes (-£15m) and associated Cost Of Capital changes (-£1m)
2007-08-01 | -3 | Changed Budgetary Priorities | Realism reprofile of Development Production Phase contract together with Directed Infra-Red Counter Measures and Cargo Hold Mock-up costs (-£4m) and associated Cost Of Capital changes (+£1m)
2007-08-01 | -26 | Accounting Adjustments and Re-definitions | Changes in timing of expenditure leading to a variation in Cost of Capital (-£26m)
2007-08-01 | 61 | Technical Factors | Growth in estimates for training and Government Furnished Facilities (+£57m) and associated Cost Of Capital changes (+£4m)
2007-08-01 | -26 | Changed requirement | Deletion of one training simulator (-£23m) and associated Cost Of Capital changes (-£3m)
Historic | -51 | Accounting Adjustments and Redefinitions | Variation in Cost of Capital Charge due to a revision of accruals in future forecast costs (-£8m). Changes to Cost of Capital Charge and Sunk Costs (-£1m). Correction of previous years treatment of deliveries (+£1m). Transfer from RDEL to CDEL (-£1m). Difference in variation figures due to revision of Cost of Capital Charge (-£42m).
Historic | -90 | Changed Budgetary Priorities | Departmental Reviews have identified savings to programme risks (-£23m). Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of Organisation Conjointe de Coopération en matière d'ARmement (OCCAR) Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m). Minor realism changes includes Certification, Special To Type equipment and Training Facilities (+£7m).
Historic | -320 | Changed Requirement | Defer UK A400M National Training Facility by 2 years (-£2m). Fuel Tank Inertion System Pipe work (+£6m). Deletion of Centralised Crypto Management Unit requirement (-£12m). Deletion of Civil Pallets Configuration Item (-£5m). Addition of Propeller Brake (+£6m). Option to re-profile Training Facilities for realism (-£1m). Programme measure to move deferred Configuration Items back into aircraft delivery profile (-£2m). Reduction in number of aircraft to be equipped with Defensive Aids Sub-System from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months. (-£81m). Option bringing the Defensive Aids Sub- System forward onto aircraft 1-9 (+£9m).
Historic | 353 | Contracting Process | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date slipped from November 2001 - October 2002 (+£149m). Contract Effectivity Date slipped from October 2002 - April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). Contract Effectivity Date slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | 5 | Exchange Rate | A decrease in 2005/2006 (-£24m). Variation in 2004/2005 (+£39m). Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m). Variation in 2003/04 (+£222m).
Historic | 12 | Inflation | An increase in 2005/2006 (+£14m). An increase in 2004/2005 (+£8m). Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£10m).
Historic | 65 | Procurement Strategy | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in Unit Production Cost (-£65m). Subsequent contract renegotiation due to German reduction in offtake (+£130m).
Historic | 27 | Technical Factors | Increase in Training costs, figures from industry indicated a shortfall in costing line (+£32m). Realism decrease to Support activities post aircraft delivery (-£3m). Programme realism with regard to costing Technical Publications (-£5m), Special To Type Equipment (-£5m), Aircraft Ground Equipment (-£4m), Government Furnished Equipment/Facilities (-£7m) and Codification of equipment/spares (-£1m). Training Needs Analysis identified the need for funding increase; Develop & Build Facilities (+£11m), Initial Training (+£7m), Develop & Build Training Devices (+£6m), and Develop & Build Training Facilities (-£3m). Identification of UK only certification requirements (+£6m). Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m). Costing re- adjusted with understanding of future programme – Certification (-£15m), Government Furnished Equipment (+£4m), Support (+£4m). Re-profiling deliveries for realism Build Facilities (-£1m), Initial Provision Spares (-£5m), Deployment Kits (-£1m). Reduction in the requirement for government procured items. (-£46m). Improved understanding of programme requirement for Initial Provision Spares (+£83m), Deployment Kits (-£1m), Initial Training (-£13m) and Mission Planning & Restitution System (-£10m).
Historic | -116 | Risk Differential | Difference between the risk allowed for in the most likely (50%) and the approved figures at Main Gate
Net Variation | -112
Expenditure to date
Expenditure to 31 March 2008 (£m) | 564
Unit Production Cost
Unit Production Cost (£m) |  | Quantities Required
at Main Gate | Current | At Main Gate | Current
*** | *** | 25 | 25

## 2007
Performance against approved cost
£m (outturn prices) | Procurement Cost
Current Forecast Cost | 2629
Approved Cost at Main Gate | 2744
Variation | -115
In-year changes | 13
Reasons for variation from approved cost
Factor | Variation (£m) | Factor | Explanation
2007-03-01 | -8 | Accounting Adjustments and Redefinitions | Variation in Cost of Captial due to a revision of accruals in future forecast costs
2007-03-01 | -2 | Change Requirement | Defer UK A400M National Training Facility by 2 years.
2007-03-01 | 6 | Change Requirement | Fule Tank Inertion System Pipe work
2007-03-01 | -12 | Change Requirement | Deltion of Centralised Crypto Management Unit requirement
2006-05-01 | 32 | Technical Factors | Increase in Training cost, figures form industry indicated a shortfall in costing line
2006-05-01 | -3 | Technical Factors | Realism decrease to Support acitivities post aircraft delivery
Historic | -43 | Accounting Adjustments and Redefinitions | Changes to Cost of Capital costs and Sunk Costs (-£1m). Correction of previous years treatment of deliveries (+£1m). Transfer from RDEL to CDEL (-£1m). Difference in variation figures due to revision of Cost of Capital Charge (-£42m).
Historic | -312 | Change Requirement | Deletion of Civil Pallets Configuration Item (-£5m). Addition of Propeller Brake(+£6m). Option to re-profile Training Facilities for realism (-£1m). Programme measure to move deferred configuration Items back into aircraft delivery profile (-£2m). Reduction in number of aircraft to be equipped with Defensive Aids Sub-System (DASS) from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months (-£81m) Option bringing the DASS forward onto aircraft 1-9 (+£9m).
Historic | -2 | Technical Factors | Programme realism with regard to costing Technical Publications (-£5m), Special To Type Equipment (-£5m), Aircraft Ground Equipment (-£4m), Government Furnished Equipment/Facilities (-£7m) and Codification of equipment/spares (-£1m). Training Needs Analysis identified the need for funding increase; Develop &Build Facilities (+£11m), Initial Training (+£7m), Develop & Build Training Devices (+£6m), and Develop & Build Training Facilities (-£3m). Identification of UK only certification requirements (+£6m). Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m). Costing re- adjusted with understanding of future programme – Certification (-£15m), Government Furnished Equipment (+£4m), Support (+£4m). Re-profiling deliveries for realism Build Facilities (-£1m), Initial Provision Spares (-£5m), Deployment Kits (-£1m). Reduction in the requirement for government procured items. (-£46m). Improved understanding of programme requirement for Initial Provision Spares (+£83m), Deployment Kits (-£1m), Initial Training (-£13m) and Mission Planning & Restitution System (-£10m).
Historic | 5 | Exchange Rate | A decrease in 2005/2006 (-£24m). Variation in 2004/2005 (+£39m). Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m). Variation in 2003/04 (+£222m).
Historic | -90 | Changed Budgetary Priorities | Departmental Reviews have identified savings to programme risks (-£23m). Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of Organisation Conjointe de Coopération en matière d'ARmement (OCCAR) Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m). Minor realism changes includes Certification, Special To Type equipment and Training Facilities (+£7m).
Historic | 12 | Inflation | An increase in 2005/2006 (+£14m). An increase in 2004/2005 (+£8m). Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£10m).
Historic | 353 | Contracting Process | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date (CED) slipped from November 2001 - October 2002 (+£149m). CED slipped from October 2002 – April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). CED slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | 65 | Procurement Strategy | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in Unit Production Cost (-£65m). Subsequent contract renegotiation due to German reduction in offtake (+£130m).
Historic | -116 | Risk Differential | Difference between the risk allowed for in the most likely (50%) and the approved figures at Main Gate.
Net Variation | -115
Expenditure to date
Expenditure to 31 March 2007 (£m) | 334
Unit Production Cost (£m) |  | Quantities Required
at Main Gate | Current | at Main Gate | Current
*** | *** | 25 | 25

## 2006
Performance against approved cost
£m (outturn prices) | Procurement Cost
Current Forecast Cost | 2616
Approved Cost at Main Gate | 2744
Variation | -128
In-year changes | -28
Reasons for variation from approved cost
Factor | Variation (£m) | Factor | Explanation
2006-03-01 | -1 | Accounting Adjustments and Redefinitions | Changes to Cost of Capital cost and sunk costs.
2006-03-01 | -5 | Change Requirement | Departmental Review - Deletion of civil pallets configuration item
2006-02-01 | -22 | Technical Factors | Programme realism with regard to costing Technical Publications (-£5m), Special to Type Equipment (-£5m), Aircraft Ground Equipment (-£4m), Government Furnished Equipment/Facilities (-£7m) and Codification of equipment/spares (-£1m).
2006-02-01 | -24 | Exchange Rate | Variation in 2005/2006
2006-02-01 | 21 | Technical Factors | Training Needs Analysis identified the need for funding increase; Develop & Build Facilities (+£11m), Initial Training (+£7m), Develop & Build Training Devices (+£6m), and Develop & Build Training Facilities (-£3m).
2006-02-01 | 6 | Technical Factors | Identification of UK only certification requirements
2006-01-01 | 6 | Changed Requirement | Addition of Propeller Brake
2006-01-01 | -23 | Changed Budgetary Priorities | Departmental Reviews have identified savings to programme risks.
2006-01-01 | 14 | Inflation | Variation in 2005/2006
Historic | -42 |  | Transfer from RDEL to CDEL (-£1m). Difference in variation figures due to revision of Cost of Capital Charge (-£42m). Correction of previous years' treatment of deliveries (+£1m).
Historic | -7 | Technical Factors | Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m). Costing re-adjusted with understanding of future programme: Certification (-£15m), Government Furnished Equipment (+£4m), Support (+£4m). Reprofiling deliveries for realism Build Facilities (-£1m), Initial Provision Spares (-£5m), Deployment Kits (-£1m). Reduction in the requirement for government procured items. (-£46m). Improved understanding of programme requirement for Initial Provision Spares (+83m), Deployment Kits (-£1m), Initial Training (-£13m) and Mission Planning & Restitution System (-£10m).
Historic | -313 | Changed Requirement | Option to reprofile Training Facilities for realism (-£1m). Programme measure to move deferred configuration items back into aircraft delivery profile (-£2m). Reduction in number of aircraft to be equipped with Defensive Aids Sub-System (DASS) from 25 to 9 (-£238m). Programme option to delete and defer configuration items and to slip In Service Date by 12 months (-£81m). Option bringing the DASS forward onto aircraft 1-9 (+£9m).
Historic | -67 | Changed Budgetary Priorities | Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of OCCAR Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m). Minor realism changes includes Certification, Special to Type equipment and Training Facilities (+£7m).
Historic | -2 | Inflation | Variation in 2004/2005 (+£8m). Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in variations: 2000/2001 (-£6m), 2001/2002 (+£6m), 2002/2003 (-£10m).
Historic | 29 | Exchange Rate | Variation in 2004/2005 (+£39m). Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m). Variation in 2003/2004 (+£222m).
Historic | 353 | Contracting Process | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date (CED) slipped from November 2001 - October 2002 (+£149m). CED slipped from October 2002 – April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). CED slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | 65 | Procurement Strategy | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in UPC (-£65m). Subsequent contract renegotiation due to German reduction in offtake (+£130m).
Historic | -116 | Risk Differential | Difference between the risk allowed for in the most likely (50%) and the highest acceptable (90%) estimates at Main Gate
Net Variation | -128
Expenditure to date
Expenditure to 31 March 2006 (£m) | 199
Unit Production Cost (£m) |  | Quantities Required
at Main Gate | Current | at Main Gate | Current
*** | *** | 25 | 25

## 2005
Performance against approved cost
£m (outturn prices) | Procurement Cost
Current Forecast Cost | 2644
Approved Cost at Main Gate | 2744
Variation | -100
In-year changes to 2004/2005 | 25
Reasons for variation from approved cost
Factor | Variation (£m) | Factor | Explanation
2005-03-01 | 1 | Accounting Adjustment | Correction of previous years treatment of deliveries (+£1m).
2005-03-01 | -6 | Technical Factors | Costing realism in line with better programme understanding including adjustment for actual sunk costs (-£6m).
2005-03-01 | -1 | Changed requirement | Option to reprofile Training Facilities for realism (-£1m).
2004-06-01 | 39 | Exchange Rate | Variation in 2004/2005 (+£39m).
2004-04-01 | -2 | Changed requirement | Programme measure to move deferred configuration items back into aircraft delivery profiel (-£2m).
2004-04-01 | 8 | Inflation | An increase in 2004/2005 (+£8m).
2004-04-01 | -14 | Technical Factors | Costing re-adjusted with understand of future programme: Certification (-£15m), Government Furnished Equipment (+£4m), Support (+£4m). Reprofiling deliveries for realism. Build facilities (-£1m), Initial Provision Spares, (-£5m), Deployment Kits (-£1m).
Historic | 13 | Technical Factors | Reduction in the requirement for government procured items (-£46m). Improved understanding of programme requirement for Initial Provision Spares (+£83m), Deployment Kits (-£1m), Initial Training (-£13m) and Mission Planning & Restitution System (-£10m).
Historic | -310 | Changed requirement | Reduction in number of aircraft to be equipped with Defensive Aids Sub-System (DASS) from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months (-£81m). Option bringing the DASS forward onto aircraft 1-9 (+£9m).
Historic | -67 | Changed Budgetary Priorities | Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of OCCAR Programme Division costs (+£5m), QinetiQ support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m). Minor realism changes includes Certification, Special To Type equipment and Training Facilities (+£7m).
Historic | -10 | Inflation | Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£10m).
Historic | -10 | Exchange Rate | Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m). Variation in 2003/04 (+£222m).
Historic | 353 | Contracting Process | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date (CED) slipped from November 2001 - October 2002 (+£149m). CED slipped from October 2002 – April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). CED slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Historic | 65 | Procurement Strategy | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in UPC (-£65m). Subsequent contract renegotiation due to German reduction in offtake (+£130m).
Historic | -43 | Accounting Adjustment and Re-definitions | Transfer from RDEL to CDEL (-£1m). Difference in variation figures due to revision of Cost of Capital Charge (-£42m).
Historic | -116 | Risk Differential | Difference between the most likely and highest acceptable cost at Main Gate (-£119m). Variation due to revised approval figure (+£3m).
Total Variation | -100
Expenditure to date
Expenditure to 31 March 2005 (£m) | 105
Unit Production Cost (£m) |  | Quantities Required
at Main Gate | Current | at Main Gate | Current
*** | *** | 25 | 25

## 2004
Performance against approved cost
£m (outturn prices) | Procurement Cost
Current Forecast Cost | 2619
Approved Cost at Main Gate | 2744
Variation | -125
In-year changes to 2003/2004 | 258
Reasons for variation from approved cost
Factor | Increase £m | Decrease £m | Explanation
Technical Factors | 83 | 70 | Reduction in the requirement for government procured items (-£46m). Improved understanding of programme requirement for Initial Provision Spares (+£83m), Deployment Kits (-£1m), Initial Training (-£13m) and Mission Planning & Restitution System (-£10m).
Changed Requirement | 9 | 319 | Reduction in number of aircraft to be equipped with Defensive Aids Sub-System (DASS) from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months (-£81m). Option bringing the DASS forward onto aircraft 1-9 (+£9m).
Changed Budgetary Priorities | 14 | 81 | Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of OCCAR Programme Division costs (+£5m), QinetiQ support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m). Minor realism changes includes Certification, Special To Type equipment and Training Facilities (+£7m).
Inflation | 6 | 16 | Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£10m).
Exchange Rate | 222 | 232 | Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m). Variation in 2003/04 (+£222m).
Contracting Process | 442 | 89 | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date (CED) slipped from November 2001 - October 2002 (+£149m). CED slipped from October 2002 – April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m). CED slipped from April 2003 - May 2003, includes redefinition of Asset Deliveries to align with aircraft delivery schedule (-£30m).
Procurement Strategy | 130 | 65 | Total number of aircraft ordered by participating nations higher than anticipated, and consequent reduction in UPC (-£65m). Subsequent contract renegotiation due to German reduction in offtake (+£130m).
Accounting Adjustments and Re-definitions |  | 43 | Transfer from RDEL to CDEL (-£1m). Difference in variation figures due to revision of Cost of Capital Charge (-£42m).
Risk Differential | 3 | 119 | Difference between the risk allowed for in the most likely (50%) and highest acceptable (90%) estimates at Main Gate (-£119m). Variation due to revised approval figure (+£3m).
Total | 909 | -1034
Net variation |  | -125
Expenditure to date
Expenditure to 31 March 2004 (£m) | 38
Unit Production Cost (£m) |  | Quantities Required
at Main Gate | Current | at Main Gate | Current
*** | *** | 25 | 25

## 2003
Performance against approved costs
£m (outturn prices) Procurement Cost | Procurement Cost
Current Forecast Cost | 2484
Approved Cost at Main Gate | 2828
Variation | -344
In-year changes in 2002/2003 | 128
Reasons for variation from approved cost
Factor | Increase £m | Decrease £m | Explanation
Technical Factors |  | 46 | Reduction in the requirement for government procured items. (-£46m).
Changed Requirements | 9 | 319 | Reduction in number of aircraft to be equipped with Defensive Aids Sub-System (DASS) from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months (-£81m). Option bringing the DASS forward onto aircraft 1-9 (+£9m).
Changed Budgetary Priorities | 7 | 81 | Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of OCCAR Programme Division costs (+£5m), QinetiQ Support costs increased (+£1m), unidentified variance (+£1m). Equipment Programme Measure deleting 1 Simulator (-£20m).
Inflation | 6 | 16 | Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a decrease 2000/2001 (-£6m), an increase 2001/2002 (+£6m), a decrease 2002/2003 (-£10m).
Exchange Rate |  | 232 | Variation in exchange rate assumptions used in the Business Case, 2000/2001, 2001/2002 and 2002/2003 (-£232m).
Contracting Process | 442 | 59 | Realism to reflect 3 month delay in 2000/01 to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m). Contract Effectivity Date (CED) slipped from November 2001 - October 2002 (+£149m). CED slipped from October 2002 - April 2003 (-£59m). Adjustments in line with increased knowledge of Programme (+£66m).
Procurement Strategy | 130 | 65 | Total number of aicraft ordered by participating nations higher than anticipated, and consequent reduction in UPC (-£65m). Subsequent contract renegotiation due to German reduction in offtake (+£130m).
Accounting Adjustments and Re-definitions |  | 1 | Transfer from RDEL to CDEL (-£1m).
Risk Differential |  | 119 | Difference between the most likely and highest acceptable cost at Main Gate (-£119m)
Total | 594 | -938
Net Variation |  | -344
Expenditure to date
Expenditure to 31 March 2003 (£m) | 2
Unit Production Cost (£m) |  | Quantities Required
at Main Gate | Current | at Main Gate | Current
*** | *** | 25 | 25

## 2002
Performance against approved costs
£m (outturn prices) Procurement Cost | Procurement Cost
Current Forecast Cost | 2356
Approved Cost at Main Gate | 2828
Variation | -472
In-year changes in 2001/2002 | -226
Reasons for variation from approved cost
Factor | Increase £m | Decrease £m | Explanation
Changed Requirement |  | 319 | Reduction in number of aircraft to be equipped with Defensive Aids Suite from 25 to 9 (-£238m). Programme option to delete and defer Configuration Items and to slip In Service Date by 12 months (-£81m).
Changed Budgetary Priorities | 7 | 61 | Changed delivery profile from that in the Business Case (-£61m). Minor realism adjustments, includes UK share of OCCAR Programme Division costs increased (+£5m), DERA Support costs increased (+£1m), unidentified variance (+£1m).
Inflation | 6 | 6 | Changes between inflation rate assumed in the Business Case and yearly inflation indices resulting in a reduction 2001/2001 (-£6m) and an increase 2001/2002 (+£6m).
Exchange Rate |  | 142 | Variation in exchange rate assumptions used in the Business Case, 2000/2001 and 2001/2002 (-£142m).
Contracting Process | 227 |  | Realism to reflect 3 months’ delay to contract effectivity (+£52m). Slip of aircraft payments and associated equipment to reflect above contract let decision (+£15m). Improved costing data for Configuration Items available (+£160m).
Procurement Strategy |  | 65 | Total number of aircraft ordered by participating nations increased, and consequent reduction in UPC (-£65m).
Risk Differential |  | 119 | Difference between the risk allowed for in the most likely (50%) and highest acceptable (90%) estimates at Main Gate (-£119m).
Total | 240 | -712
Net Variation |  | -472

## 2001
Cost of the assessment phase
£m (outturn prices) | Assessment phase cost
Forecast Cost | 1.4
Approved Cost at Initial Gate | 2
Variation | -0.6

## 2000
Cost of the assessment phase
£m (outturn prices) | Assessment phase cost
Forecast Cost | 1.4
Approved Cost at Initial Gate | 2
Variation | -0.6