## CostSummary
Cost Summary
Total Acquisition Cost and Quantity - Total Program 2015
| BY 2012 $M |  |  | BY2012 | TY $M
$M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
[5 empty] | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 59677.3 | 59398.1 | -- | 59491.2 | 55233.8 | 55182.9 | 55133
Procurement | 266665.8 | 266665.8 | -- | 249667.8 | 335680.7 | 335680.7 | 319115.7 | `
Flyaway | -- | -- | -- | 222668.7 | -- | -- | 286951.9
Recurring | -- | -- | -- | 197002 | -- | -- | 255294.7
Non Recurring | -- | -- | -- | 25666.7 | -- | -- | 31657.2
Support | -- | -- | -- | 26999.1 | -- | -- | 32163.8
Other Support | -- | -- | -- | 16223.6 | -- | -- | 19225.3
Initial Spares | -- | -- | -- | 10775.5 | -- | -- | 12938.5
MILCON | 4168 | 4168 | -- | 4101.4 | 4797.3 | 4797.3 | 4793.3
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 330511.1 | 330231.9 | N/A | 313260.4 | 395711.8 | 395660.9 | 379042
Total Acquisition Cost and Quantity - F-35 Aircraft
| BY 2012 $M |  |  | BY2012 | TY $M
$M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
[5 empty] | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 47982.1 | 46457.5 | 51103.3 | 46368.6 | 44410.1 | 43360.7 | 43170.1
Procurement | 224332.9 | 224332.9 | 246766.2 | 211290.9 | 282647.8 | 282647.8 | 270427.5
Flyaway | -- | -- | -- | 189120.8 | -- | -- | 244057.7
Recurring | -- | -- | -- | 166222.4 | -- | -- | 215735.2
Non Recurring | -- | -- | -- | 22898.4 | -- | -- | 28322.5
Support | -- | -- | -- | 22170.1 | -- | -- | 26369.8
Other Support | -- | -- | -- | 14549 | -- | -- | 17248.4
Initial Spares | -- | -- | -- | 7621.1 | -- | -- | 9121.4
MILCON | 4168 | 4168 | 4584.8 | 4101.4 | 4797.3 | 4797.3 | 4793.3
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 276483 | 274958.4 | N/A | 261760.9 | 331855.2 | 330805.8 | 318390.9
| SAR Baseline | Current APB Development | Current Estimate
Quantity | Dev Est
RDT&E | 14 | 14 | 14
Procurement | 2443 | 2443 | 2443
Total | 2457 | 2457 | 2457
Total Acquisition Cost and Quantity - F-35 Engine
| BY 2012 $M |  |  | BY2012 | TY $M
$M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
[5 empty] | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 11695.2 | 12940.6 | 14234.7 | 13122.6 | 10823.7 | 11822.2 | 11962.9
Procurement | 42332.9 | 42332.9 | 46566.2 | 38376.9 | 53032.9 | 53032.9 | 48688.2
Flyaway | -- | -- | -- | 33547.9 | -- | -- | 42894.2
Recurring | -- | -- | -- | 30779.6 | -- | -- | 39559.5
Non Recurring | -- | -- | -- | 2768.3 | -- | -- | 3334.7
Support | -- | -- | -- | 4829 | -- | -- | 5794
Other Support | -- | -- | -- | 1674.6 | -- | -- | 1976.9
Initial Spares | -- | -- | -- | 3154.4 | -- | -- | 3817.1
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 54028.1 | 55273.5 | N/A | 51499.5 | 63856.6 | 64855.1 | 60651.1
| SAR Baseline | Current APB Development | Current Estimate
Quantity | Dev Est
RDT&E | 14 | 14 | 14
Procurement | 2443 | 2443 | 2443
Total | 2457 | 2457 | 2457

## Funding Summary
Appropriation and Quantity Summary
Funding Summary - Total Program
FY 2017 President's Budget / December 2015 SAR (TY$ M)
To
Appropriation | Prior | FY2016 | FY2017 | FY2018 | FY2019 | FY2020 | FY2021 | Complete | Total
RDT&E | 51881.1 | 1506.2 | 1436.9 | 273.3 | 14.9 | 11.2 | 9.4 | 0 | 55133
Procurement | 46173 | 9876.8 | 8703 | 10593.3 | 10402.1 | 11278.6 | 13107 | 208981.9 | 319115.7
MILCON | 1489.6 | 292.7 | 571.7 | 165.7 | 183.5 | 135.7 | 116.2 | 1838.2 | 4793.3
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2017 Total | 99543.7 | 11675.7 | 10711.6 | 11032.3 | 10600.5 | 11425.5 | 13232.6 | 210820.1 | 379042
PB 2016 Total | 99532.9 | 10959.5 | 11586.7 | 12093.5 | 12034.6 | 11906.9 | 12358.6 | 220662 | 391134.7
Delta | 10.8 | 716.2 | -875.1 | -1061.2 | -1434.1 | -481.4 | 874 | -9841.9 | -12092.7
Funding Summary - F-35 Aircraft
FY 2017 President's Budget / December 2015 SAR (TY$ M)
To
Appropriation | Prior | FY2016 | FY2017 | FY2018 | FY2019 | FY2020 | FY2021 | Complete | Total
RDT&E | 40174.4 | 1306.6 | 1380.3 | 273.3 | 14.9 | 11.2 | 9.4 | 0 | 43170.1
Procurement | 39405.5 | 8625.9 | 7194.4 | 8784 | 8627.7 | 9366.7 | 10866.2 | 177557.1 | 270427.5
MILCON | 1489.6 | 292.7 | 571.7 | 165.7 | 183.5 | 135.7 | 116.2 | 1838.2 | 4793.3
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2017 Total | 81069.5 | 10225.2 | 9146.4 | 9223 | 8826.1 | 9513.6 | 10991.8 | 179395.3 | 318390.9
PB 2016 Total | 81040.1 | 9508.6 | 10072.4 | 10305.4 | 10076.7 | 9893 | 10216.9 | 183008.2 | 324121.3
Delta | 29.4 | 716.6 | -926 | -1082.4 | -1250.6 | -379.4 | 774.9 | -3612.9 | -5730.4
Quantity | Undistributed | Prior | FY2016 | FY2017 | FY2018 | FY2019 | FY2020 | FY2021 | To Complete | Total
Development | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Production | 0 | 217 | 68 | 63 | 70 | 80 | 86 | 105 | 1754 | 2443
PB 2016 Total | 14 | 217 | 68 | 63 | 70 | 80 | 86 | 105 | 1754 | 2457
PB 2015 Total | 14 | 217 | 57 | 66 | 88 | 90 | 92 | 100 | 1733 | 2457
Delta | 0 | 0 | 11 | -3 | -18 | -10 | -6 | 5 | 21 | 0
Funding Summary - F-35 Engine
FY 2017 President's Budget / December 2015 SAR (TY$ M)
To
Appropriation | Prior | FY2016 | FY2017 | FY2018 | FY2019 | FY2020 | FY2021 | Complete | Total
RDT&E | 11706.7 | 199.6 | 56.6 | 0 | 0 | 0 | 0 | 0 | 11962.9
Procurement | 6767.5 | 1250.9 | 1508.6 | 1809.3 | 1774.4 | 1911.9 | 2240.8 | 31424.8 | 48688.2
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2017 Total | 18474.2 | 1450.5 | 1565.2 | 1809.3 | 1774.4 | 1911.9 | 2240.8 | 31424.8 | 60651.1
PB 2016 Total | 18492.8 | 1450.9 | 1514.3 | 1788.1 | 1957.9 | 2013.9 | 2141.7 | 37653.8 | 67013.4
Delta | -18.6 | -0.4 | 50.9 | 21.2 | -183.5 | -102 | 99.1 | -6229 | -6362.3
Quantity | Undistributed | Prior | FY2016 | FY2017 | FY2018 | FY2019 | FY2020 | FY2021 | To Complete | Total
Development | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Production | 0 | 217 | 68 | 63 | 70 | 80 | 86 | 105 | 1754 | 2443
PB 2017 Total | 14 | 217 | 68 | 63 | 70 | 80 | 86 | 105 | 1754 | 2457
PB 2016 Total | 14 | 217 | 57 | 66 | 88 | 90 | 92 | 100 | 1733 | 2457
Delta | 0 | 0 | 11 | -3 | -18 | -10 | -6 | 5 | 21 | 0
Annual Funding TY$M, RDT&E, F-35 Aircraft, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1996 | -- | -- | -- | -- | -- | -- | 23.2
1997 | -- | -- | -- | -- | -- | -- | 54.8
1998 | -- | -- | -- | -- | -- | -- | 16.9
Subtotal | -- | -- | -- | -- | -- | -- | 94.9
Annual Funding BY 2012 $M, RDT&E, F-35 Aircraft, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1996 | -- | -- | -- | -- | -- | -- | 30.1
1997 | -- | -- | -- | -- | -- | -- | 70.2
1998 | -- | -- | -- | -- | -- | -- | 21.5
Subtotal | -- | -- | -- | -- | -- | -- | 121.8
Annual Funding TY $M, RDT&E, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1995 | -- | -- | -- | -- | -- | -- | 67.5
1996 | -- | -- | -- | -- | -- | -- | 65.4
1997 | -- | -- | -- | -- | -- | -- | 202.3
1998 | -- | -- | -- | -- | -- | -- | 357.2
1999 | -- | -- | -- | -- | -- | -- | 366.5
2000 | -- | -- | -- | -- | -- | -- | 200.3
2001 | -- | -- | -- | -- | -- | -- | 274.3
2002 | -- | -- | -- | -- | -- | -- | 302.6
2003 | -- | -- | -- | -- | -- | -- | 1210.1
2004 | -- | -- | -- | -- | -- | -- | 1584.1
2005 | -- | -- | -- | -- | -- | -- | 1465.8
2006 | -- | -- | -- | -- | -- | -- | 1678.6
2007 | -- | -- | -- | -- | -- | -- | 1632.4
2008 | -- | -- | -- | -- | -- | -- | 1359
2009 | -- | -- | -- | -- | -- | -- | 1197.5
2010 | -- | -- | -- | -- | -- | -- | 1567.4
2011 | -- | -- | -- | -- | -- | -- | 715.4
2012 | -- | -- | -- | -- | -- | -- | 1262.2
2013 | -- | -- | -- | -- | -- | -- | 972.1
2014 | -- | -- | -- | -- | -- | -- | 553.6
2015 | -- | -- | -- | -- | -- | -- | 479.8
2016 | -- | -- | -- | -- | -- | -- | 457.1
2017 | -- | -- | -- | -- | -- | -- | 389
2018 | -- | -- | -- | -- | -- | -- | 113.6
2019 | -- | -- | -- | -- | -- | -- | 5.3
2020 | -- | -- | -- | -- | -- | -- | 5.4
2021 | -- | -- | -- | -- | -- | -- | 5.5
Subtotal | 5 | -- | -- | -- | -- | -- | 18490
Annual Funding BY 2012 $M, RDT&E, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1995 | -- | -- | -- | -- | -- | -- | 89.1
1996 | -- | -- | -- | -- | -- | -- | 84.9
1997 | -- | -- | -- | -- | -- | -- | 259.5
1998 | -- | -- | -- | -- | -- | -- | 454.5
1999 | -- | -- | -- | -- | -- | -- | 460.9
2000 | -- | -- | -- | -- | -- | -- | 248.3
2001 | -- | -- | -- | -- | -- | -- | 335.4
2002 | -- | -- | -- | -- | -- | -- | 366.3
2003 | -- | -- | -- | -- | -- | -- | 1443.6
2004 | -- | -- | -- | -- | -- | -- | 1838.4
2005 | -- | -- | -- | -- | -- | -- | 1657.5
2006 | -- | -- | -- | -- | -- | -- | 1840.8
2007 | -- | -- | -- | -- | -- | -- | 1747.3
2008 | -- | -- | -- | -- | -- | -- | 1428.6
2009 | -- | -- | -- | -- | -- | -- | 1242.9
2010 | -- | -- | -- | -- | -- | -- | 1602.8
2011 | -- | -- | -- | -- | -- | -- | 714.5
2012 | -- | -- | -- | -- | -- | -- | 1240
2013 | -- | -- | -- | -- | -- | -- | 945.1
2014 | -- | -- | -- | -- | -- | -- | 530.7
2015 | -- | -- | -- | -- | -- | -- | 454.2
2016 | -- | -- | -- | -- | -- | -- | 425.8
2017 | -- | -- | -- | -- | -- | -- | 355.9
2018 | -- | -- | -- | -- | -- | -- | 101.9
2019 | -- | -- | -- | -- | -- | -- | 4.7
2020 | -- | -- | -- | -- | -- | -- | 4.7
2021 | -- | -- | -- | -- | -- | -- | 4.7
Subtotal | 5 | -- | -- | -- | -- | -- | 19883
Annual Funding TY $M, RDT&E, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1994 | -- | -- | -- | -- | -- | -- | 23.7
1995 | -- | -- | -- | -- | -- | -- | 78.7
1996 | -- | -- | -- | -- | -- | -- | 64.6
1997 | -- | -- | -- | -- | -- | -- | 195.6
1998 | -- | -- | -- | -- | -- | -- | 360.4
1999 | -- | -- | -- | -- | -- | -- | 378.9
2000 | -- | -- | -- | -- | -- | -- | 191.7
2001 | -- | -- | -- | -- | -- | -- | 274.3
2002 | -- | -- | -- | -- | -- | -- | 366.8
2003 | -- | -- | -- | -- | -- | -- | 1090.1
2004 | -- | -- | -- | -- | -- | -- | 1548.2
2005 | -- | -- | -- | -- | -- | -- | 1510.3
2006 | -- | -- | -- | -- | -- | -- | 1657.3
2007 | -- | -- | -- | -- | -- | -- | 1470.7
2008 | -- | -- | -- | -- | -- | -- | 1285
2009 | -- | -- | -- | -- | -- | -- | 1271.2
2010 | -- | -- | -- | -- | -- | -- | 1440.5
2011 | -- | -- | -- | -- | -- | -- | 987.9
2012 | -- | -- | -- | -- | -- | -- | 960.1
2013 | -- | -- | -- | -- | -- | -- | 1081.5
2014 | -- | -- | -- | -- | -- | -- | 683.6
2015 | -- | -- | -- | -- | -- | -- | 773.2
2016 | -- | -- | -- | -- | -- | -- | 832.5
2017 | -- | -- | -- | -- | -- | -- | 969.3
2018 | -- | -- | -- | -- | -- | -- | 132.2
2019 | -- | -- | -- | -- | -- | -- | 9.6
2020 | -- | -- | -- | -- | -- | -- | 5.8
2021 | -- | -- | -- | -- | -- | -- | 3.9
Subtotal | 9 | -- | -- | -- | -- | -- | 19647.6
Annual Funding BY 2012 $M, RDT&E, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1994 | -- | -- | -- | -- | -- | -- | 31.9
1995 | -- | -- | -- | -- | -- | -- | 103.9
1996 | -- | -- | -- | -- | -- | -- | 83.9
1997 | -- | -- | -- | -- | -- | -- | 250.9
1998 | -- | -- | -- | -- | -- | -- | 458.6
1999 | -- | -- | -- | -- | -- | -- | 476.5
2000 | -- | -- | -- | -- | -- | -- | 237.6
2001 | -- | -- | -- | -- | -- | -- | 335.4
2002 | -- | -- | -- | -- | -- | -- | 444
2003 | -- | -- | -- | -- | -- | -- | 1300.4
2004 | -- | -- | -- | -- | -- | -- | 1796.8
2005 | -- | -- | -- | -- | -- | -- | 1707.8
2006 | -- | -- | -- | -- | -- | -- | 1817.4
2007 | -- | -- | -- | -- | -- | -- | 1574.3
2008 | -- | -- | -- | -- | -- | -- | 1350.8
2009 | -- | -- | -- | -- | -- | -- | 1319.4
2010 | -- | -- | -- | -- | -- | -- | 1473
2011 | -- | -- | -- | -- | -- | -- | 986.6
2012 | -- | -- | -- | -- | -- | -- | 943.2
2013 | -- | -- | -- | -- | -- | -- | 1051.5
2014 | -- | -- | -- | -- | -- | -- | 655.3
2015 | -- | -- | -- | -- | -- | -- | 731.9
2016 | -- | -- | -- | -- | -- | -- | 775.5
2017 | -- | -- | -- | -- | -- | -- | 886.7
2018 | -- | -- | -- | -- | -- | -- | 118.6
2019 | -- | -- | -- | -- | -- | -- | 8.4
2020 | -- | -- | -- | -- | -- | -- | 5
2021 | -- | -- | -- | -- | -- | -- | 3.3
Subtotal | 9 | -- | -- | -- | -- | -- | 20928.6
Annual Funding TY $M, RDT&E, F-35 Aircraft, Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1996 | -- | -- | -- | -- | -- | -- | 11.3
1997 | -- | -- | -- | -- | -- | -- | 67.1
1998 | -- | -- | -- | -- | -- | -- | 72.1
1999 | -- | -- | -- | -- | -- | -- | 49
2000 | -- | -- | -- | -- | -- | -- | 25.2
2001 | -- | -- | -- | -- | -- | -- | 9.5
2002 | -- | -- | -- | -- | -- | -- | 255.8
2003 | -- | -- | -- | -- | -- | -- | 298.7
2004 | -- | -- | -- | -- | -- | -- | 486.7
2005 | -- | -- | -- | -- | -- | -- | 734.8
2006 | -- | -- | -- | -- | -- | -- | 801.3
2007 | -- | -- | -- | -- | -- | -- | 635.4
2008 | -- | -- | -- | -- | -- | -- | 574
2009 | -- | -- | -- | -- | -- | -- | 236
2010 | -- | -- | -- | -- | -- | -- | 133.2
2011 | -- | -- | -- | -- | -- | -- | 171.3
2012 | -- | -- | -- | -- | -- | -- | 124.2
2013 | -- | -- | -- | -- | -- | -- | 148.5
2014 | -- | -- | -- | -- | -- | -- | 22
2015 | -- | -- | -- | -- | -- | -- | 15
2016 | -- | -- | -- | -- | -- | -- | 17
2017 | -- | -- | -- | -- | -- | -- | 22
2018 | -- | -- | -- | -- | -- | -- | 27.5
Subtotal | -- | -- | -- | -- | -- | -- | 4937.6
Annual Funding BY 2012 $M, RDT&E, F-35 Aircraft, Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1996 | -- | -- | -- | -- | -- | -- | 14.7
1997 | -- | -- | -- | -- | -- | -- | 86.1
1998 | -- | -- | -- | -- | -- | -- | 91.7
1999 | -- | -- | -- | -- | -- | -- | 61.6
2000 | -- | -- | -- | -- | -- | -- | 31.2
2001 | -- | -- | -- | -- | -- | -- | 11.6
2002 | -- | -- | -- | -- | -- | -- | 309.6
2003 | -- | -- | -- | -- | -- | -- | 356.3
2004 | -- | -- | -- | -- | -- | -- | 564.8
2005 | -- | -- | -- | -- | -- | -- | 830.9
2006 | -- | -- | -- | -- | -- | -- | 878.7
2007 | -- | -- | -- | -- | -- | -- | 680.1
2008 | -- | -- | -- | -- | -- | -- | 603.4
2009 | -- | -- | -- | -- | -- | -- | 244.9
2010 | -- | -- | -- | -- | -- | -- | 136.2
2011 | -- | -- | -- | -- | -- | -- | 171.1
2012 | -- | -- | -- | -- | -- | -- | 122
2013 | -- | -- | -- | -- | -- | -- | 144.4
2014 | -- | -- | -- | -- | -- | -- | 21.1
2015 | -- | -- | -- | -- | -- | -- | 14.2
2016 | -- | -- | -- | -- | -- | -- | 15.8
2017 | -- | -- | -- | -- | -- | -- | 20.1
2018 | -- | -- | -- | -- | -- | -- | 24.7
Subtotal | -- | -- | -- | -- | -- | -- | 5435.2
Annual Funding TY $M, Procurement, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
2006 | -- | 107.6 | -- | -- | 107.6 | -- | 107.6
2007 | 2 | 428.5 | -- | 80.8 | 509.3 | 91.1 | 600.4
2008 | 6 | 983.1 | -- | 172.3 | 1155.4 | 131.5 | 1286.9
2009 | 7 | 1009.2 | -- | 277.6 | 1286.8 | 175.8 | 1462.6
2010 | 10 | 1471.2 | -- | 355.7 | 1826.9 | 277.7 | 2104.6
2011 | 22 | 2751.2 | -- | 569.1 | 3320.3 | 679.6 | 3999.9
2012 | 18 | 2041.5 | -- | 375.7 | 2417.2 | 773 | 3190.2
2013 | 19 | 2074.6 | -- | 76.6 | 2151.2 | 528.9 | 2680.1
2014 | 19 | 2034.6 | -- | 617.8 | 2652.4 | 433 | 3085.4
2015 | 28 | 2715.8 | -- | 625 | 3340.8 | 605 | 3945.8
2016 | 47 | 4076 | -- | 561.5 | 4637.5 | 626.3 | 5263.8
2017 | 43 | 3339.3 | -- | 649.7 | 3989 | 488.5 | 4477.5
2018 | 44 | 3584 | -- | 1070.4 | 4654.4 | 559.4 | 5213.8
2019 | 48 | 3247.9 | -- | 1079.3 | 4327.2 | 566.2 | 4893.4
2020 | 48 | 3473.2 | -- | 886.9 | 4360.1 | 638 | 4998.1
2021 | 60 | 4300.8 | -- | 709.3 | 5010.1 | 802.1 | 5812.2
2022 | 80 | 6091.5 | -- | 640.6 | 6732.1 | 748.4 | 7480.5
2023 | 80 | 5332.8 | -- | 609.7 | 5942.5 | 648.7 | 6591.2
2024 | 80 | 5462 | -- | 620.7 | 6082.7 | 717.2 | 6799.9
2025 | 80 | 6101.5 | -- | 634.5 | 6736 | 605.3 | 7341.3
2026 | 80 | 6961.8 | -- | 647.4 | 7609.2 | 818.1 | 8427.3
2027 | 80 | 6472.7 | -- | 598.4 | 7071.1 | 648.5 | 7719.6
2028 | 80 | 5901.4 | -- | 607.9 | 6509.3 | 599.3 | 7108.6
2029 | 80 | 5990.1 | -- | 616.6 | 6606.7 | 487.4 | 7094.1
2030 | 80 | 6622.5 | -- | 634 | 7256.5 | 547 | 7803.5
2031 | 80 | 7570.5 | -- | 649.8 | 8220.3 | 699.2 | 8919.5
2032 | 80 | 7465 | -- | 676.1 | 8141.1 | 645.3 | 8786.4
2033 | 80 | 6998 | -- | 694.7 | 7692.7 | 571.2 | 8263.9
2034 | 80 | 7179.5 | -- | 698.4 | 7877.9 | 75.3 | 7953.2
2035 | 80 | 7878.9 | -- | 711.8 | 8590.7 | 32.9 | 8623.6
2036 | 80 | 8035 | -- | 722.5 | 8757.5 | 29.1 | 8786.6
2037 | 80 | 8150 | -- | 676.7 | 8826.7 | 20.7 | 8847.4
2038 | 62 | 6604.9 | -- | 552.2 | 7157.1 | 6.2 | 7163.3
Subtotal | 1763 | 152456.6 | -- | 19099.7 | 171556.3 | 15275.9 | 186832.2
Annual Funding BY 2012 $M, Procurement, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
2006 | -- | 116.8 | -- | -- | 116.8 | -- | 116.8
2007 | 2 | 452.5 | -- | 85.4 | 537.9 | 96.2 | 634.1
2008 | 6 | 1022.9 | -- | 179.3 | 1202.2 | 136.8 | 1339
2009 | 7 | 1035.7 | -- | 284.7 | 1320.4 | 180.5 | 1500.9
2010 | 10 | 1478.8 | -- | 357.6 | 1836.4 | 279.1 | 2115.5
2011 | 22 | 2711.7 | -- | 561 | 3272.7 | 669.8 | 3942.5
2012 | 18 | 1983.8 | -- | 365.1 | 2348.9 | 751.1 | 3100
2013 | 19 | 1994.5 | -- | 73.6 | 2068.1 | 508.5 | 2576.6
2014 | 19 | 1930.9 | -- | 586.3 | 2517.2 | 411 | 2928.2
2015 | 28 | 2539.2 | -- | 584.4 | 3123.6 | 565.6 | 3689.2
2016 | 47 | 3746.2 | -- | 516.1 | 4262.3 | 575.6 | 4837.9
2017 | 43 | 3011.8 | -- | 586 | 3597.8 | 440.6 | 4038.4
2018 | 44 | 3170.3 | -- | 946.7 | 4117 | 494.9 | 4611.9
2019 | 48 | 2816.6 | -- | 936.1 | 3752.7 | 491 | 4243.7
2020 | 48 | 2953 | -- | 754.1 | 3707.1 | 542.4 | 4249.5
2021 | 60 | 3584.9 | -- | 591.2 | 4176.1 | 668.6 | 4844.7
2022 | 80 | 4978 | -- | 523.5 | 5501.5 | 611.6 | 6113.1
2023 | 80 | 4272.5 | -- | 488.5 | 4761 | 519.7 | 5280.7
2024 | 80 | 4290.2 | -- | 487.6 | 4777.8 | 563.3 | 5341.1
2025 | 80 | 4698.6 | -- | 488.6 | 5187.2 | 466.1 | 5653.3
2026 | 80 | 5255.9 | -- | 488.7 | 5744.6 | 617.7 | 6362.3
2027 | 80 | 4790.9 | -- | 442.9 | 5233.8 | 480 | 5713.8
2028 | 80 | 4282.4 | -- | 441.2 | 4723.6 | 434.8 | 5158.4
2029 | 80 | 4261.5 | -- | 438.6 | 4700.1 | 346.8 | 5046.9
2030 | 80 | 4619 | -- | 442.2 | 5061.2 | 381.5 | 5442.7
2031 | 80 | 5176.7 | -- | 444.3 | 5621 | 478.1 | 6099.1
2032 | 80 | 5004.5 | -- | 453.2 | 5457.7 | 432.6 | 5890.3
2033 | 80 | 4599.4 | -- | 456.6 | 5056 | 375.4 | 5431.4
2034 | 80 | 4626.2 | -- | 450 | 5076.2 | 48.5 | 5124.7
2035 | 80 | 4935.2 | -- | 445.8 | 5381 | 20.6 | 5401.6
2036 | 80 | 4934.3 | -- | 443.6 | 5377.9 | 17.9 | 5395.8
2037 | 80 | 4906.7 | -- | 407.4 | 5314.1 | 12.5 | 5326.6
2038 | 62 | 3898.5 | -- | 325.9 | 4224.4 | 3.7 | 4228.1
Subtotal | 1763 | 114080.1 | -- | 15076.2 | 129156.3 | 12622.5 | 141778.8
Cost Quantity Information, Procurement, F-35 Aircraft, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2012 $M
2006 | -- | --
2007 | 2 | 452.5
2008 | 6 | 1022.9
2009 | 7 | 1035.7
2010 | 10 | 1478.8
2011 | 22 | 2711.7
2012 | 18 | 1983.8
2013 | 19 | 1994.5
2014 | 19 | 1930.9
2015 | 28 | 2539.2
2016 | 47 | 3746.2
2017 | 43 | 3011.8
2018 | 44 | 3170.3
2019 | 48 | 2816.6
2020 | 48 | 2953
2021 | 60 | 3584.9
2022 | 80 | 4978
2023 | 80 | 4272.5
2024 | 80 | 4290.2
2025 | 80 | 4698.6
2026 | 80 | 5255.9
2027 | 80 | 4790.9
2028 | 80 | 4282.4
2029 | 80 | 4261.5
2030 | 80 | 4619
2031 | 80 | 5176.7
2032 | 80 | 5004.5
2033 | 80 | 4599.4
2034 | 80 | 4626.2
2035 | 80 | 4935.2
2036 | 80 | 4934.3
2037 | 80 | 4906.7
2038 | 62 | 4015.3
Subtotal | 1763 | 114080.1
Annual Funding TY $M, Procurement, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
2007 | -- | 96.9 | -- | -- | 96.9 | -- | 96.9
2008 | 6 | 923.2 | -- | 38.6 | 961.8 | 10.7 | 972.5
2009 | 7 | 1062 | -- | 182 | 1244 | 206.1 | 1450.1
2010 | 20 | 2681.2 | -- | 305.4 | 2986.6 | 560.9 | 3547.5
2011 | 10 | 1494.8 | -- | 251 | 1745.8 | 431.8 | 2177.6
2012 | 13 | 1477.7 | -- | 330.2 | 1807.9 | 746.7 | 2554.6
2013 | 10 | 1107.3 | -- | 44.1 | 1151.4 | 557.3 | 1708.7
2014 | 10 | 1205.5 | -- | 406.3 | 1611.8 | 642.3 | 2254.1
2015 | 10 | 1115 | -- | 650.9 | 1765.9 | 414.1 | 2180
2016 | 21 | 2130.3 | -- | 601.9 | 2732.2 | 629.9 | 3362.1
2017 | 20 | 1867.2 | -- | 422.9 | 2290.1 | 426.8 | 2716.9
2018 | 26 | 2555.1 | -- | 668.2 | 3223.3 | 346.9 | 3570.2
2019 | 32 | 2648.5 | -- | 603.2 | 3251.7 | 482.6 | 3734.3
2020 | 38 | 3242.8 | -- | 501.5 | 3744.3 | 624.3 | 4368.6
2021 | 45 | 3731.8 | -- | 535.4 | 4267.2 | 786.8 | 5054
2022 | 45 | 4015.2 | -- | 396.9 | 4412.1 | 644.6 | 5056.7
2023 | 45 | 3511.2 | -- | 377.5 | 3888.7 | 533.7 | 4422.4
2024 | 45 | 3566.7 | -- | 368 | 3934.7 | 490.6 | 4425.3
2025 | 45 | 3896.6 | -- | 377.9 | 4274.5 | 400.8 | 4675.3
2026 | 45 | 4396.8 | -- | 381.4 | 4778.2 | 441.8 | 5220
2027 | 45 | 4131.9 | -- | 358.6 | 4490.5 | 335.6 | 4826.1
2028 | 45 | 3834.2 | -- | 364 | 4198.2 | 369 | 4567.2
2029 | 45 | 3721.1 | -- | 356.9 | 4078 | 260.7 | 4338.7
2030 | 28 | 2685.4 | -- | 373.5 | 3058.9 | 388.6 | 3447.5
2031 | 24 | 2180.2 | -- | 326.5 | 2506.7 | 361.3 | 2868
Subtotal | 680 | 63278.6 | -- | 9222.8 | 72501.4 | 11093.9 | 83595.3
Annual Funding BY 2012 $M, Procurement, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
2007 | -- | 102.3 | -- | -- | 102.3 | -- | 102.3
2008 | 6 | 960.6 | -- | 40.2 | 1000.8 | 11.1 | 1011.9
2009 | 7 | 1089.8 | -- | 186.8 | 1276.6 | 211.5 | 1488.1
2010 | 20 | 2695.1 | -- | 307 | 3002.1 | 563.8 | 3565.9
2011 | 10 | 1473.3 | -- | 247.4 | 1720.7 | 425.6 | 2146.3
2012 | 13 | 1435.9 | -- | 320.9 | 1756.8 | 725.6 | 2482.4
2013 | 10 | 1064.5 | -- | 42.4 | 1106.9 | 535.8 | 1642.7
2014 | 10 | 1144.1 | -- | 385.6 | 1529.7 | 609.5 | 2139.2
2015 | 10 | 1042.5 | -- | 608.5 | 1651 | 387.2 | 2038.2
2016 | 21 | 1957.9 | -- | 553.2 | 2511.1 | 578.9 | 3090
2017 | 20 | 1684.1 | -- | 381.4 | 2065.5 | 385 | 2450.5
2018 | 26 | 2260.2 | -- | 591 | 2851.2 | 306.9 | 3158.1
2019 | 32 | 2296.8 | -- | 523.2 | 2820 | 418.5 | 3238.5
2020 | 38 | 2757.1 | -- | 426.4 | 3183.5 | 530.8 | 3714.3
2021 | 45 | 3110.6 | -- | 446.3 | 3556.9 | 655.8 | 4212.7
2022 | 45 | 3281.2 | -- | 324.3 | 3605.5 | 526.8 | 4132.3
2023 | 45 | 2813.1 | -- | 302.4 | 3115.5 | 427.6 | 3543.1
2024 | 45 | 2801.5 | -- | 289.1 | 3090.6 | 385.3 | 3475.9
2025 | 45 | 3000.6 | -- | 291.1 | 3291.7 | 308.6 | 3600.3
2026 | 45 | 3319.4 | -- | 287.9 | 3607.3 | 333.6 | 3940.9
2027 | 45 | 3058.3 | -- | 265.4 | 3323.7 | 248.4 | 3572.1
2028 | 45 | 2782.3 | -- | 264.2 | 3046.5 | 267.7 | 3314.2
2029 | 45 | 2647.3 | -- | 253.8 | 2901.1 | 185.5 | 3086.6
2030 | 28 | 1873 | -- | 260.4 | 2133.4 | 271.1 | 2404.5
2031 | 24 | 1490.8 | -- | 223.3 | 1714.1 | 247 | 1961.1
Subtotal | 680 | 52142.3 | -- | 7822.2 | 59964.5 | 9547.6 | 69512.1
Cost Quantity Information, Procurement, F-35 Aircraft, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2012 $M
2007 | -- | --
2008 | 6 | 960.6
2009 | 7 | 1089.8
2010 | 20 | 2695.1
2011 | 10 | 1473.3
2012 | 13 | 1435.9
2013 | 10 | 1064.5
2014 | 10 | 1144.1
2015 | 10 | 1042.5
2016 | 21 | 1957.9
2017 | 20 | 1684.1
2018 | 26 | 2260.2
2019 | 32 | 2296.8
2020 | 38 | 2757.1
2021 | 45 | 3110.6
2022 | 45 | 3281.2
2023 | 45 | 2813.1
2024 | 45 | 2801.5
2025 | 45 | 3000.6
2026 | 45 | 3319.4
2027 | 45 | 3058.3
2028 | 45 | 2782.3
2029 | 45 | 2647.3
2030 | 28 | 1873
2031 | 24 | 1593.1
Subtotal | 680 | 52142.3
Annual Funding TY $M, F-35 Aircraft, Military Construction, Navy and Marine Corps
Fiscal Year | Total Program TY $M
2004 | 24.4
2005 | --
2006 | 0.1
2007 | --
2008 | 0.2
2009 | 0.7
2010 | 34.1
2011 | 377.9
2012 | 172.2
2013 | 94.9
2014 | --
2015 | 131.9
2016 | 94.4
2017 | 230.9
2018 | 64.7
2019 | 122
2020 | 119.8
2021 | 116.2
2022 | 75.9
2023 | 101.3
2024 | 145
2025 | --
2026 | 61.9
2027 | 75
2028 | 65.1
2029 | 2
Subtotal | 2110.6
Annual Funding BY 2012 $M, F-35 Aircraft, Military Construction, Navy and Marine Corps
Fiscal Year | Total Program BY 2012 $M
2004 | 27.8
2005 | --
2006 | 0.1
2007 | --
2008 | 0.2
2009 | 0.7
2010 | 34.1
2011 | 368.9
2012 | 165.9
2013 | 90.2
2014 | --
2015 | 121.5
2016 | 85.4
2017 | 204.9
2018 | 56.3
2019 | 104
2020 | 100.2
2021 | 95.2
2022 | 61
2023 | 79.8
2024 | 112
2025 | --
2026 | 46
2027 | 54.6
2028 | 46.5
2029 | 1.4
Subtotal | 1857.1
Annual Funding TY $M, F-35 Aircraft, Military Construction, Air Force
Fiscal Year | Total Program TY $M
2004 | 1.7
2005 | 10
2006 | --
2007 | --
2008 | 100.3
2009 | 116
2010 | 125.1
2011 | 139.6
2012 | 24.3
2013 | 13.5
2014 | 56
2015 | 66.7
2016 | 198.3
2017 | 340.8
2018 | 101
2019 | 61.5
2020 | 15.9
2021 | --
2022 | 123.7
2023 | 167
2024 | 142.3
2025 | 122.1
2026 | 118.4
2027 | 129.9
2028 | 101.8
2029 | 102.7
2030 | 94.6
2031 | 71.7
2032 | 71.2
2033 | 37.5
2034 | 24.8
2035 | 4.3
Subtotal | 2682.7
Annual Funding BY 2012 $M, F-35 Aircraft, Military Construction, Air Force
Fiscal Year | Total Program BY 2012 $M
2004 | 1.9
2005 | 11.1
2006 | --
2007 | --
2008 | 104.1
2009 | 118.8
2010 | 125
2011 | 136.4
2012 | 23.4
2013 | 12.8
2014 | 52.5
2015 | 61.5
2016 | 179.4
2017 | 302.4
2018 | 87.9
2019 | 52.4
2020 | 13.3
2021 | --
2022 | 99.4
2023 | 131.6
2024 | 109.9
2025 | 92.5
2026 | 87.9
2027 | 94.5
2028 | 72.6
2029 | 71.8
2030 | 64.4
2031 | 47.9
2032 | 46.6
2033 | 24
2034 | 15.6
2035 | 2.7
Subtotal | 2244.3
Annual Funding TY $M, RDT&E, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1995 | -- | -- | -- | -- | -- | -- | 16.4
1996 | -- | -- | -- | -- | -- | -- | 15.9
1997 | -- | -- | -- | -- | -- | -- | 49.3
1998 | -- | -- | -- | -- | -- | -- | 87.1
1999 | -- | -- | -- | -- | -- | -- | 89.4
2000 | -- | -- | -- | -- | -- | -- | 48.8
2001 | -- | -- | -- | -- | -- | -- | 66.9
2002 | -- | -- | -- | -- | -- | -- | 409.8
2003 | -- | -- | -- | -- | -- | -- | 400.5
2004 | -- | -- | -- | -- | -- | -- | 435.8
2005 | -- | -- | -- | -- | -- | -- | 614.3
2006 | -- | -- | -- | -- | -- | -- | 586.3
2007 | -- | -- | -- | -- | -- | -- | 441.6
2008 | -- | -- | -- | -- | -- | -- | 596
2009 | -- | -- | -- | -- | -- | -- | 544.6
2010 | -- | -- | -- | -- | -- | -- | 466.1
2011 | -- | -- | -- | -- | -- | -- | 216.2
2012 | -- | -- | -- | -- | -- | -- | 101.8
2013 | -- | -- | -- | -- | -- | -- | 143.6
2014 | -- | -- | -- | -- | -- | -- | 52
2015 | -- | -- | -- | -- | -- | -- | 54.5
2016 | -- | -- | -- | -- | -- | -- | 58.4
2017 | -- | -- | -- | -- | -- | -- | 14.5
Subtotal | 5 | -- | -- | -- | -- | -- | 5509.8
Annual Funding BY 2012 $M, RDT&E, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1995 | -- | -- | -- | -- | -- | -- | 21.7
1996 | -- | -- | -- | -- | -- | -- | 20.6
1997 | -- | -- | -- | -- | -- | -- | 63.2
1998 | -- | -- | -- | -- | -- | -- | 110.8
1999 | -- | -- | -- | -- | -- | -- | 112.4
2000 | -- | -- | -- | -- | -- | -- | 60.5
2001 | -- | -- | -- | -- | -- | -- | 81.8
2002 | -- | -- | -- | -- | -- | -- | 496
2003 | -- | -- | -- | -- | -- | -- | 477.8
2004 | -- | -- | -- | -- | -- | -- | 505.8
2005 | -- | -- | -- | -- | -- | -- | 694.7
2006 | -- | -- | -- | -- | -- | -- | 643
2007 | -- | -- | -- | -- | -- | -- | 472.7
2008 | -- | -- | -- | -- | -- | -- | 626.5
2009 | -- | -- | -- | -- | -- | -- | 565.2
2010 | -- | -- | -- | -- | -- | -- | 476.6
2011 | -- | -- | -- | -- | -- | -- | 215.9
2012 | -- | -- | -- | -- | -- | -- | 100
2013 | -- | -- | -- | -- | -- | -- | 139.6
2014 | -- | -- | -- | -- | -- | -- | 49.8
2015 | -- | -- | -- | -- | -- | -- | 51.6
2016 | -- | -- | -- | -- | -- | -- | 54.4
2017 | -- | -- | -- | -- | -- | -- | 13.3
Subtotal | 5 | -- | -- | -- | -- | -- | 6053.9
Annual Funding TY $M, RDT&E, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1994 | -- | -- | -- | -- | -- | -- | 5.8
1995 | -- | -- | -- | -- | -- | -- | 19.3
1996 | -- | -- | -- | -- | -- | -- | 15.8
1997 | -- | -- | -- | -- | -- | -- | 47.7
1998 | -- | -- | -- | -- | -- | -- | 87.8
1999 | -- | -- | -- | -- | -- | -- | 92.4
2000 | -- | -- | -- | -- | -- | -- | 46.7
2001 | -- | -- | -- | -- | -- | -- | 66.9
2002 | -- | -- | -- | -- | -- | -- | 350.4
2003 | -- | -- | -- | -- | -- | -- | 550.8
2004 | -- | -- | -- | -- | -- | -- | 533.2
2005 | -- | -- | -- | -- | -- | -- | 573.5
2006 | -- | -- | -- | -- | -- | -- | 528.1
2007 | -- | -- | -- | -- | -- | -- | 639.1
2008 | -- | -- | -- | -- | -- | -- | 563.9
2009 | -- | -- | -- | -- | -- | -- | 433.1
2010 | -- | -- | -- | -- | -- | -- | 445.7
2011 | -- | -- | -- | -- | -- | -- | 252.9
2012 | -- | -- | -- | -- | -- | -- | 187.6
2013 | -- | -- | -- | -- | -- | -- | 199.2
2014 | -- | -- | -- | -- | -- | -- | 116.1
2015 | -- | -- | -- | -- | -- | -- | 173.7
2016 | -- | -- | -- | -- | -- | -- | 141.2
2017 | -- | -- | -- | -- | -- | -- | 42.1
Subtotal | 9 | -- | -- | -- | -- | -- | 6113
Annual Funding BY 2012 $M, RDT&E, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1994 | -- | -- | -- | -- | -- | -- | 7.8
1995 | -- | -- | -- | -- | -- | -- | 25.5
1996 | -- | -- | -- | -- | -- | -- | 20.5
1997 | -- | -- | -- | -- | -- | -- | 61.2
1998 | -- | -- | -- | -- | -- | -- | 111.7
1999 | -- | -- | -- | -- | -- | -- | 116.2
2000 | -- | -- | -- | -- | -- | -- | 57.9
2001 | -- | -- | -- | -- | -- | -- | 81.8
2002 | -- | -- | -- | -- | -- | -- | 424.1
2003 | -- | -- | -- | -- | -- | -- | 657.1
2004 | -- | -- | -- | -- | -- | -- | 618.8
2005 | -- | -- | -- | -- | -- | -- | 648.5
2006 | -- | -- | -- | -- | -- | -- | 579.1
2007 | -- | -- | -- | -- | -- | -- | 684.1
2008 | -- | -- | -- | -- | -- | -- | 592.8
2009 | -- | -- | -- | -- | -- | -- | 449.5
2010 | -- | -- | -- | -- | -- | -- | 455.8
2011 | -- | -- | -- | -- | -- | -- | 252.6
2012 | -- | -- | -- | -- | -- | -- | 184.3
2013 | -- | -- | -- | -- | -- | -- | 193.7
2014 | -- | -- | -- | -- | -- | -- | 111.3
2015 | -- | -- | -- | -- | -- | -- | 164.4
2016 | -- | -- | -- | -- | -- | -- | 131.5
2017 | -- | -- | -- | -- | -- | -- | 38.5
Subtotal | 9 | -- | -- | -- | -- | -- | 6668.7
Annual Funding TY $M, RDT&E, F-35 Engine, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1994 | -- | -- | -- | -- | -- | -- | 5.7
1995 | -- | -- | -- | -- | -- | -- | 13.4
1996 | -- | -- | -- | -- | -- | -- | 4
Subtotal | -- | -- | -- | -- | -- | -- | 23.1
Annual Funding BY 2012 $M, RDT&E, F-35 Engine, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1994 | -- | -- | -- | -- | -- | -- | 7.7
1995 | -- | -- | -- | -- | -- | -- | 17.7
1996 | -- | -- | -- | -- | -- | -- | 5.2
Subtotal | -- | -- | -- | -- | -- | -- | 30.6
Annual Funding TY $M, RDT&E, F-35 Engine, Non-Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1996 | -- | -- | -- | -- | -- | -- | 2.7
1997 | -- | -- | -- | -- | -- | -- | 3.9
1998 | -- | -- | -- | -- | -- | -- | 5.1
1999 | -- | -- | -- | -- | -- | -- | 5.7
2000 | -- | -- | -- | -- | -- | -- | 1.8
2001 | -- | -- | -- | -- | -- | -- | 0.5
2002 | -- | -- | -- | -- | -- | -- | 43.3
2003 | -- | -- | -- | -- | -- | -- | 124.3
2004 | -- | -- | -- | -- | -- | -- | 54.1
2005 | -- | -- | -- | -- | -- | -- | 0.3
2006 | -- | -- | -- | -- | -- | -- | --
2007 | -- | -- | -- | -- | -- | -- | 75
2008 | -- | -- | -- | -- | -- | -- | --
2009 | -- | -- | -- | -- | -- | -- | --
2010 | -- | -- | -- | -- | -- | -- | --
2011 | -- | -- | -- | -- | -- | -- | --
2012 | -- | -- | -- | -- | -- | -- | --
2013 | -- | -- | -- | -- | -- | -- | 0.3
Subtotal | -- | -- | -- | -- | -- | -- | 317
Annual Funding BY 2012 $M, RDT&E, F-35 Engine, Non-Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
1996 | -- | -- | -- | -- | -- | -- | 3.5
1997 | -- | -- | -- | -- | -- | -- | 5
1998 | -- | -- | -- | -- | -- | -- | 6.5
1999 | -- | -- | -- | -- | -- | -- | 7.2
2000 | -- | -- | -- | -- | -- | -- | 2.2
2001 | -- | -- | -- | -- | -- | -- | 0.6
2002 | -- | -- | -- | -- | -- | -- | 52.4
2003 | -- | -- | -- | -- | -- | -- | 148.3
2004 | -- | -- | -- | -- | -- | -- | 62.8
2005 | -- | -- | -- | -- | -- | -- | 0.3
2006 | -- | -- | -- | -- | -- | -- | --
2007 | -- | -- | -- | -- | -- | -- | 80.3
2008 | -- | -- | -- | -- | -- | -- | --
2009 | -- | -- | -- | -- | -- | -- | --
2010 | -- | -- | -- | -- | -- | -- | --
2011 | -- | -- | -- | -- | -- | -- | --
2012 | -- | -- | -- | -- | -- | -- | --
2013 | -- | -- | -- | -- | -- | -- | 0.3
Subtotal | -- | -- | -- | -- | -- | -- | 369.4
Annual Funding TY $M, Procurement, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
2006 | -- | 9.8 | -- | -- | 9.8 | -- | 9.8
2007 | 2 | 47.5 | -- | 6.9 | 54.4 | 27.7 | 82.1
2008 | 6 | 123.6 | -- | 35 | 158.6 | 30.9 | 189.5
2009 | 7 | 127 | -- | 63.9 | 190.9 | 33.3 | 224.2
2010 | 10 | 176.7 | -- | 72.6 | 249.3 | 59.1 | 308.4
2011 | 22 | 353.2 | -- | 91.6 | 444.8 | 136.6 | 581.4
2012 | 18 | 275.3 | -- | 65.7 | 341 | 123 | 464
2013 | 19 | 262.5 | -- | 11.9 | 274.4 | 89.6 | 364
2014 | 19 | 282.1 | -- | 31.2 | 313.3 | 47.5 | 360.8
2015 | 28 | 386.7 | -- | 15.5 | 402.2 | 116.2 | 518.4
2016 | 47 | 606.1 | -- | 23.2 | 629.3 | 126.7 | 756
2017 | 43 | 606.7 | -- | 48.9 | 655.6 | 116.7 | 772.3
2018 | 44 | 651.2 | -- | 80.6 | 731.8 | 135.8 | 867.6
2019 | 48 | 590.1 | -- | 81.2 | 671.3 | 145.4 | 816.7
2020 | 48 | 631.1 | -- | 66.8 | 697.9 | 153.6 | 851.5
2021 | 60 | 781.4 | -- | 53.4 | 834.8 | 172.1 | 1006.9
2022 | 80 | 1066.3 | -- | 48.2 | 1114.5 | 178.5 | 1293
2023 | 80 | 976.1 | -- | 45.9 | 1022 | 189.3 | 1211.3
2024 | 80 | 997.2 | -- | 46.7 | 1043.9 | 177.6 | 1221.5
2025 | 80 | 1094.6 | -- | 47.8 | 1142.4 | 184.4 | 1326.8
2026 | 80 | 1123.6 | -- | 48.7 | 1172.3 | 218.3 | 1390.6
2027 | 80 | 1068 | -- | 45 | 1113 | 135.7 | 1248.7
2028 | 80 | 977.9 | -- | 45.8 | 1023.7 | 130.3 | 1154
2029 | 80 | 996.6 | -- | 46.4 | 1043 | 119 | 1162
2030 | 80 | 1091.1 | -- | 47.7 | 1138.8 | 122.4 | 1261.2
2031 | 80 | 1237.8 | -- | 48.9 | 1286.7 | 153.9 | 1440.6
2032 | 80 | 1185.7 | -- | 50.9 | 1236.6 | 143 | 1379.6
2033 | 80 | 1090.4 | -- | 52.3 | 1142.7 | 137.1 | 1279.8
2034 | 80 | 1110.8 | -- | 52.6 | 1163.4 | 18.8 | 1182.2
2035 | 80 | 1219.4 | -- | 53.6 | 1273 | 3.7 | 1276.7
2036 | 80 | 1241.5 | -- | 54.4 | 1295.9 | 3.2 | 1299.1
2037 | 80 | 1243.9 | -- | 50.9 | 1294.8 | 2.3 | 1297.1
2038 | 62 | 902.2 | -- | 41.6 | 943.8 | 0.5 | 944.3
Subtotal | 1763 | 24534.1 | -- | 1575.8 | 26109.9 | 3432.2 | 29542.1
Annual Funding BY 2012 $M, Procurement, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
2006 | -- | 10.6 | -- | -- | 10.6 | -- | 10.6
2007 | 2 | 50.2 | -- | 7.3 | 57.5 | 29.2 | 86.7
2008 | 6 | 128.6 | -- | 36.4 | 165 | 32.2 | 197.2
2009 | 7 | 130.3 | -- | 65.6 | 195.9 | 34.2 | 230.1
2010 | 10 | 177.6 | -- | 73 | 250.6 | 59.4 | 310
2011 | 22 | 348.1 | -- | 90.3 | 438.4 | 134.7 | 573.1
2012 | 18 | 267.5 | -- | 63.8 | 331.3 | 119.6 | 450.9
2013 | 19 | 252.4 | -- | 11.4 | 263.8 | 86.1 | 349.9
2014 | 19 | 267.7 | -- | 29.6 | 297.3 | 45.1 | 342.4
2015 | 28 | 361.6 | -- | 14.5 | 376.1 | 108.6 | 484.7
2016 | 47 | 557.1 | -- | 21.3 | 578.4 | 116.4 | 694.8
2017 | 43 | 547.2 | -- | 44.1 | 591.3 | 105.3 | 696.6
2018 | 44 | 576 | -- | 71.3 | 647.3 | 120.1 | 767.4
2019 | 48 | 511.7 | -- | 70.4 | 582.1 | 126.2 | 708.3
2020 | 48 | 536.6 | -- | 56.8 | 593.4 | 130.6 | 724
2021 | 60 | 651.3 | -- | 44.5 | 695.8 | 143.5 | 839.3
2022 | 80 | 871.4 | -- | 39.4 | 910.8 | 145.8 | 1056.6
2023 | 80 | 782 | -- | 36.8 | 818.8 | 151.7 | 970.5
2024 | 80 | 783.3 | -- | 36.7 | 820 | 139.4 | 959.4
2025 | 80 | 842.9 | -- | 36.8 | 879.7 | 142 | 1021.7
2026 | 80 | 848.3 | -- | 36.8 | 885.1 | 164.8 | 1049.9
2027 | 80 | 790.5 | -- | 33.3 | 823.8 | 100.4 | 924.2
2028 | 80 | 709.6 | -- | 33.2 | 742.8 | 94.6 | 837.4
2029 | 80 | 709 | -- | 33 | 742 | 84.7 | 826.7
2030 | 80 | 761 | -- | 33.3 | 794.3 | 85.4 | 879.7
2031 | 80 | 846.4 | -- | 33.4 | 879.8 | 105.3 | 985.1
2032 | 80 | 794.9 | -- | 34.1 | 829 | 95.9 | 924.9
2033 | 80 | 716.7 | -- | 34.4 | 751.1 | 90 | 841.1
2034 | 80 | 715.8 | -- | 33.9 | 749.7 | 12.1 | 761.8
2035 | 80 | 763.8 | -- | 33.6 | 797.4 | 2.3 | 799.7
2036 | 80 | 762.4 | -- | 33.4 | 795.8 | 2 | 797.8
2037 | 80 | 748.9 | -- | 30.6 | 779.5 | 1.4 | 780.9
2038 | 62 | 532.5 | -- | 24.6 | 557.1 | 0.3 | 557.4
Subtotal | 1763 | 18353.9 | -- | 1277.6 | 19631.5 | 2809.3 | 22440.8
Cost Quantity Information, Procurement, F-35 Engine, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2012 $M
2006 | -- | --
2007 | 2 | 50.2
2008 | 6 | 128.6
2009 | 7 | 130.3
2010 | 10 | 177.6
2011 | 22 | 348.1
2012 | 18 | 267.5
2013 | 19 | 252.4
2014 | 19 | 267.7
2015 | 28 | 361.6
2016 | 47 | 557.1
2017 | 43 | 547.2
2018 | 44 | 576
2019 | 48 | 511.7
2020 | 48 | 536.6
2021 | 60 | 651.3
2022 | 80 | 871.4
2023 | 80 | 782
2024 | 80 | 783.3
2025 | 80 | 842.9
2026 | 80 | 848.3
2027 | 80 | 790.5
2028 | 80 | 709.6
2029 | 80 | 709
2030 | 80 | 761
2031 | 80 | 846.4
2032 | 80 | 794.9
2033 | 80 | 716.7
2034 | 80 | 715.8
2035 | 80 | 763.8
2036 | 80 | 762.4
2037 | 80 | 748.9
2038 | 62 | 543.1
Subtotal | 1763 | 18353.9
Annual Funding TY $M, Procurement, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
2007 | -- | 27.4 | -- | -- | 27.4 | -- | 27.4
2008 | 6 | 246.1 | -- | 1.3 | 247.4 | 1.2 | 248.6
2009 | 7 | 298 | -- | 54.3 | 352.3 | 65.6 | 417.9
2010 | 20 | 599 | -- | 118.5 | 717.5 | 127.6 | 845.1
2011 | 10 | 400.5 | -- | 112.5 | 513 | 122.3 | 635.3
2012 | 13 | 191.4 | -- | 57.7 | 249.1 | 62 | 311.1
2013 | 10 | 236.9 | -- | 26.6 | 263.5 | 169.8 | 433.3
2014 | 10 | 227.1 | -- | 21.6 | 248.7 | 142.4 | 391.1
2015 | 10 | 259.5 | -- | 27.6 | 287.1 | 68 | 355.1
2016 | 21 | 362.7 | -- | 22.3 | 385 | 109.9 | 494.9
2017 | 20 | 568.4 | -- | 87.3 | 655.7 | 80.6 | 736.3
2018 | 26 | 742.3 | -- | 138 | 880.3 | 61.4 | 941.7
2019 | 32 | 750.5 | -- | 124.6 | 875.1 | 82.6 | 957.7
2020 | 38 | 840.1 | -- | 103.6 | 943.7 | 116.7 | 1060.4
2021 | 45 | 937.1 | -- | 110.6 | 1047.7 | 186.2 | 1233.9
2022 | 45 | 994.1 | -- | 82 | 1076.1 | 117.3 | 1193.4
2023 | 45 | 910.7 | -- | 76 | 986.7 | 117 | 1103.7
2024 | 45 | 926.6 | -- | 89.5 | 1016.1 | 93.2 | 1109.3
2025 | 45 | 1012.3 | -- | 85.4 | 1097.7 | 93.6 | 1191.3
2026 | 45 | 1006.6 | -- | 89.5 | 1096.1 | 104.3 | 1200.4
2027 | 45 | 970.3 | -- | 61.5 | 1031.8 | 82.5 | 1114.3
2028 | 45 | 910.7 | -- | 57.4 | 968.1 | 90.6 | 1058.7
2029 | 45 | 865.2 | -- | 60.8 | 926 | 67.5 | 993.5
2030 | 28 | 442.9 | -- | 71.8 | 514.7 | 95.9 | 610.6
2031 | 24 | 299 | -- | 78.5 | 377.5 | 103.6 | 481.1
Subtotal | 680 | 15025.4 | -- | 1758.9 | 16784.3 | 2361.8 | 19146.1
Annual Funding BY 2012 $M, Procurement, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway | Non End Item Recurring Flyaway | Non Recurring Flyaway | Total Flyaway | Total Support | Total Program
2007 | -- | 28.9 | -- | -- | 28.9 | -- | 28.9
2008 | 6 | 256.1 | -- | 1.4 | 257.5 | 1.2 | 258.7
2009 | 7 | 305.8 | -- | 55.8 | 361.6 | 67.3 | 428.9
2010 | 20 | 602.1 | -- | 119.2 | 721.3 | 128.2 | 849.5
2011 | 10 | 394.8 | -- | 110.8 | 505.6 | 120.6 | 626.2
2012 | 13 | 186 | -- | 56 | 242 | 60.3 | 302.3
2013 | 10 | 227.8 | -- | 25.6 | 253.4 | 163.2 | 416.6
2014 | 10 | 215.5 | -- | 20.5 | 236 | 135.2 | 371.2
2015 | 10 | 242.6 | -- | 25.8 | 268.4 | 63.6 | 332
2016 | 21 | 333.4 | -- | 20.5 | 353.9 | 101 | 454.9
2017 | 20 | 512.7 | -- | 78.7 | 591.4 | 72.7 | 664.1
2018 | 26 | 656.6 | -- | 122.1 | 778.7 | 54.3 | 833
2019 | 32 | 650.8 | -- | 108.1 | 758.9 | 71.6 | 830.5
2020 | 38 | 714.3 | -- | 88.1 | 802.4 | 99.2 | 901.6
2021 | 45 | 781.1 | -- | 92.2 | 873.3 | 155.2 | 1028.5
2022 | 45 | 812.4 | -- | 67 | 879.4 | 95.8 | 975.2
2023 | 45 | 729.6 | -- | 60.9 | 790.5 | 93.8 | 884.3
2024 | 45 | 727.8 | -- | 70.3 | 798.1 | 73.2 | 871.3
2025 | 45 | 779.5 | -- | 65.8 | 845.3 | 72.1 | 917.4
2026 | 45 | 759.9 | -- | 67.7 | 827.6 | 78.7 | 906.3
2027 | 45 | 718.2 | -- | 45.5 | 763.7 | 61.1 | 824.8
2028 | 45 | 660.9 | -- | 41.7 | 702.6 | 65.6 | 768.2
2029 | 45 | 615.5 | -- | 43.3 | 658.8 | 48 | 706.8
2030 | 28 | 308.9 | -- | 50.1 | 359 | 66.9 | 425.9
2031 | 24 | 204.5 | -- | 53.6 | 258.1 | 70.9 | 329
Subtotal | 680 | 12425.7 | -- | 1490.7 | 13916.4 | 2019.7 | 15936.1
Cost Quantity Information, Procurement, F-35 Engine, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2012 $M
2007 | -- | --
2008 | 6 | 256.1
2009 | 7 | 305.8
2010 | 20 | 602.1
2011 | 10 | 394.8
2012 | 13 | 186
2013 | 10 | 227.8
2014 | 10 | 215.5
2015 | 10 | 242.6
2016 | 21 | 333.4
2017 | 20 | 512.7
2018 | 26 | 656.6
2019 | 32 | 650.8
2020 | 38 | 714.3
2021 | 45 | 781.1
2022 | 45 | 812.4
2023 | 45 | 729.6
2024 | 45 | 727.8
2025 | 45 | 779.5
2026 | 45 | 759.9
2027 | 45 | 718.2
2028 | 45 | 660.9
2029 | 45 | 615.5
2030 | 28 | 308.9
2031 | 24 | 233.4
Subtotal | 680 | 12425.7

## Low Rate Initial Production
Low Rate Initial Production, F-35 Aircraft
| Initial LRIP Decision | Current Total LRIP
Approval Date | 2001-10-26 | 2015-05-23
Approved Quantity | 465 | 518
Reference | ADM | ADM
Start Year | 2006 | 2006
End Year | 2015 | 2019
Low Rate Initial Production, F-35 Engine
| Initial LRIP Decision | Current Total LRIP
Approval Date | 2001-10-26 | 2015-05-23
Approved Quantity | 465 | 518
Reference | ADM | ADM
Start Year | 2006 | 2006
End Year | 2015 | 2019

## Foreign Military Sales
Foreign Military Sales, F-35 Aircraft
Country | Date of Sale | Quantity | Total Cost $M | Memo
Japan | 2015-09-14 | 16 | 4360.4
Israel | 2015-02-15 | 33 | 5008
Korea | 2014-09-14 | 40 | 6277

## Unit Cost
Unit Cost - F-35 Aircraft
Unit Cost Report | BY 2012 $M | BY 2012 $M
Unit Cost | Current UCR Baseline (JUN 2014 APB) | Current Estimate (DEC 2015 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 274958.4 | 261760.9
Quantity | 2457 | 2457
Unit Cost | 111.908 | 106.537 | -4.8
Average Procurement Unit Cost (APUC)
Cost | 224332.9 | 211290.9
Quantity | 2443 | 2443
Unit Cost | 91.827 | 86.488 | -5.81
| BY 2012 $M | BY 2012 $M
Unit Cost | Revised Original UCR Baseline (MAR 2012 APB) | Current Estimate (DEC 2015 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 276482.2 | 261760.9
Quantity | 2458 | 2457
Unit Cost | 112.483 | 106.537 | -5.29
Average Procurement Unit Cost (APUC)
Cost | 224333.7 | 211290.9
Quantity | 2443 | 2443
Unit Cost | 91.827 | 86.488 | -5.81
Unit Cost History, F-35 Aircraft
|  | BY 2012 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2001-10-01 | 74.567 | 60.632 | 81.298 | 68.934
APB as of JAN 2006 | 2004-03-01 | 94.837 | 73.845 | 100.407 | 81.826
Revised Original APB | 2012-03-01 | 112.529 | 91.827 | 135.065 | 115.697
Prior APB | 2012-03-01 | 112.529 | 91.827 | 135.065 | 115.697
Current APB | 2014-06-01 | 111.908 | 91.827 | 134.638 | 115.697
Prior Annual SAR | 2014-12-01 | 107.755 | 87.889 | 131.918 | 113.208
Current Estimate | 2015-12-01 | 106.537 | 86.488 | 129.585 | 110.695
SAR Unit Cost History | Changes | [7 empty] | PAUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial PAUC Dev Est
135.065 | 0.422 | 0 | 1.592 | 0.744 | -4.257 | 0 | -3.981 | -5.48 | 129.585
| Changes Econ: Changes | APUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial APUC Dev Est
115.697 | 0.427 | 0 | 1.602 | 0.748 | -3.775 | 0 | -4.004 | -5.002 | 110.695
SAR Baseline History | bar: Changes Econ to Changes Eng
Item/Event | Changes Econ: SAR Planning Estimate (PE); Changes Qty: SAR Development Estimate (DE); Changes Sch: SAR Production Estimate (PdE); Changes Eng: Current Estimate
Milestone I | Changes Econ: N/A; Changes Qty: 1996-11-01; Changes Sch: N/A; Changes Eng: 1996-11-01
Milestone B | Changes Econ: 2001-03-01; Changes Qty: 2012-03-01; Changes Sch: N/A; Changes Eng: 2012-03-01
Milestone C | Changes Econ: TBD; Changes Qty: 2019-04-01; Changes Sch: N/A; Changes Eng: 2019-04-01
IOC | Changes Econ: TBD; Changes Qty: TBD; Changes Sch: N/A; Changes Eng: 2015-07-01
Total Cost (TY $M) | Changes Econ: 24800; Changes Qty: 331855.2; Changes Sch: N/A; Changes Eng: 318390.9
Total Quantity | Changes Econ: N/A; Changes Qty: 2457; Changes Sch: N/A; Changes Eng: 2457
Prog. Acq. Unit Cost (PAUC) | Changes Econ: N/A; Changes Qty: 135.065; Changes Sch: N/A; Changes Eng: 129.585
Unit Cost - F-35 Engine
Unit Cost Report | Changes Econ: BY 2012 $M; Changes Qty: BY 2012 $M
Unit Cost | Changes Econ: Current UCR Baseline (JUN 2014 APB); Changes Qty: Current Estimate (DEC 2015 SAR); Changes Sch: BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | Changes Econ: 55273.5; Changes Qty: 51499.5
Quantity | Changes Econ: 2457; Changes Qty: 2457
Unit Cost | Changes Econ: 22.496; Changes Qty: 20.96; Changes Sch: -6.83
Average Procurement Unit Cost (APUC)
Cost | Changes Econ: 42332.9; Changes Qty: 38376.9
Quantity | Changes Econ: 2443; Changes Qty: 2443
Unit Cost | Changes Econ: 17.328; Changes Qty: 15.709; Changes Sch: -9.34
| BY 2012 $M | BY 2012 $M
Unit Cost | Changes Econ: Original UCR Baseline (MAR 2012 APB); Changes Qty: Current Estimate (DEC 2015 SAR); Changes Sch: BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | Changes Econ: 53916.4; Changes Qty: 51499.5
Quantity | Changes Econ: 2458; Changes Qty: 2457
Unit Cost | Changes Econ: 21.935; Changes Qty: 20.96; Changes Sch: -4.44
Average Procurement Unit Cost (APUC)
Cost | Changes Econ: 42332.9; Changes Qty: 38376.9
Quantity | Changes Econ: 2443; Changes Qty: 2443
Unit Cost | Changes Econ: 17.328; Changes Qty: 15.709; Changes Sch: -9.34
Unit Cost History, F-35 Engine
|  | BY 2012 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2012-03-01 | 21.989 | 17.328 | 25.99 | 21.708
APB as of JAN 2006 | N/A | N/A | N/A | N/A | N/A
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | 2012-03-01 | 21.989 | 17.328 | 25.99 | 21.708
Current APB | 2014-06-01 | 22.496 | 17.328 | 26.396 | 21.708
Prior Annual SAR | 2014-12-01 | 22.626 | 17.378 | 27.274 | 22.526
Current Estimate | 2015-12-01 | 20.96 | 15.709 | 24.685 | 19.93
SAR Unit Cost History | Changes Econ: Changes | PAUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial PAUC Dev Est
25.99 | 0.054 | 0 | 0.303 | 0 | -0.501 | 0 | -1.161 | -1.305 | 24.685
| Changes Econ: Changes | APUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial APUC Dev Est
21.708 | 0.048 | 0 | 0.305 | 0 | -0.963 | 0 | -1.167 | -1.777 | 19.93
SAR Baseline History | bar: Changes Econ to Changes Eng
Item/Event | Changes Econ: SAR Planning Estimate (PE); Changes Qty: SAR Development Estimate (DE); Changes Sch: SAR Production Estimate (PdE); Changes Eng: Current Estimate
Milestone A | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
Milestone B | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
Milestone C | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
IOC | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
Total Cost (TY $M) | Changes Econ: N/A; Changes Qty: 63856.6; Changes Sch: N/A; Changes Eng: 60651.1
Total Quantity | Changes Econ: N/A; Changes Qty: 2457; Changes Sch: N/A; Changes Eng: 2457
Prog. Acq. Unit Cost (PAUC) | Changes Econ: N/A; Changes Qty: 25.99; Changes Sch: N/A; Changes Eng: 24.685

## Cost Variance
Cost Variance - F-35 Aircraft
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 44410.1 | 282647.8 | 4797.3 | 331855.2
Previous Changes
Economic | 24.6 | 2886.2 | 29.5 | 2940.3
Quantity | -- | -- | -- | --
Schedule | -- | 3425.5 | -- | 3425.5
Engineering | -- | -- | -- | --
Estimating | -1507.9 | -7348.4 | -199.7 | -9056
Other | -- | -- | -- | --
Support | -- | -5043.7 | -- | -5043.7
Subtotal | -1483.3 | -6080.4 | -170.2 | -7733.9
Current Changes
Economic | -36.7 | -1842.6 | -25.2 | -1904.5
Quantity | -- | -- | -- | --
Schedule | -- | 487.2 | -- | 487.2
Engineering | -- | 1826.8 | -- | 1826.8
Estimating | 280 | -1873.1 | 191.4 | -1401.7
Other | -- | -- | -- | --
Support | -- | -4738.2 | -- | -4738.2
Subtotal | 243.3 | -6139.9 | 166.2 | -5730.4
Total Changes | -1240 | -12220.3 | -4 | -13464.3
CE - Cost Variance | 43170.1 | 270427.5 | 4793.3 | 318390.9
CE - Cost & Funding | 43170.1 | 270427.5 | 4793.3 | 318390.9
Summary Base Year 2012 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 47982.1 | 224332.9 | 4168 | 276483
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -1870 | -5117.6 | -238.6 | -7226.2
Other | -- | -- | -- | --
Support | -- | -4502.9 | -- | -4502.9
Subtotal | -1870 | -9620.5 | -238.6 | -11729.1
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | 1346.4 | -- | 1346.4
Estimating | 256.5 | -1349.7 | 172 | -921.2
Other | -- | -- | -- | --
Support | -- | -3418.2 | -- | -3418.2
Subtotal | 256.5 | -3421.5 | 172 | -2993
Total Changes | -1613.5 | -13042 | -66.6 | -14722.1
CE - Cost Variance | 46368.6 | 211290.9 | 4101.4 | 261760.9
CE - Cost & Funding | 46368.6 | 211290.9 | 4101.4 | 261760.9
Cost Variance - F-35 Engine
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 10823.7 | 53032.9 | -- | 63856.6
Previous Changes
Economic | 21.2 | 489.3 | -- | 510.5
Quantity | -- | -- | -- | --
Schedule | -- | 645.6 | -- | 645.6
Engineering | -- | -- | -- | --
Estimating | 1136.7 | 1695.7 | -- | 2832.4
Other | -- | -- | -- | --
Support | -- | -831.7 | -- | -831.7
Subtotal | 1157.9 | 1998.9 | -- | 3156.8
Current Changes
Economic | -4.7 | -373.1 | -- | -377.8
Quantity | -- | -- | -- | --
Schedule | -- | 98.5 | -- | 98.5
Engineering | -- | -- | -- | --
Estimating | -14 | -4048.7 | -- | -4062.7
Other | -- | -- | -- | --
Support | -- | -2020.3 | -- | -2020.3
Subtotal | -18.7 | -6343.6 | -- | -6362.3
Total Changes | 1139.2 | -4344.7 | -- | -3205.5
CE - Cost Variance | 11962.9 | 48688.2 | -- | 60651.1
CE - Cost & Funding | 11962.9 | 48688.2 | -- | 60651.1
Summary Base Year 2012 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 11695.2 | 42332.9 | -- | 54028.1
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 1440.8 | 888.6 | -- | 2329.4
Other | -- | -- | -- | --
Support | -- | -766.3 | -- | -766.3
Subtotal | 1440.8 | 122.3 | -- | 1563.1
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -13.4 | -2670.3 | -- | -2683.7
Other | -- | -- | -- | --
Support | -- | -1408 | -- | -1408
Subtotal | -13.4 | -4078.3 | -- | -4091.7
Total Changes | 1427.4 | -3956 | -- | -2528.6
CE - Cost Variance | 13122.6 | 38376.9 | -- | 51499.5
CE - Cost & Funding | 13122.6 | 38376.9 | -- | 51499.5

## Contracts
Contract Name: F-35 LRIP 6
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
4392.1 | N/A | 36 | 7233.6 | N/A | 36 | 7093.6 | 7233.6
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -131.2 | -203.4
Previous Cumulative Variances | -183 | -193
Net Change | 51.8 | -10.4
Contract Name: F135 LRIP 6
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1122 | 1128.8 | 38 | 1131.9 | 1139 | 38 | 1099.3 | 1091.6
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -10.9 | -36.5
Previous Cumulative Variances | -8.6 | -31
Net Change | -2.3 | -5.5
Contract Name: F-35 LRIP 7
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
4447.1 | N/A | 35 | 5640.4 | N/A | 35 | 5547.1 | 5640.4
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -78.6 | -84.8
Previous Cumulative Variances | -10 | -46
Net Change | -68.6 | -38.8
Contract Name: F135 LRIP 8
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1009.1 | 1011.9 | 48 | 1185.1 | 1191.4 | 48 | 1141.7 | 1185.1
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -68.9 | -9.5
Previous Cumulative Variances | -- | --
Net Change | -68.9 | -9.5
Contract Name: F-35 LRIP 8
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
5153.5 | N/A | 43 | 5171.3 | N/A | 43 | 5162.2 | 5171.3
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -65 | -136.1
Previous Cumulative Variances | -- | --
Net Change | -65 | -136.1
Contract Name: FY 15 Annualized Sustainment
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
5153.5 | N/A | 43 | 5171.3 | N/A | 43 | 5162.2 | 5171.3
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -65 | -136.1
Previous Cumulative Variances | -- | --
Net Change | -65 | -136.1

## Deliveries and Expenditures
F-35 Aircraft
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 14 | 14 | 14 | 100%
Production | 148 | 146 | 2443 | 5.98%
Total Program Quantities Delivered | 162 | 160 | 2457 | 6.51%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 318390.9 | Years Appropriated | 23
Expenditures to Date | 66171.9 | Percent Years Appropriated | 51.11%
Precent Expended | 20.78% | Appropriated to Date | 91294.7
Total Funding Years | 45 | Percent Appropriated | 28.67%
F-35 Engine
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 14 | 14 | 14 | 100%
Production | 148 | 146 | 2443 | 5.98%
Total Program Quantities Delivered | 162 | 160 | 2457 | 6.51%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 60651.1 | Years Appropriated | 23
Expenditures to Date | 17008.4 | Percent Years Appropriated | 51.11%
Precent Expended | 28.04% | Appropriated to Date | 19924.7
Total Funding Years | 45 | Percent Appropriated | 32.85%

## Operating and Support Cost
F-35 Aircraft
Unitized O&S Costs BY 2012 $K
Cost Element | F-35 Aircraft Cost per Flying Hour ($) | F-16C/D Cost per Flying Hour ($)
Unit-Level Manpower | 8.47 | 10.042
Unit Operations | 4.923 | 5.632
Maintenance | 11.126 | 5.501
Sustaining Support | 3.179 | 2.075
Continuing System Improvements | 2.108 | 2.291
Indirect Support | 0 | 0
Other | 0 | 0
Total Unitized Cost (Base Year 2002 $) | 29.806 | 25.541
| Current Development APB Objective/Threshold |  | Current Estimate
Total O&S Costs $M | F-35 Aircraft |  | F-35 Aircraft | F-16C/D
Base Year | 617000 | 678700 | 620805.4 | N/A
Then Year | 1113272.6 | N/A | 1123844 | N/A