## Cost Summary
Total Acquisition Cost and Quantity
| BY2002 $M |  |  |  | TY $M
Appropriation | SAR Baseline Deve Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 32300 | 42100 | 46310 | 42032.8 | 34400 | 44800 | 44778.3
Procurement | 143300 | 149500 | 164450 | 149403.6 | 196600 | 199900 | 199835.2
Flyaway | 121215.5 | -- | -- | -- | 166349.7 | -- | --
Recurring | 116093.6 | -- | -- | -- | 159390.4 | -- | --
Non Recurring | 5121.9 | -- | -- | 6696 | 6959.3 | -- | 8876.5
Support | 22084.5 |  | -- | -- | 30250.3 | -- | --
Other Support | 15403.5 | -- | -- | -- | 21109.3 | -- | --
Initial Spares | 6681 | -- | -- | -- | 9141 | -- | --
MILCON | 1500 | 1500 | 1700 | 196.5 | 2000 | 2000 | 220.8
Acq O&M | -- | -- | -- | -- | -- | -- | --
Total | 177100 | 193100 | N/A | 191632.9 | 23000 | 246700 | 244834.3
Quantity | SAR Baseline Dev Est | Current APB Development | Current Estimate
RDT&E | 14 | 14 | 14
Procurement | 2852 | 2443 | 2443
Total | 2866 | 2457 | 2457

## Funding Summary
Appropriation and Quantity Summary
FY2005 President's Budget / December 2003 SAR (TY$ M)
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | To Complete | Total
RDT&E | 9679.5 | 4773.5 | 5328.2 | 5787 | 5191.2 | 4623.5 | 3472.7 | 5922.7 | 44778.3
Procurement | 0 | 0 | 0 | 235 | 1876.6 | 4098.8 | 7375.5 | 186249.3 | 199835.2
MILCON | 0 | 44.5 | 10.9 | 0 | 0 | 85.4 | 80 | 0 | 220.8
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 9679.5 | 4818 | 5339.1 | 6022 | 7067.8 | 8807.7 | 10928.2 | 192172 | 244834.3
PB 2014 Total | 9805.6 | 4933.5 | 5357.1 | 6548.9 | 7058.5 | 8763.3 | 10759.5 | 146510 | 199736.4
Delta | -126.1 | -115.5 | -18 | -526.9 | 9.3 | 44.4 | 168.7 | 45662 | 45097.9
Quantity | Prior | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Production | 0 | 0 | 0 | 0 | 8 | 24 | 58 | 2353 | 2443
PB2005 Total | 0 | 0 | 0 | 0 | 8 | 24 | 58 | 2353 | 2457
PB2004 Total | 0 | 0 | 0 | 10 | 22 | 49 | 82 | 2280 | 2457
Delta | 0 | 0 | 0 | -10 | -14 | -25 | -24 | 73 | 0

## Annual Funding By Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 29.5
1995 | -- | -- | -- | -- | -- | -- | 98.3
1996 | -- | -- | -- | -- | -- | -- | 80.4
1997 | -- | -- | -- | -- | -- | -- | 243.3
1998 | -- | -- | -- | -- | -- | -- | 448.2
1999 | -- | -- | -- | -- | -- | -- | 471.3
2000 | -- | -- | -- | -- | -- | -- | 238.4
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 722.9
2003 | -- | -- | -- | -- | -- | -- | 1661.5
2004 | -- | -- | -- | -- | -- | -- | 2159.2
2005 | -- | -- | -- | -- | -- | -- | 2264.5
2006 | -- | -- | -- | -- | -- | -- | 2493.8
2007 | -- | -- | -- | -- | -- | -- | 2281.8
2008 | -- | -- | -- | -- | -- | -- | 2086.4
2009 | -- | -- | -- | -- | -- | -- | 1615.6
2010 | -- | -- | -- | -- | -- | -- | 1275.6
2011 | -- | -- | -- | -- | -- | -- | 792.8
2012 | -- | -- | -- | -- | -- | -- | 414.1
2013 | -- | -- | -- | -- | -- | -- | 240.9
Subtotal | -- | -- | -- | -- | -- | -- | 19959.7
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1994 | -- | -- | -- | -- | -- | -- | 32.6
1995 | -- | -- | -- | -- | -- | -- | 106.6
1996 | -- | -- | -- | -- | -- | -- | 85.7
1997 | -- | -- | -- | -- | -- | -- | 256.3
1998 | -- | -- | -- | -- | -- | -- | 468.1
1999 | -- | -- | -- | -- | -- | -- | 486.4
2000 | -- | -- | -- | -- | -- | -- | 242.4
2001 | -- | -- | -- | -- | -- | -- | 342.2
2002 | -- | -- | -- | -- | -- | -- | 718.2
2003 | -- | -- | -- | -- | -- | -- | 1631.4
2004 | -- | -- | -- | -- | -- | -- | 2091.8
2005 | -- | -- | -- | -- | -- | -- | 2163
2006 | -- | -- | -- | -- | -- | -- | 2343.8
2007 | -- | -- | -- | -- | -- | -- | 2106.3
2008 | -- | -- | -- | -- | -- | -- | 1888.8
2009 | -- | -- | -- | -- | -- | -- | 1433.8
2010 | -- | -- | -- | -- | -- | -- | 1109.7
2011 | -- | -- | -- | -- | -- | -- | 676
2012 | -- | -- | -- | -- | -- | -- | 346.1
2013 | -- | -- | -- | -- | -- | -- | 197.4
Subtotal | -- | -- | -- | -- | -- | -- | 18726.6
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | -- | -- | -- | -- | -- | -- | 83.8
1996 | -- | -- | -- | -- | -- | -- | 81.3
1997 | -- | -- | -- | -- | -- | -- | 251.6
1998 | -- | -- | -- | -- | -- | -- | 444.3
1999 | -- | -- | -- | -- | -- | -- | 456.1
2000 | -- | -- | -- | -- | -- | -- | 249.1
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 720.1
2003 | -- | -- | -- | -- | -- | -- | 1612.8
2004 | -- | -- | -- | -- | -- | -- | 2092.5
2005 | -- | -- | -- | -- | -- | -- | 2307.4
2006 | -- | -- | -- | -- | -- | -- | 2489.8
2007 | -- | -- | -- | -- | -- | -- | 2203.4
2008 | -- | -- | -- | -- | -- | -- | 2051.9
2009 | -- | -- | -- | -- | -- | -- | 1686.7
2010 | -- | -- | -- | -- | -- | -- | 1315.6
2011 | -- | -- | -- | -- | -- | -- | 832.8
2012 | -- | -- | -- | -- | -- | -- | 454
2013 | -- | -- | -- | -- | -- | -- | 242.1
Subtotal | 7 | -- | -- | -- | -- | -- | 19916.5
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1995 | -- | -- | -- | -- | -- | -- | 90.9
1996 | -- | -- | -- | -- | -- | -- | 86..7
1997 | -- | -- | -- | -- | -- | -- | 265
1998 | -- | -- | -- | -- | -- | -- | 464
1999 | -- | -- | -- | -- | -- | -- | 470.7
2000 | -- | -- | -- | -- | -- | -- | 253.3
2001 | -- | -- | -- | -- | -- | -- | 342.2
2002 | -- | -- | -- | -- | -- | -- | 715.4
2003 | -- | -- | -- | -- | -- | -- | 1583.6
2004 | -- | -- | -- | -- | -- | -- | 2027.2
2005 | -- | -- | -- | -- | -- | -- | 2203.9
2006 | -- | -- | -- | -- | -- | -- | 2340.1
2007 | -- | -- | -- | -- | -- | -- | 2033.9
2008 | -- | -- | -- | -- | -- | -- | 1857.6
2009 | -- | -- | -- | -- | -- | -- | 1496.9
2010 | -- | -- | -- | -- | -- | -- | 1144.5
2011 | -- | -- | -- | -- | -- | -- | 710.2
2012 | -- | -- | -- | -- | -- | -- | 379.5
2013 | -- | -- | -- | -- | -- | -- | 198.4
Subtotal | 7 | -- | -- | -- | -- | -- | 18664
Annual Funding TY$
9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 14
1997 | -- | -- | -- | -- | -- | -- | 71
1998 | -- | -- | -- | -- | -- | -- | 77.2
1999 | -- | -- | -- | -- | -- | -- | 54.7
2000 | -- | -- | -- | -- | -- | -- | 34.5
2001 | -- | -- | -- | -- | -- | -- | 2.5
2002 | -- | -- | -- | -- | -- | -- | 306.4
2003 | -- | -- | -- | -- | -- | -- | 425.9
2004 | -- | -- | -- | -- | -- | -- | 521.8
2005 | -- | -- | -- | -- | -- | -- | 756.3
2006 | -- | -- | -- | -- | -- | -- | 803.4
2007 | -- | -- | -- | -- | -- | -- | 706
2008 | -- | -- | -- | -- | -- | -- | 485.2
2009 | -- | -- | -- | -- | -- | -- | 170.4
2010 | -- | -- | -- | -- | -- | -- | 186.2
2011 | -- | -- | -- | -- | -- | -- | 165.7
2012 | -- | -- | -- | -- | -- | -- | 2.9
Subtotal | -- | -- | -- | -- | -- | -- | 4784.1
Annual Funding BY$
9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1996 | -- | -- | -- | -- | -- | -- | 14.9
1997 | -- | -- | -- | -- | -- | -- | 74.8
1998 | -- | -- | -- | -- | -- | -- | 80.6
1999 | -- | -- | -- | -- | -- | -- | 56.4
2000 | -- | -- | -- | -- | -- | -- | 35.1
2001 | -- | -- | -- | -- | -- | -- | 2.5
2002 | -- | -- | -- | -- | -- | -- | 304.4
2003 | -- | -- | -- | -- | -- | -- | 418.2
2004 | -- | -- | -- | -- | -- | -- | 505.5
2005 | -- | -- | -- | -- | -- | -- | 722.4
2006 | -- | -- | -- | -- | -- | -- | 755.1
2007 | -- | -- | -- | -- | -- | -- | 651.7
2008 | -- | -- | -- | -- | -- | -- | 439.3
2009 | -- | -- | -- | -- | -- | -- | 151.2
2010 | -- | -- | -- | -- | -- | -- | 162
2011 | -- | -- | -- | -- | -- | -- | 141.3
2012 | -- | -- | -- | -- | -- | -- | 2.4
Subtotal | -- | -- | -- | -- | -- | -- | 4517.8
Annual Funding TY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 28.9
1997 | -- | -- | -- | -- | -- | -- | 68.2
1998 | -- | -- | -- | -- | -- | -- | 20.9
Subtotal | -- | -- | -- | -- | -- | -- | 4517.8
Annual Funding BY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1996 | -- | -- | -- | -- | -- | -- | 30.8
1997 | -- | -- | -- | -- | -- | -- | 71.8
1998 | -- | -- | -- | -- | -- | -- | 21.8
Subtotal | -- | -- | -- | -- | -- | -- | 124.4
Annual Funding TY$
1506 ¦ RDT&E ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | -- | -- | -- | -- | -- | 61.6
2007 | 2 | -- | -- | 44.6 | -- | -- | 711.3
2008 | 16 | -- | -- | 206.8 | -- | -- | 2865.8
2009 | 40 | -- | -- | 203.9 | -- | -- | 5134.1
2010 | 31 | -- | -- | 214.8 | -- | -- | 3730
2011 | 34 | -- | -- | 222 | -- | -- | 3659.7
2012 | 39 | -- | -- | 175 | -- | -- | 3921.3
2013 | 47 | -- | -- | 223.3 | -- | -- | 4456.4
2014 | 55 | -- | -- | 199.5 | -- | -- | 4569.2
2015 | 55 | -- | -- | 198.8 | -- | -- | 4685.5
2016 | 55 | -- | -- | 198.9 | -- | -- | 4637.4
2017 | 55 | -- | -- | 199.6 | -- | -- | 4619.8
2018 | 55 | -- | -- | 204.9 | -- | -- | 4619.8
2019 | 57 | -- | -- | 209.2 | -- | -- | 4774.9
2020 | 57 | -- | -- | 211.1 | -- | -- | 4739.5
2021 | 46 | -- | -- | 174.2 | -- | -- | 3889.1
2022 | 36 | -- | -- | 141.4 | -- | -- | 3021.7
Subtotal | -- | -- | -- | 3028 | -- | -- | 64097.1
Annual Funding BY$
1506 ¦ RDT&E ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2006 | -- | -- | -- | -- | -- | -- | 57.2
2007 | 2 | -- | -- | 40.6 | -- | -- | 647.9
2008 | 16 | -- | -- | 184.7 | -- | -- | 2559.6
2009 | 40 | -- | -- | 178.5 | -- | -- | 4495.6
2010 | 31 | -- | -- | 184.4 | -- | -- | 3202.1
2011 | 34 | -- | -- | 186.8 | -- | -- | 3080.1
2012 | 39 | -- | -- | 144.4 | -- | -- | 3235.6
2013 | 47 | -- | -- | 180.6 | -- | -- | 3605
2014 | 55 | -- | -- | 158.2 | -- | -- | 3623.8
2015 | 55 | -- | -- | 154.6 | -- | -- | 3643.1
2016 | 55 | -- | -- | 151.6 | -- | -- | 3535
2017 | 55 | -- | -- | 149.2 | -- | -- | 3452.6
2018 | 55 | -- | -- | 150.1 | -- | -- | 3384.9
2019 | 57 | -- | -- | 150.3 | -- | -- | 3429.9
2020 | 57 | -- | -- | 148.7 | -- | -- | 3337.7
2021 | 46 | -- | -- | 120.3 | -- | -- | 2685.2
2022 | 36 | -- | -- | 95.7 | -- | -- | 2045.4
Subtotal | 680 | -- | -- | 2378.7 | -- | -- | 50020.7
Cost Quantity Information
1506 ¦ RDT&E ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2002 $M)
2006 | -- | --
2007 | 2 | 299.9
2008 | 16 | 1892.3
2009 | 40 | 3575.8
2010 | 31 | 2427.1
2011 | 34 | 2391.9
2012 | 39 | 2481
2013 | 47 | 2802.5
2014 | 55 | 2965.7
2015 | 55 | 2847.4
2016 | 55 | 2761.1
2017 | 55 | 2692.8
2018 | 55 | 2638.4
2019 | 57 | 2676
2020 | 57 | 2618.7
2021 | 46 | 2107.6
2022 | 36 | 1649.7
Subtotal | 680 | 38827.9
Annual Funding TY$
3010 ¦ Procurement ¦ Aircraft Procurement, AF
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | -- | -- | -- | -- | -- | 173.4
2007 | 6 | -- | -- | 124.6 | -- | -- | 1165.3
2008 | 8 | -- | -- | 94.7 | -- | -- | 1233
2009 | 18 | -- | -- | 77.5 | -- | -- | 2241.4
2010 | 31 | -- | -- | 188.7 | -- | -- | 3468.3
2011 | 58 | -- | -- | 327.9 | -- | -- | 5537.2
2012 | 92 | -- | -- | 332.1 | -- | -- | 7725.1
2013 | 96 | -- | -- | 372.5 | -- | -- | 7652.1
2014 | 110 | -- | -- | 310.1 | -- | -- | 7692.5
2015 | 110 | -- | -- | 308.4 | -- | -- | 7922.4
2016 | 110 | -- | -- | 308.3 | -- | -- | 7856.3
2017 | 110 | -- | -- | 309.2 | -- | -- | 7842.3
2018 | 110 | -- | -- | 319 | -- | -- | 7838.9
2019 | 110 | -- | -- | 312.5 | -- | -- | 7842.7
2020 | 110 | -- | -- | 315.2 | -- | -- | 7843.3
2021 | 110 | -- | -- | 320.8 | -- | -- | 7940.8
2022 | 110 | -- | -- | 328.9 | -- | -- | 8089.2
2023 | 110 | -- | -- | 343 | -- | -- | 8373.6
2024 | 110 | -- | -- | 348 | -- | -- | 8481.6
2025 | 110 | -- | -- | 353.1 | -- | -- | 8547.3
2026 | 110 | -- | -- | 358.4 | -- | -- | 8252.6
2027 | 24 | -- | -- | 95.6 | -- | -- | 2018.8
Subtotal | 1763 | -- | -- | 5848.5 | -- | -- | 135738.1
Annual Funding TY$
3010 ¦ Procurement ¦ Aircraft Procurement, AF
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2006 | -- | -- | -- | -- | -- | -- | 160.9
2007 | 6 | -- | -- | 113.5 | -- | -- | 1061.4
2008 | 8 | -- | -- | 84.6 | -- | -- | 1101.2
2009 | 18 | -- | -- | 67.9 | -- | -- | 1962.6
2010 | 31 | -- | -- | 162 | -- | -- | 2977.4
2011 | 58 | -- | -- | 276 | -- | -- | 4660.3
2012 | 92 | -- | -- | 274 | -- | -- | 6374.2
2013 | 96 | -- | -- | 301.3 | -- | -- | 6190.2
2014 | 110 | -- | -- | 245.9 | -- | -- | 6100.8
2015 | 110 | -- | -- | 239.8 | -- | -- | 6160
2016 | 110 | -- | -- | 235 | -- | -- | 5988.8
2017 | 110 | -- | -- | 231.1 | -- | -- | 5860.9
2018 | 110 | -- | -- | 233.7 | -- | -- | 5743.5
2019 | 110 | -- | -- | 224.5 | -- | -- | 5633.6
2020 | 110 | -- | -- | 222 | -- | -- | 5523.6
2021 | 110 | -- | -- | 221.5 | -- | -- | 5482.6
2022 | 110 | -- | -- | 222.6 | -- | -- | 5475.5
2023 | 110 | -- | -- | 227.6 | -- | -- | 5556.9
2024 | 110 | -- | -- | 226.4 | -- | -- | 5518.2
2025 | 110 | -- | -- | 225.2 | -- | -- | 5451.9
2026 | 110 | -- | -- | 224.1 | -- | -- | 5160.7
2027 | 24 | -- | -- | 58.6 | -- | -- | 1237.7
Subtotal | 1763 | -- | -- | 4317.3 | -- | -- | 99382.9
Cost Quantity Information
3010 ¦ RDT&E ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2002 $M)
2006 | -- | --
2007 | 6 | 810.3
2008 | 8 | 828.4
2009 | 18 | 1465.5
2010 | 31 | 2186.9
2011 | 58 | 3587.3
2012 | 92 | 5064.5
2013 | 96 | 4935.1
2014 | 110 | 5119.7
2015 | 110 | 4932.4
2016 | 110 | 4792.8
2017 | 110 | 4683.9
2018 | 110 | 4593.9
2019 | 110 | 4505.1
2020 | 110 | 4413.5
2021 | 110 | 4378.9
2022 | 110 | 4369.1
2023 | 110 | 4436.4
2024 | 110 | 4405.8
2025 | 110 | 4354.4
2026 | 110 | 4227.7
2027 | 24 | 968
Subtotal | 1763 | 79059.6
Annual Funding TY$
1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | Total Program TY $M
2004 | 24.4
Subtotal | 24.4
Annual Funding BY$
1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | Total Program TY $M
2004 | 23.2
Subtotal | 23.2
Annual Funding TY$
3300 ¦ MILCON ¦ Military Construction, Air Foce
Fiscal Year | Total Program TY $M
2004 | 20.1
2005 | 10.9
2006 | --
2007 | --
2008 | 85.4
2009 | 80
Subtotal | 24.4
Annual Funding BY$
3300 ¦ MILCON ¦ Military Construction, Air Foce
Fiscal Year | Total Program TY $M
2004 | 19.1
2005 | 10.2
2006 | --
2007 | --
2008 | 75.1
2009 | 68.9
Subtotal | 173.3

## Unit Cost
Unit Cost Report
6 | BY2002 $M
Unit Cost | Current UCR Baseline (OCT 2001 APB) | Current Estimate (DEC 2003 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 177100 | 191632.9
Quantity | 2866 | 2457
Unit Cost | 61.793 | 77.995 | 26.22
Average Procurement Unit Cost (APUC)
Cost | 143300 | 149403.6
Quantity | 2852 | 2443
Unit Cost | 50.245 | 61.156 | 21.72
BY2002 $M
Unit Cost | Original UCR Baseline | Current Estimate (DEC 2003 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost |  | 191632.9
Quantity |  | 2457
Unit Cost |  | 77.995 | 0
Average Procurement Unit Cost (APUC)
Cost | 143300 | 149403.6
Quantity | 2852 | 2443
Unit Cost | 50.245 | 61.156 | 0
TY $M
Unit Cost | Current UCR Baseline (OCT 2001 APB) | Current Estimate (DEC 2003 SAR) | TY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 233000 | 244834.3
Unit Cost | 81.298 | 99.648 | 26.22
Average Procurement Unit Cost (APUC)
Cost | 196600 | 199835.2
Unit Cost | 68.934 | 81.799 | 18.66
TY $M
Unit Cost | Original UCR Baseline | Current Estimate (DEC 2003 SAR) | TY % Change
Program Acquisition Unit Cost (PAUC)
Cost |  | 244834.3
Unit Cost |  | 99.648 | 0
Average Procurement Unit Cost (APUC)
Cost |  | 199835.2
Unit Cost |  | 81.799 | 0
Nunn McCurdy Breach
Unit Cost Breach Data
Changes from Previous SAR | $M/Qty | Percent
PUAC (BY $M) | 12.25 | 18.63
APUC (BY $M) | 9.6 | 18.62
PAUC Quantity
PAUC (TY $M) | 18.35 | 22.58
APUC (TY $M) | 15.41 | 23.21
Initial SAR Information DEC 2001 | BY2002 $M | TY $M
Program Acquisition Cost | 177530.6 | 226458.3

## Unit Cost History
APB Unit Cost History
|  | BY2002 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | N/A | N/A | N/A | N/A | N/A
APB as of January 2006 | N/A | N/A | N/A | N/A | N/A
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | N/A | N/A | N/A | N/A | N/A
Current APB | N/A | N/A | N/A | N/A | N/A
Prior Annual SAR | N/A | N/A | N/A | N/A | N/A
Current Estimate | 2003-12-01 | 77.995 | 61.156 | 99.648 | 81.799
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Dev Est | Changes | [7 empty] | PAUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
81.298 | -2.238 | 2.368 | 6.389 | 2.13 | 8.017 | 0 | 1.684 | 18.35 | 99.648
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [7 empty] | APUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
68.934 | -2.113 | 1.129 | 3.342 | 1.045 | 7.768 | 0 | 1.694 | 12.865 | 81.799

## Cost Variance
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 34400 | 196600 | 2000 | 233000
Previous Changes
Economic | -334.3 | -7618.3 | 0 | -7952.6
Quantity | 0 | -25434.9 | 0 | -25434.9
Schedule | 39.2 | 2623.7 | 0 | 2662.9
Engineering | 2427.8 | 0 | 252.8 | 2680.6
Estimating | 754.8 | -300.9 | 0 | 453.9
Other | 0 | 0 | 0 | 0
Support | 0 | -3673.5 | 0 | -3673.5
Subtotal | 2887.5 | -34403.9 | 252.8 | -31263.6
Current Changes
Economic | -4.6 | 2456.3 | 2.3 | 2454
Quantity | -- | -- | -- | --
Schedule | 7495.4 | 5540.4 | -- | 13035.8
Engineering | -- | 2553.1 | -- | 2553.1
Estimating | 0 | 19278.2 | -34.3 | 19243.9
Other | -- | -- | -- | --
Support | -- | 7811.1 | -- | 7811.1
Subtotal | 7490.8 | 37639.1 | -32 | 45097.9
Adjustments | 0 | 0 | -2000 | -2000
Total Changes | 10378.3 | 3235.2 | -1779.2 | 11834.3
CE - Cost Variance | 44778.3 | 199835.2 | 220.8 | 244834.3
CE - Cost & Funding | 44778.3 | 199835.2 | 220.8 | 244834.3
Summary Base Year 2002 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 32300 | 143300 | 1500 | 177100
Previous Changes
Economic | 0 | 0 | 0 | 0
Quantity | 0 | -16249.1 | 0 | -16249.1
Schedule | 0 | 0 | 0 | 0
Engineering | 2231 | 0 | 227.3 | 2458.3
Estimating | 837.1 | 1492.7 | 0 | 2329.8
Other | 0 | 0 | 0 | 0
Support | 0 | -2595.1 | 0 | -2595.1
Subtotal | 3068.1 | -17351.5 | 227.3 | -14056.1
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | 6664.2 | 1359.5 | -- | 8023.7
Engineering | -- | 1911.8 | -- | 1911.8
Estimating | 0.5 | 14853.4 | -30.8 | 14823.1
Other | -- | -- | -- | --
Support | -- | 5330.4 | -- | 5330.4
Subtotal | 6664.7 | 23455.1 | -30.8 | 30089
Adjustments | 0 | 0 | -1500 | -1500
Total Changes | 9732.8 | 6103.6 | -1303.5 | 14532.9
CE - Cost Variance | 42032.8 | 149403.6 | 196.5 | 191632.9
CE - Cost & Funding | 42032.8 | 149403.6 | 196.5 | 191632.9
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -4.7
Economic adjustment for negative program change. (Economic) | N/A | 0.1
SDD schedule extension for additional design maturation and known and unknown risks (including anti-tamper) (Schedule) | 6664.2 | 7495.4
Adjustment for Current and Prior Inflation. (Estimating) | 2.7 | 2.7
Model Refinements to the cost estimating refinements (Estimating) | -2.2 | -2.7
RDT&E Subtotal | 6664.7 | 7490.8
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 2456.3
Delay in procure,emt start from FY 2006 to FY 2007 and revised annual quantity profiles (Schedule) | 1359.5 | 5540.4
Increased quantity procurement of Electro Optical Tracking System (EOTS) (Engineering) | 831 | 1083.8
Multi-Year Procurement delayed from 2012 to 2014 due to production start delay and revised annual procurement profiles (Estimating) | 739.4 | 904.7
Design maturation to reflet governmetn assessment based on Lockheed Martin 240-2.2 configuration and December 2003 Bottom-Up Weight #4 (Engineering) | 1080.8 | 1469.3
Revised Contract Direct Labor and Overhead Rates (Estimating) | 10525.5 | 13669.2
Learning curve impact of revised SDD and production schedules on prime contractors and subs and vendors (Estimating) | 3358 | 4374
Increase in standard hardware and general equipment costs. (Estimating) | 230.5 | 330.3
Increase due to aircraft configuration update, methodology changes, and refined definitions of support requirements (Support) | 5330.4 | 7811.1
Procurement Subtotal | 23455.1 | 37639.1
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | 3.3
Economic adjustment for negative program change. (Economic) | N/A | -1
SDD schedule extension for additional design maturation and known and unknown risks (including anti-tamper) (Schedule) | -0.2 | -0.2
Adjustment for Current and Prior Inflation. (Estimating) | -30.6 | -34.1
MILCON Subtotal | -30.8 | -32

## Deliveries and Expenditures
Deliveries to Date | Plan | Actual | Total Quantity | Percent Delivered
Development | 0 | 0 | 14 | 0
Production | 0 | 0 | 2443 | 0
Total Program Quantities Delivered | 0 | 0 | 2457 | 0
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 244834.3 | Years Appropriated | 11
Expenditures to Date | 8935.5 | Percent Years Appropriated | 32.35
Percent Expended | 3.65 | Appropriated to Date | 14497.5
Total Funding Years | 34 | Percent Appropriated | 5.92

## Operating and Support CostCi
Cost BY2002 $M
Cost Element | JSF Cost per Flying Hour ($) | F-16C/D Cost per Flying Hour ($)
Mission Pay & Allowance | 3289 | 5233
Unit Level Consumption | 3624 | 3507
Intermediate Maintenance | 0 | 3
Depot Maintenance | 399 | 293
Contractor Support | 0 | 44
Sustaining Support | 861 | 627
Indirect | 1301 | 2329
Other | -- | --
Total Unitized Cost (Base Year 2002 $) | 9474 | 12036
Total O&S Costs $M | JSF | F-16C/D
Base Year | 134821 | --
Then Year | 343981 | --