## Cost Summary
Total Acquisition Cost and Quantity
| BY2002 $M |  |  |  | TY $M
Appropriation | SAR Baseline Deve Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 32300 | 42100 | 46310 | 45136 | 34400 | 44800 | 50168.1
Procurement | 143300 | 168980.8 | 185878.9 | 193005.2 | 196600 | 231735.5 | 277533.6
Flyaway | 121215.6 | -- | -- | 164167.7 | 166349.7 | -- | 237334.1
Recurring | 116093.7 | -- | -- | 148352.6 | 159390.4 | -- | 215401.8
Non Recurring | 5121.9 | -- | -- | 15815.1 | 6959.3 | -- | 21932.3
Support | 22084.4 |  | -- | 28837.5 | 30250.3 | -- | 40199.5
Other Support | 15403.4 | -- | -- | 15542.2 | 21109.3 | -- | 20900.2
Initial Spares | 6681 | -- | -- | 13295.3 | 9141 | -- | 19299.3
MILCON | 1500 | 1500 | 1700 | 457.4 | 2000 | 2000 | 551.2
Acq O&M | -- | -- | -- | 0 | -- | 0 | 0
Total | 177100 | 212580.8 | N/A | 238598.6 | 23000 | 278535.5 | 328252.9
APB Breach
Quantity | SAR Baseline Dev Est | Current APB Development | Current Estimate
RDT&E | 14 | 15 | 14
Procurement | 2852 | 2443 | 2443
Total | 2866 | 2458 | 2457

## Funding Summary
Appropriation and Quantity Summary
FY2011 President's Budget / December 2009 SAR (TY$ M)
Appropriation | Prior | FY2010 | FY2011 | FY2012 | FY2013 | FY2014 | FY2015 | To Complete | Total
RDT&E | 37385.9 | 4132.6 | 2449.8 | 2433 | 1982.7 | 1337.4 | 446.7 | 0 | 50168.1
Procurement | 7125.8 | 7197.1 | 9313 | 9602.5 | 12054.7 | 12996.7 | 14183.1 | 205060.7 | 277533.6
MILCON | 151.4 | 76.4 | 139.7 | 73.8 | 82.3 | 0 | 27.6 | 0 | 551.2
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2011 Total | 44663.1 | 11406.1 | 11902.5 | 12109.3 | 14119.7 | 14334.1 | 14657.4 | 205060.7 | 328252.9
PB 2009 Total | 44452.1 | 8430.9 | 9032.9 | 12265.2 | 12262.3 | 12391.6 | 13081.9 | 186925.9 | 298842.8
Delta | 211 | 2975.2 | 2869.6 | -155.9 | 1857.4 | 1942.5 | 1575.5 | 18134.8 | 29410.1
Quantity | Undistributed | Prior | FY2010 | FY2011 | FY2012 | FY2013 | FY2014 | FY2015 | To Complete | Total
Development | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Production | 0 | 28 | 30 | 43 | 45 | 71 | 90 | 113 | 2023 | 2443
PB2005 Total | 14 | 28 | 30 | 43 | 45 | 71 | 90 | 113 | 2023 | 2457
PB2004 Total | 13 | 30 | 30 | 43 | 82 | 90 | 110 | 130 | 1928 | 2457
Delta | 1 | -2 | 0 | 0 | -37 | -19 | -20 | -17 | 95 | 1

## Annual Funding by Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 29.5
1995 | -- | -- | -- | -- | -- | -- | 98.3
1996 | -- | -- | -- | -- | -- | -- | 80.4
1997 | -- | -- | -- | -- | -- | -- | 243.3
1998 | -- | -- | -- | -- | -- | -- | 448.2
1999 | -- | -- | -- | -- | -- | -- | 471.3
2000 | -- | -- | -- | -- | -- | -- | 238.4
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 721.3
2003 | -- | -- | -- | -- | -- | -- | 1640.9
2004 | -- | -- | -- | -- | -- | -- | 2081.4
2005 | -- | -- | -- | -- | -- | -- | 2083.8
2006 | -- | -- | -- | -- | -- | -- | 2187.1
2007 | -- | -- | -- | -- | -- | -- | 2109.4
2008 | -- | -- | -- | -- | -- | -- | 1848.9
2009 | -- | -- | -- | -- | -- | -- | 1704.6
2010 | -- | -- | -- | -- | -- | -- | 1950.2
2011 | -- | -- | -- | -- | -- | -- | 1317.7
2012 | -- | -- | -- | -- | -- | -- | 1112.2
2013 | -- | -- | -- | -- | -- | -- | 965.6
2014 | -- | -- | -- | -- | -- | -- | 671.1
2015 | -- | -- | -- | -- | -- | -- | 223.3
Subtotal | 9 | -- | -- | -- | -- | -- | 22568.1
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1994 | -- | -- | -- | -- | -- | -- | 32.5
1995 | -- | -- | -- | -- | -- | -- | 106.4
1996 | -- | -- | -- | -- | -- | -- | 85.6
1997 | -- | -- | -- | -- | -- | -- | 255.9
1998 | -- | -- | -- | -- | -- | -- | 467.5
1999 | -- | -- | -- | -- | -- | -- | 485.9
2000 | -- | -- | -- | -- | -- | -- | 242.2
2001 | -- | -- | -- | -- | -- | -- | 342
2002 | -- | -- | -- | -- | -- | -- | 715.7
2003 | -- | -- | -- | -- | -- | -- | 1604.7
2004 | -- | -- | -- | -- | -- | -- | 1980.2
2005 | -- | -- | -- | -- | -- | -- | 1931.8
2006 | -- | -- | -- | -- | -- | -- | 1966.1
2007 | -- | -- | -- | -- | -- | -- | 1851.1
2008 | -- | -- | -- | -- | -- | -- | 1593.5
2009 | -- | -- | -- | -- | -- | -- | 1452
2010 | -- | -- | -- | -- | -- | -- | 1643.5
2011 | -- | -- | -- | -- | -- | -- | 1095
2012 | -- | -- | -- | -- | -- | -- | 909.2
2013 | -- | -- | -- | -- | -- | -- | 776.1
2014 | -- | -- | -- | -- | -- | -- | 530.4
2015 | -- | -- | -- | -- | -- | -- | 173.5
Subtotal | 9 | -- | -- | -- | -- | -- | 20240.8
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | -- | -- | -- | -- | -- | -- | 83.8
1996 | -- | -- | -- | -- | -- | -- | 81.3
1997 | -- | -- | -- | -- | -- | -- | 251.6
1998 | -- | -- | -- | -- | -- | -- | 444.3
1999 | -- | -- | -- | -- | -- | -- | 456.1
2000 | -- | -- | -- | -- | -- | -- | 249.1
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 712.4
2003 | -- | -- | -- | -- | -- | -- | 1610.6
2004 | -- | -- | -- | -- | -- | -- | 2019.9
2005 | -- | -- | -- | -- | -- | -- | 2080.1
2006 | -- | -- | -- | -- | -- | -- | 2264.8
2007 | -- | -- | -- | -- | -- | -- | 2074
2008 | -- | -- | -- | -- | -- | -- | 1955
2009 | -- | -- | -- | -- | -- | -- | 1743.6
2010 | -- | -- | -- | -- | -- | -- | 2072.9
2011 | -- | -- | -- | -- | -- | -- | 1043.6
2012 | -- | -- | -- | -- | -- | -- | 1298.5
2013 | -- | -- | -- | -- | -- | -- | 1005.5
2014 | -- | -- | -- | -- | -- | -- | 666.3
2015 | -- | -- | -- | -- | -- | -- | 223.4
Subtotal | 5 | -- | -- | -- | -- | -- | 22678
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1995 | -- | -- | -- | -- | -- | -- | 90.8
1996 | -- | -- | -- | -- | -- | -- | 86.5
1997 | -- | -- | -- | -- | -- | -- | 264.2
1998 | -- | -- | -- | -- | -- | -- | 463.6
1999 | -- | -- | -- | -- | -- | -- | 471
2000 | -- | -- | -- | -- | -- | -- | 253.4
2001 | -- | -- | -- | -- | -- | -- | 342.2
2002 | -- | -- | -- | -- | -- | -- | 707.1
2003 | -- | -- | -- | -- | -- | -- | 1577
2004 | -- | -- | -- | -- | -- | -- | 1929.6
2005 | -- | -- | -- | -- | -- | -- | 1937.4
2006 | -- | -- | -- | -- | -- | -- | 2047.9
2007 | -- | -- | -- | -- | -- | -- | 1827.3
2008 | -- | -- | -- | -- | -- | -- | 1688.9
2009 | -- | -- | -- | -- | -- | -- | 1486.9
2010 | -- | -- | -- | -- | -- | -- | 1749.5
2011 | -- | -- | -- | -- | -- | -- | 869.4
2012 | -- | -- | -- | -- | -- | -- | 1064.3
2013 | -- | -- | -- | -- | -- | -- | 810.3
2014 | -- | -- | -- | -- | -- | -- | 528
2015 | -- | -- | -- | -- | -- | -- | 174.1
Subtotal | 5 | -- | -- | -- | -- | -- | 22678
Annual Funding TY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense Wide
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 28.9
1997 | -- | -- | -- | -- | -- | -- | 68.2
1998 | -- | -- | -- | -- | -- | -- | 20.9
Subtotal | -- | -- | -- | -- | -- | -- | 118
Annual Funding TY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense Wide
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1996 | -- | -- | -- | -- | -- | -- | 30.8
1997 | -- | -- | -- | -- | -- | -- | 71.7
1998 | -- | -- | -- | -- | -- | -- | 21.8
Subtotal | -- | -- | -- | -- | -- | -- | 124.3
Annual Funding TY$
9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 14
1997 | -- | -- | -- | -- | -- | -- | 71
1998 | -- | -- | -- | -- | -- | -- | 77.2
1999 | -- | -- | -- | -- | -- | -- | 54.7
2000 | -- | -- | -- | -- | -- | -- | 34.5
2001 | -- | -- | -- | -- | -- | -- | 2.5
2002 | -- | -- | -- | -- | -- | -- | 306.4
2003 | -- | -- | -- | -- | -- | -- | 425.8
2004 | -- | -- | -- | -- | -- | -- | 517.8
2005 | -- | -- | -- | -- | -- | -- | 758.1
2006 | -- | -- | -- | -- | -- | -- | 802.5
2007 | -- | -- | -- | -- | -- | -- | 710.3
2008 | -- | -- | -- | -- | -- | -- | 552.7
2009 | -- | -- | -- | -- | -- | -- | 244.6
2010 | -- | -- | -- | -- | -- | -- | 109.5
2011 | -- | -- | -- | -- | -- | -- | 88.5
2012 | -- | -- | -- | -- | -- | -- | 22.3
2013 | -- | -- | -- | -- | -- | -- | 11.6
Subtotal | -- | -- | -- | -- | -- | -- | 4804
Annual Funding BY$
9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1996 | -- | -- | -- | -- | -- | -- | 14.9
1997 | -- | -- | -- | -- | -- | -- | 74.8
1998 | -- | -- | -- | -- | -- | -- | 80.7
1999 | -- | -- | -- | -- | -- | -- | 56.5
2000 | -- | -- | -- | -- | -- | -- | 35.1
2001 | -- | -- | -- | -- | -- | -- | 2.5
2002 | -- | -- | -- | -- | -- | -- | 304.1
2003 | -- | -- | -- | -- | -- | -- | 416.3
2004 | -- | -- | -- | -- | -- | -- | 492.5
2005 | -- | -- | -- | -- | -- | -- | 702.5
2006 | -- | -- | -- | -- | -- | -- | 721.1
2007 | -- | -- | -- | -- | -- | -- | 623
2008 | -- | -- | -- | -- | -- | -- | 476.1
2009 | -- | -- | -- | -- | -- | -- | 208.2
2010 | -- | -- | -- | -- | -- | -- | 92.2
2011 | -- | -- | -- | -- | -- | -- | 73.5
2012 | -- | -- | -- | -- | -- | -- | 18.2
2013 | -- | -- | -- | -- | -- | -- | 9.3
Subtotal | -- | -- | -- | -- | -- | -- | 4401.5
Annual Funding TY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2007 | -- | 124.5 | -- | -- | 124.5 | -- | 124.5
2008 | 6 | 1171.5 | -- | 40 | 1211.5 | 11.9 | 1223.4
2009 | 7 | 1365.1 | -- | 237.1 | 1602.2 | 273.2 | 1875.4
2010 | 20 | 3338.8 | -- | 651.1 | 3989.9 | 722.6 | 4712.5
2011 | 20 | 3003 | -- | 629.8 | 3632.8 | 1101.5 | 4734.3
2012 | 21 | 3003.8 | -- | 785.6 | 3789.4 | 1314.8 | 5104.2
2013 | 38 | 4260.7 | -- | 854.2 | 5114.9 | 2028.6 | 7143.5
2014 | 37 | 3867.5 | -- | 726.9 | 4594.4 | 1840.3 | 6434.7
2015 | 43 | 4172.2 | -- | 626.6 | 4798.8 | 1934.3 | 6733.1
2016 | 50 | 4524.5 | -- | 427.5 | 4952 | 963.1 | 5915.1
2017 | 50 | 4431.9 | -- | 424.4 | 4856.3 | 1094.7 | 5951
2018 | 50 | 4321.9 | -- | 412.5 | 4734.4 | 936.6 | 5671
2019 | 50 | 4329.1 | -- | 401.5 | 4730.6 | 798.2 | 5528.8
2020 | 50 | 4347.4 | -- | 388.5 | 4735.9 | 754.5 | 5490.4
2021 | 50 | 4391.6 | -- | 391.3 | 4782.9 | 696.7 | 5479.6
2022 | 50 | 4428.2 | -- | 389.8 | 4818 | 642.9 | 5460.9
2023 | 50 | 4307.3 | -- | 351.5 | 4658.8 | 529.3 | 5188.1
2024 | 38 | 3273.3 | -- | 241 | 3514.3 | 334.2 | 3848.5
2025 | 25 | 2165.6 | -- | 178.1 | 2343.7 | 194.7 | 2538.4
2026 | 25 | 1966.9 | -- | 108.5 | 2075.4 | 208.2 | 2283.6
Subtotal | 680 | 66794.8 | -- | 8265.9 | 75060.7 | 16380.3 | 91441
Annual Funding BY$
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2007 | -- | 107.8 | -- | -- | 107.8 | -- | 107.8
2008 | 6 | 1000.3 | -- | 34.1 | 1034.4 | 10.2 | 1044.6
2009 | 7 | 1152.2 | -- | 200.1 | 1352.3 | 230.6 | 1582.9
2010 | 20 | 2781.7 | -- | 542.4 | 3324.1 | 602 | 3926.1
2011 | 20 | 2463.3 | -- | 516.6 | 2979.9 | 903.5 | 3883.4
2012 | 21 | 2423.1 | -- | 633.7 | 3056.8 | 1060.7 | 4117.5
2013 | 38 | 3379.6 | -- | 677.6 | 4057.2 | 1609 | 5666.2
2014 | 37 | 3016.4 | -- | 566.9 | 3583.3 | 1435.4 | 5018.7
2015 | 43 | 3199.7 | -- | 480.5 | 3680.2 | 1483.5 | 5163.7
2016 | 50 | 3411.9 | -- | 322.4 | 3734.3 | 726.2 | 4460.5
2017 | 50 | 3286.2 | -- | 314.7 | 3600.9 | 811.7 | 4412.6
2018 | 50 | 3151 | -- | 300.7 | 3451.7 | 683 | 4134.7
2019 | 50 | 3103.5 | -- | 287.8 | 3391.3 | 572.3 | 3963.6
2020 | 50 | 3064.6 | -- | 273.9 | 3338.5 | 531.8 | 3870.3
2021 | 50 | 3044 | -- | 271.2 | 3315.2 | 482.9 | 3798.1
2022 | 50 | 3018 | -- | 265.8 | 3283.8 | 438.1 | 3721.9
2023 | 50 | 2886.6 | -- | 235.6 | 3122.2 | 354.6 | 3476.8
2024 | 38 | 2156.9 | -- | 158.8 | 2315.7 | 220.3 | 2536
2025 | 25 | 1403.2 | -- | 115.3 | 1518.5 | 126.2 | 1644.7
2026 | 25 | 1253.1 | -- | 69.1 | 1322.2 | 132.7 | 1454.9
Subtotal | 680 | 49303.1 | -- | 6267.2 | 55570.3 | 12414.7 | 67985
Cost Quantity Information
1506 ¦ Procurement ¦ Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2002 $M
2007 | -- | --
2008 | 6 | 1000.3
2009 | 7 | 1152.2
2010 | 20 | 2781.7
2011 | 20 | 2463.3
2012 | 21 | 2423.1
2013 | 38 | 3379.6
2014 | 37 | 3016.4
2015 | 43 | 3199.7
2016 | 50 | 3411.9
2017 | 50 | 3286.2
2018 | 50 | 3151
2019 | 50 | 3103.5
2020 | 50 | 3064.6
2021 | 50 | 3044
2022 | 50 | 3048
2023 | 50 | 2886.6
2024 | 38 | 2186.9
2025 | 25 | 1433.2
2026 | 25 | 1270.9
Subtotal | 680 | 49303.1
Annual Funding TY$
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | 104.5 | -- | -- | 104.5 | -- | 104.5
2007 | 2 | 412.1 | -- | 43.4 | 455.5 | 48.9 | 504.4
2008 | 6 | 949.4 | -- | 177.5 | 1126.9 | 138.9 | 1265.8
2009 | 7 | 985.4 | -- | 286.5 | 1271.9 | 177.6 | 1449.5
2010 | 10 | 1223.6 | -- | 456.6 | 1680.2 | 380.1 | 2060.3
2011 | 23 | 2365.3 | -- | 546.5 | 2911.8 | 824.5 | 3736.3
2012 | 24 | 2264.1 | -- | 626.5 | 2890.6 | 719 | 3609.6
2013 | 33 | 2701.4 | -- | 466.2 | 3167.6 | 707.5 | 3875.1
2014 | 53 | 3688.6 | -- | 523.7 | 4212.3 | 878.7 | 5091
2015 | 70 | 4525.6 | -- | 440.1 | 4965.7 | 717.7 | 5683.4
2016 | 80 | 4414.9 | -- | 386.8 | 4801.7 | 902.4 | 5704.1
2017 | 80 | 4380.7 | -- | 372.8 | 4753.5 | 784.5 | 5538
2018 | 80 | 4226 | -- | 361.6 | 4587.6 | 748.6 | 5336.2
2019 | 80 | 4196.1 | -- | 350.9 | 4547 | 713.7 | 5260.7
2020 | 80 | 4144.5 | -- | 337.5 | 4482 | 726.3 | 5208.3
2021 | 80 | 4122.1 | -- | 337.4 | 4459.5 | 742.2 | 5201.7
2022 | 80 | 4132.8 | -- | 335.3 | 4468.1 | 678.5 | 5146.6
2023 | 80 | 4098.3 | -- | 334.7 | 4433 | 685.6 | 5118.6
2024 | 80 | 4128 | -- | 297.3 | 4425.3 | 699.5 | 5124.8
2025 | 80 | 4129.4 | -- | 297.4 | 4426.8 | 713 | 5139.8
2026 | 80 | 4110.5 | -- | 295.6 | 4406.1 | 587.3 | 4993.4
2027 | 80 | 4154.7 | -- | 300.5 | 4455.2 | 660.1 | 5115.3
2028 | 80 | 4177.3 | -- | 300.6 | 4477.9 | 629 | 5106.9
2029 | 80 | 4164.2 | -- | 298.1 | 4462.3 | 556.8 | 5019.1
2030 | 80 | 4151 | -- | 294.1 | 4445.1 | 412.9 | 4858
2031 | 80 | 4138 | -- | 292.3 | 4430.3 | 375.2 | 4805.5
2032 | 80 | 4125.8 | -- | 291.2 | 4417 | 372.7 | 4789.7
2033 | 80 | 4114.6 | -- | 281 | 4395.6 | 371.4 | 4767
2034 | 80 | 3803.3 | -- | 175.2 | 3978.5 | 371.1 | 4349.6
2035 | 15 | 917.3 | -- | 40.6 | 957.9 | 99.1 | 1057
Subtotal | 1763 | 99049.5 | -- | 9547.9 | 108597.4 | 16422.8 | 125020.2
Cost Quantity Information
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M
2006 | -- | --
2007 | 2 | 412.1
2008 | 6 | 949.4
2009 | 7 | 985.4
2010 | 10 | 1223.6
2011 | 23 | 2365.3
2012 | 24 | 2264.1
2013 | 33 | 2701.4
2014 | 53 | 3688.6
2015 | 70 | 4525.6
2016 | 80 | 4414.9
2017 | 80 | 4380.7
2018 | 80 | 4226
2019 | 80 | 4196.1
2020 | 80 | 4144.5
2021 | 80 | 4122.1
2022 | 80 | 4132.8
2023 | 80 | 4098.3
2024 | 80 | 4128
2025 | 80 | 4129.4
2026 | 80 | 4110.5
2027 | 80 | 4154.7
2028 | 80 | 4177.3
2029 | 80 | 4164.2
2030 | 80 | 4151
2031 | 80 | 4138
2032 | 80 | 4155.8
2033 | 80 | 4144.6
2034 | 80 | 3843.3
2035 | 15 | 921.8
Subtotal | 1763 | 99049.5
Annual Funding TY$
1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | Total Program TY $M
2004 | 24.4
2005 | --
2006 | --
2007 | --
2008 | --
2009 | --
2010 | 3
Subtotal | 27.4
Annual Funding BY$
1205 ¦ MILCON ¦ Military Construction, Navy and Marine Corps
Fiscal Year | Total Program BY 2002 $M
2004 | 22.8
2005 | --
2006 | --
2007 | --
2008 | --
2009 | --
2010 | 2.5
Subtotal | 25.3
Annual Funding TY$
3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | Total Program TY $M
2004 | 20.1
2005 | 10.6
2006 | --
2007 | --
2008 | 74.3
2009 | 22
2010 | 73.4
2011 | 139.7
2012 | 73.8
2013 | 82.3
2014 | --
2015 | 27.6
Subtotal | 523.8
Annual Funding BY$
3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | Total Program TY $M
2004 | 18.7
2005 | 9.6
2006 | --
2007 | --
2008 | 63.4
2009 | 18.6
2010 | 61.2
2011 | 114.6
2012 | 59.5
2013 | 65.3
2014 | --
2015 | 21.2
Subtotal | 432.1

## Unit Cost
| BY2002 $M | BY2002 $M
Unit Cost | Current UCR Baseline (MAR 2007 APB) | Current Estimate (DEC 2009 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 212580.8 | 191632.9
Quantity | 2458 | 2457
Unit Cost | 86.485 | 77.995 | 0
Average Procurement Unit Cost (APUC)
Cost | 168980.8 | 149403.6
Quantity | 2443 | 2443
Unit Cost | 69.169 | 61.156 | 0
| BY2002 $M | BY2002 $M
Unit Cost | Original UCR Baseline (OCT 2001 APB) | Current Estimate (DEC 2009 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 177100 | 238598.6
Quantity | 2866 | 2457
Unit Cost | 61.793 | 97.11 | 57.15
Average Procurement Unit Cost (APUC)
Cost | 143300 | 193005.2
Quantity | 2852 | 2443
Unit Cost | 50.245 | 79.003 | 57.24
TY $M
Unit Cost | Current UCR Baseline (MAR 2007 APB) | Current Estimate (DEC 2009 SAR) | TY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 278535.5 | 328252.9
Unit Cost | 113.318 | 133.599 | 17.9
Average Procurement Unit Cost (APUC)
Cost | 23173.5 | 277533.6
Unit Cost | 94.857 | 113.604 | 19.76
TY $M
Unit Cost | Original UCR Baseline (OCT 2001 APB) | Current Estimate (DEC 2009 SAR) | TY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 233000 | 328252.9
Unit Cost | 81.298 | 133.599 | 64.33
Average Procurement Unit Cost (APUC)
Cost | 196600 | 277533.6
Unit Cost | 68.934 | 113.604 | 64.8
Nunn-McCurdy Breach
Unit Cost Breach Data
Changes from Previous SAR | $M/Qty | Percent
PAUC (BY $M) | 97.11 | 13.56
APUC (BY $M) | 79.003 | 13.93
PAUC Quantity | 2457 | 0
PAUC (TY $M) | 133.599 | 9.8
APUC (TY $M) | 113.604 | 9.29
Initial SAR Information DEC 1996 | BY1994 $M | TY $M
Program Acquisition Cost | 18860.4 | 23165.9

## Unit Cost History
|  | BY2002 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2001-10-01 | 61.793 | 50.245 | 81.298 | 68.934
APB as of January 2006 | 2004-03-01 | 78.592 | 61.195 | 100.407 | 81.826
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | 2004-03-01 | 78.592 | 61.195 | 100.407 | 81.826
Current APB | 2007-03-01 | 86.485 | 69.169 | 113.318 | 94.857
Prior Annual SAR | 2007-12-01 | 85.511 | 69.341 | 121.679 | 103.951
Current Estimate | 2009-12-01 | 97.11 | 79.003 | 133.599 | 113.604
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Dev Est | Changes | [7 empty] | PAUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
81.298 | -2.684 | 3.246 | 12.927 | 5.205 | 29.122 | 0 | 4.485 | 52.301 | 133.599
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes | [7 empty] | PAUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
68.934 | -3.092 | 1.131 | 9.781 | 3.853 | 28.486 | 0 | 4.511 | 44.67 | 113.604

## Cost Variance
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 34400 | 196600 | 2000 | 233000
Previous Changes
Economic | 1197.7 | 4103.3 | 8.9 | 5309.9
Quantity | -- | -25434.9 | -- | -25434.9
Schedule | 7866.9 | 21747.2 | -- | 29614.1
Engineering | 3122.5 | 9414 | 252.8 | 12789.3
Estimating | -2217.2 | 45486 | -1740.5 | 41528.3
Other | -- | -- | -- | --
Support | -- | 2036.1 | -- | 2036.1
Subtotal | 9969.9 | 57351.7 | -1478.8 | 65842.8
Current Changes
Economic | -234.5 | -11656.6 | -13.8 | -11904.9
Quantity | 157 | -- | -- | 157
Schedule | -- | 2148.3 | -- | 2148.3
Engineering | -- | -- | -- | --
Estimating | 5875.7 | 24106 | 43.8 | 30025.5
Other | -- | -- | -- | --
Support | -- | 8984.2 | -- | 8984.2
Subtotal | 5798.2 | 23581.9 | 30 | 29410.1
Total Changes | 15768.1 | 80933.6 | -1448.8 | 95252.9
CE - Cost Variance | 50168.1 | 277533.6 | 551.2 | 328252.9
CE - Cost & Funding | 50168.1 | 277533.6 | 551.2 | 328252.9
Summary Base Year 2002 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 32300 | 143300 | 1500 | 177100
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -16249.1 | -- | -16249.1
Schedule | 6779.4 | 2017.7 | -- | 8797.1
Engineering | 2814.6 | 6644.8 | 227.3 | 9686.7
Estimating | -1704.6 | 33745.5 | -1303.4 | 30737.5
Other | -- | -- | -- | --
Support | -- | -57.7 | -- | -57.7
Subtotal | 7889.4 | 26101.2 | -1076.1 | 32914.5
Current Changes
Economic | -- | -- | -- | --
Quantity | 130.6 | -- | -- | 130.6
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 4816 | 16793.3 | 33.5 | 21642.8
Other | -- | -- | -- | --
Support | -- | 6810.7 | -- | 6810.7
Subtotal | 4946.6 | 23604 | 33.5 | 28584.1
Total Changes | 12836 | 49705.2 | -1042.6 | 61498.6
CE - Cost Variance | 45136 | 193005.2 | 457.4 | 238598.6
CE - Cost & Funding | 45136 | 193005.2 | 457.4 | 238598.6
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -234.5
Adjustment for current and prior escalation. (Estimating) | 87.6 | 100.9
Revised International funding profile. (Estimating) | 0.7 | -1.7
Added additional CV flight test article to reduce risk in accordance with the restructure. (Air Force) (Quantity) | 65.4 | 78.5
Added additional CV flight test article to reduce risk in accordance with the restructure. (Navy) (Quantity) | 65.2 | 78.5
Increase for F136 engine Congressional adds in FY09 and FY10 appropriations. (AirForce) (Estimating) | 364.9 | 430
Increase for F136 engine Congressional adds in FY09 and FY10 appropriations. (Navy) (Estimating) | 365.7 | 431.6
Increase due to revised estimate of required risk funding based on OSD led independent program assessments (Air Force) (Estimating) | 1362.5 | 1672
Increase due to revised estimate of required risk funding based on OSD led independent program assessments (Navy). (Estimating) | 1360.3 | 1672
Increase for Lockheed Martin and Pratt & Whitney cost overruns. (Air Force) (Estimating) | 631.6 | 775.9
Increase for Lockheed Martin and Pratt & Whitney cost overruns. (Navy) (Estimating) | 642.7 | 795
RDT&E Subtotal | 4946.6 | 5798.2
Procurement | $M
| Base | Then
Current Change Explanations | Year | Year
Revised escalation indices. (Economic) | N/A | -11656.6
Adjustment for current and prior escalation. (Estimating) | 101 | 120.7
Increase for revised DoD procurement quantity profile, (i.e., lower nearterm quantity ramp, and procurement completion extended one year to FY 2035). (Air Force) (Schedule) | 0 | 1505.2
Increase for revised DoD procurement quantity profile, (i.e., lower nearterm quantity ramp, and procurement completion extended one year to FY 2026). (Navy) (Schedule) | 0 | 643.1
Increase for revised slower International procurement quantity profile. (Air Force) (Estimating) | 526 | 786.9
Increase for revised slower International procurement quantity profile. (Navy) (Estimating) | 306.1 | 405
Increase due to incorporation of latest prime and subcontractor labor rates. (Air Force) (Estimating) | 1747.2 | 2615.2
Increase due to incorporation of latest prime and subcontractor labor rates. (Navy) (Estimating) | 985.8 | 1304.5
Increase due to wing manufacturing performance, change in subcontractor manufacturing plan, cost of purchased parts, and commonality update. (Air Force) (Estimating) | 5618.3 | 8314.8
Increase due to wing manufacturing performance, change in subcontractor manufacturing plan, cost of purchased parts, and commonality update; partially offset by the decrease due to the transition from weight-based estimating to standard-hour content estimating. (Navy) (Estimating) | 636.8 | 926.3
Increases in Propulsion estimate due to raw material prices and hardware/configuration changes. (Air Force) (Estimating) | 4046.4 | 6050.6
Increases in Propulsion estimate due to raw material prices, hardware/configuration changes, exchange rate updates, and higher than expected lift system hardware costs. (Navy) (Estimating) | 1958.9 | 2591.6
Increase in non-recurring/ancillary estimate due to estimate maturity and increase to Diminishing Manufacturing Sources. (Air Force) (Estimating) | 259 | 291.4
Increase in non-recurring/ancillary estimate due to estimate maturity and increase to Diminishing Manufacturing Sources. (Navy) (Estimating) | 605.8 | 696.6
Adjustment for current and prior escalation. (Support) | 13.4 | 16.2
Initial Spares increase due to revised estimate. (Air Force) (Support) | 1030 | 1652.8
Initial Spares increase due to revised estimate. (Navy) (Support) | 421.7 | 539.8
Increase due to cost maturity, definition of customer requirements, and further definition of Service beddown plans. (Air Force) (Support) | 2072.2 | 2686.5
Increase due to cost maturity, definition of customer requirements, and further definition of Service beddown plans. (Navy) (Support) | 3275.4 | 4091.3
Correction to align support and flyaway. (Subtotal) | 0 | 0
Estimating | 2 | 2.4
(Support) | (-2.0) | (-2.4)
Procurement Subtotal | 23604 | 23581.9
MILCON | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices (Economic) | N/A | -13.8
Adjustment for currrent and prior escalation (Estimating) | 3.4 | 4.1
Increase for revised MILCON planning (Air Force) (Estimating) | 27.6 | 36.7
Increase for revised MILCON planning (Navy) (Estimating) | 2.5 | 3
MILCON Subtotal | 33.5 | 30

## Deliveries and ExpendituresDel
Deliveries and Expenditures
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 14 | 0
Production | 0 | 0 | 2443 | 0
Total Program Quantities Delivered | 0 | 0 | 2457 | 0
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 328252.9 | Years Appropriated | 17
Expenditures To Date | 37768.4 | Percent Years Appropriated | 40.48
Percent Expended | 11.51 | Appropriated to Date | 56069.2
Total Funding Years | 42 | Percent Appropriated | 17.08

## Operating and Support Cost
Cost Element | JSF Cost per Flying Hour ($) | F-16C/D Cost per Flying Hour ($)
Mission Pay & Allowance | 4.672 | 5.249
Unit Level Consumption | 7.88 | 6.369
Intermediate Maintenance | 0 | 0
Depot Maintenance | 0.762 | 0.98
Contractor Support | 0.389 | 0.13
Sustaining Support | 1.487 | 0.463
Indirect | -- | --
Other | -- | --
Total Unitized Cost (Base Year 2002 $) | 15.19 | 13.191
Total O&S Costs $M | JSF | F-16C/D
Base Year | 370844.1 | --
Then Year | 915761.4 | --