## CostSummary
Cost Summary
Total Acquisition Cost and Quantity
|  |  | BY2002 | TY $M
| BY $M |  | $M
Appropriation | SAR Baseline Dev Est | Current APB Objective/Threshold | Current Estimate
|  |  |  | SAR Baseline Dev Est | Current APB Objective | Current Estimate
RDT&E | 32300 | -- | 48385.8 | 34400 | -- | 54396.7
Procurement | 143300 | -- | 221756.5 | 196600 | -- | 324444.9
Flyaway | 121215.6 | -- | 186521.2 | 166349.7 | -- | 274644.5
Recurring | 116093.7 | -- | 166535.1 | 159390.4 | -- | 245980.9
Non Recurring | 5121.9 | -- | 19986.1 | 6959.3 | -- | 28663.6
Support | 22084.4 | -- | 35235.3 | 30250.3 | -- | 49800.4
Other Support | 15403.4 | -- | 20343.7 | 21109.3 | -- | 27841.9
Initial Spares | 6681 | -- | 14891.6 | 9141 | -- | 21958.5
MILCON | 1500 | -- | 457.4 | 2000 | -- | 551.2
Acq O&M | 0 | -- | 0 | 0 | -- | 0
Total | 177100 | -- | 270599.7 | 233000 | -- | 379392.8
Total Acquisition Quantity
| SAR Baseline |  | Current Estimate
Quantity | Dev Est | Current APB
RDT&E | 14 | 0 | 14
Procurement | 2852 | 0 | 2443
Total | 2866 | 0 | 2457

## Funding Summary
Appropriation and Quantity Summary
FY 2012 President's Budget / December 2010 SAR (TY$ M)
To
Appropriation | Prior | FY2011 | FY2012 | FY2013 | FY2014 | FY2015 | FY2016 | Complete | Total
RDT&E | 41413.3 | 2450.1 | 2720.5 | 2583.4 | 2263.5 | 1733.1 | 1232.8 | 0 | 54396.7
Procurement | 14084.6 | 7674.5 | 6948.9 | 7923.1 | 9829.7 | 11749.9 | 14290.4 | 251943.8 | 324444.9
MILCON | 227.8 | 139.7 | 73.8 | 82.3 | 0 | 27.6 | 0 | 0 | 551.2
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2012 Total | 55725.7 | 10264.3 | 9743.2 | 10588.8 | 12093.2 | 13510.6 | 15523.2 | 251943.8 | 379392.8
PB 2011 Total | 56069.2 | 11902.5 | 12109.3 | 14119.7 | 14334.1 | 14657.4 | 13519.4 | 191541.3 | 328252.9
Delta | -343.5 | -1638.2 | -2366.1 | -3530.9 | -2240.9 | -1146.8 | 2003.8 | 60402.5 | 51139.9
Quantity | Quantity
Quantity | Undistributed | Prior | FY2011 | FY2012 | FY2013 | FY2014 | FY2015 | FY2016 | To Complete | Total
Development | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Production | 0 | 58 | 32 | 32 | 42 | 62 | 81 | 108 | 2028 | 2443
PB 2012 Total | 14 | 58 | 32 | 32 | 42 | 62 | 81 | 108 | 2028 | 2457
PB 2011 Total | 14 | 58 | 43 | 45 | 71 | 90 | 113 | 130 | 1893 | 2457
Delta | 0 | 0 | -11 | -13 | -29 | -28 | -32 | -22 | 135 | 0
Annual Funding TY$, RDT&E, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 29.5
1995 | -- | -- | -- | -- | -- | -- | 98.3
1996 | -- | -- | -- | -- | -- | -- | 80.4
1997 | -- | -- | -- | -- | -- | -- | 243.3
1998 | -- | -- | -- | -- | -- | -- | 448.2
1999 | -- | -- | -- | -- | -- | -- | 471.3
2000 | -- | -- | -- | -- | -- | -- | 238.4
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 721.3
2003 | -- | -- | -- | -- | -- | -- | 1640.9
2004 | -- | -- | -- | -- | -- | -- | 2081.4
2005 | -- | -- | -- | -- | -- | -- | 2083.8
2006 | -- | -- | -- | -- | -- | -- | 2187.1
2007 | -- | -- | -- | -- | -- | -- | 2109.4
2008 | -- | -- | -- | -- | -- | -- | 1848.9
2009 | -- | -- | -- | -- | -- | -- | 1704.3
2010 | -- | -- | -- | -- | -- | -- | 1886.2
2011 | -- | -- | -- | -- | -- | -- | 1318
2012 | -- | -- | -- | -- | -- | -- | 1310.3
2013 | -- | -- | -- | -- | -- | -- | 1373.5
2014 | -- | -- | -- | -- | -- | -- | 1330
2015 | -- | -- | -- | -- | -- | -- | 1124.9
2016 | -- | -- | -- | -- | -- | -- | 871.7
Subtotal | 9 | -- | -- | -- | -- | -- | 25542.3
Annual Funding BY$, RDT&E, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1997 | -- | -- | -- | -- | -- | -- | 255.9
1998 | -- | -- | -- | -- | -- | -- | 467.5
1999 | -- | -- | -- | -- | -- | -- | 485.9
2000 | -- | -- | -- | -- | -- | -- | 242.2
2001 | -- | -- | -- | -- | -- | -- | 342
2002 | -- | -- | -- | -- | -- | -- | 715.7
2003 | -- | -- | -- | -- | -- | -- | 1604.7
2004 | -- | -- | -- | -- | -- | -- | 1980.2
2005 | -- | -- | -- | -- | -- | -- | 1931.8
2006 | -- | -- | -- | -- | -- | -- | 1966.1
2007 | -- | -- | -- | -- | -- | -- | 1851.1
2008 | -- | -- | -- | -- | -- | -- | 1593.6
2009 | -- | -- | -- | -- | -- | -- | 1451.5
2010 | -- | -- | -- | -- | -- | -- | 1588.2
2011 | -- | -- | -- | -- | -- | -- | 1094.6
2012 | -- | -- | -- | -- | -- | -- | 1071.6
2013 | -- | -- | -- | -- | -- | -- | 1104.9
2014 | -- | -- | -- | -- | -- | -- | 1052.1
2015 | -- | -- | -- | -- | -- | -- | 875
2016 | -- | -- | -- | -- | -- | -- | 666.7
Subtotal | 9 | -- | -- | -- | -- | -- | 22565.8
Annual Funding TY$, RDT&E, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | -- | -- | -- | -- | -- | -- | 83.8
1996 | -- | -- | -- | -- | -- | -- | 81.3
1997 | -- | -- | -- | -- | -- | -- | 251.6
1998 | -- | -- | -- | -- | -- | -- | 444.3
1999 | -- | -- | -- | -- | -- | -- | 456.1
2000 | -- | -- | -- | -- | -- | -- | 249.1
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 712.4
2003 | -- | -- | -- | -- | -- | -- | 1610.6
2004 | -- | -- | -- | -- | -- | -- | 2019.9
2005 | -- | -- | -- | -- | -- | -- | 2080.1
2006 | -- | -- | -- | -- | -- | -- | 2264.8
2007 | -- | -- | -- | -- | -- | -- | 2074
2008 | -- | -- | -- | -- | -- | -- | 1955
2009 | -- | -- | -- | -- | -- | -- | 1742.1
2010 | -- | -- | -- | -- | -- | -- | 2033.5
2011 | -- | -- | -- | -- | -- | -- | 1043.6
2012 | -- | -- | -- | -- | -- | -- | 1387.9
2013 | -- | -- | -- | -- | -- | -- | 1198.3
2014 | -- | -- | -- | -- | -- | -- | 933.5
2015 | -- | -- | -- | -- | -- | -- | 608.2
2016 | -- | -- | -- | -- | -- | -- | 361.1
Subtotal | 5 | -- | -- | -- | -- | -- | 23932.4
Annual Funding BY$, RDT&E, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1995 | -- | -- | -- | -- | -- | -- | 90.7
1996 | -- | -- | -- | -- | -- | -- | 86.5
1997 | -- | -- | -- | -- | -- | -- | 264.6
1998 | -- | -- | -- | -- | -- | -- | 463.4
1999 | -- | -- | -- | -- | -- | -- | 470.2
2000 | -- | -- | -- | -- | -- | -- | 253.1
2001 | -- | -- | -- | -- | -- | -- | 342
2002 | -- | -- | -- | -- | -- | -- | 706.9
2003 | -- | -- | -- | -- | -- | -- | 1575.1
2004 | -- | -- | -- | -- | -- | -- | 1921.7
2005 | -- | -- | -- | -- | -- | -- | 1928.4
2006 | -- | -- | -- | -- | -- | -- | 2036
2007 | -- | -- | -- | -- | -- | -- | 1820
2008 | -- | -- | -- | -- | -- | -- | 1685.1
2009 | -- | -- | -- | -- | -- | -- | 1483.7
2010 | -- | -- | -- | -- | -- | -- | 1712.3
2011 | -- | -- | -- | -- | -- | -- | 866.7
2012 | -- | -- | -- | -- | -- | -- | 1135.1
2013 | -- | -- | -- | -- | -- | -- | 964
2014 | -- | -- | -- | -- | -- | -- | 738.4
2015 | -- | -- | -- | -- | -- | -- | 473.1
2016 | -- | -- | -- | -- | -- | -- | 276.2
Subtotal | 5 | -- | -- | -- | -- | -- | 21293.2
Annual Funding TY$, RDT&E, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 28.9
1997 | -- | -- | -- | -- | -- | -- | 68.2
1998 | -- | -- | -- | -- | -- | -- | 20.9
Subtotal | -- | -- | -- | -- | -- | -- | 118
Annual Funding BY$, RDT&E, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1996 | -- | -- | -- | -- | -- | -- | 30.8
1997 | -- | -- | -- | -- | -- | -- | 71.7
1998 | -- | -- | -- | -- | -- | -- | 21.8
Subtotal | -- | -- | -- | -- | -- | -- | 124.3
Annual Funding TY$, RDT&E, Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 14
1997 | -- | -- | -- | -- | -- | -- | 71
1998 | -- | -- | -- | -- | -- | -- | 77.2
1999 | -- | -- | -- | -- | -- | -- | 54.7
2000 | -- | -- | -- | -- | -- | -- | 34.5
2001 | -- | -- | -- | -- | -- | -- | 2.5
2002 | -- | -- | -- | -- | -- | -- | 306.4
2003 | -- | -- | -- | -- | -- | -- | 425.8
2004 | -- | -- | -- | -- | -- | -- | 517.8
2005 | -- | -- | -- | -- | -- | -- | 758.1
2006 | -- | -- | -- | -- | -- | -- | 802.5
2007 | -- | -- | -- | -- | -- | -- | 710.3
2008 | -- | -- | -- | -- | -- | -- | 552.7
2009 | -- | -- | -- | -- | -- | -- | 244.6
2010 | -- | -- | -- | -- | -- | -- | 109.5
2011 | -- | -- | -- | -- | -- | -- | 88.5
2012 | -- | -- | -- | -- | -- | -- | 22.3
2013 | -- | -- | -- | -- | -- | -- | 11.6
Subtotal | -- | -- | -- | -- | -- | -- | 4804
Annual Funding BY$, RDT&E, Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
1996 | -- | -- | -- | -- | -- | -- | 14.9
1997 | -- | -- | -- | -- | -- | -- | 74.7
1998 | -- | -- | -- | -- | -- | -- | 80.5
1999 | -- | -- | -- | -- | -- | -- | 56.4
2000 | -- | -- | -- | -- | -- | -- | 35.1
2001 | -- | -- | -- | -- | -- | -- | 2.5
2002 | -- | -- | -- | -- | -- | -- | 304
2003 | -- | -- | -- | -- | -- | -- | 416.4
2004 | -- | -- | -- | -- | -- | -- | 492.6
2005 | -- | -- | -- | -- | -- | -- | 702.8
2006 | -- | -- | -- | -- | -- | -- | 721.4
2007 | -- | -- | -- | -- | -- | -- | 623.3
2008 | -- | -- | -- | -- | -- | -- | 476.4
2009 | -- | -- | -- | -- | -- | -- | 208.3
2010 | -- | -- | -- | -- | -- | -- | 92.2
2011 | -- | -- | -- | -- | -- | -- | 73.5
2012 | -- | -- | -- | -- | -- | -- | 18.2
2013 | -- | -- | -- | -- | -- | -- | 9.3
Subtotal | -- | -- | -- | -- | -- | -- | 4402.5
Annual Funding TY$, Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2007 | -- | 124.5 | -- | -- | 124.5 | -- | 124.5
2008 | 6 | 1171.5 | -- | 40 | 1211.5 | 11.9 | 1223.4
2009 | 7 | 1365.1 | -- | 237.1 | 1602.2 | 273.2 | 1875.4
2010 | 20 | 3100.5 | -- | 651.1 | 3751.6 | 722.6 | 4474.2
2011 | 10 | 1803.1 | -- | 614.5 | 2417.6 | 807.9 | 3225.5
2012 | 13 | 1803.5 | -- | 398.6 | 2202.1 | 931.2 | 3133.3
2013 | 18 | 2288.2 | -- | 563 | 2851.2 | 985.6 | 3836.8
2014 | 22 | 2593 | -- | 399.1 | 2992.1 | 1211.6 | 4203.7
2015 | 31 | 3280.2 | -- | 465 | 3745.2 | 1510.8 | 5256
2016 | 38 | 3799.6 | -- | 538.2 | 4337.8 | 1478.6 | 5816.4
2017 | 50 | 5157.7 | -- | 722.3 | 5880 | 1598.2 | 7478.2
2018 | 50 | 4983.6 | -- | 542 | 5525.6 | 1442.7 | 6968.3
2019 | 50 | 4959.7 | -- | 531.8 | 5491.5 | 1270.7 | 6762.2
2020 | 50 | 5009.1 | -- | 525.3 | 5534.4 | 1335.9 | 6870.3
2021 | 50 | 5100.2 | -- | 532 | 5632.2 | 1240.1 | 6872.3
2022 | 50 | 5167 | -- | 536.9 | 5703.9 | 1105.9 | 6809.8
2023 | 50 | 5173.5 | -- | 542.7 | 5716.2 | 1004.9 | 6721.1
2024 | 50 | 5321.1 | -- | 548.9 | 5870 | 790.6 | 6660.6
2025 | 50 | 5400.3 | -- | 544.3 | 5944.6 | 718.5 | 6663.1
2026 | 50 | 5106.5 | -- | 428.9 | 5535.4 | 692.8 | 6228.2
2027 | 15 | 1960.9 | -- | 173.8 | 2134.7 | 350.9 | 2485.6
Subtotal | 680 | 74668.8 | -- | 9535.5 | 84204.3 | 19484.6 | 103688.9
Annual Funding BY$, Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2007 | -- | 107.8 | -- | -- | 107.8 | -- | 107.8
2008 | 6 | 1000.6 | -- | 34.1 | 1034.7 | 10.2 | 1044.9
2009 | 7 | 1152.5 | -- | 200.1 | 1352.6 | 230.7 | 1583.3
2010 | 20 | 2583.8 | -- | 542.7 | 3126.5 | 602.1 | 3728.6
2011 | 10 | 1480.6 | -- | 504.6 | 1985.2 | 663.4 | 2648.6
2012 | 13 | 1457.4 | -- | 322.1 | 1779.5 | 752.5 | 2532
2013 | 18 | 1818.4 | -- | 447.4 | 2265.8 | 783.3 | 3049.1
2014 | 22 | 2026.2 | -- | 311.9 | 2338.1 | 946.8 | 3284.9
2015 | 31 | 2520.4 | -- | 357.3 | 2877.7 | 1160.8 | 4038.5
2016 | 38 | 2870.7 | -- | 406.6 | 3277.3 | 1117.1 | 4394.4
2017 | 50 | 3831.6 | -- | 536.6 | 4368.2 | 1187.2 | 5555.4
2018 | 50 | 3640.4 | -- | 395.9 | 4036.3 | 1053.8 | 5090.1
2019 | 50 | 3562.3 | -- | 382 | 3944.3 | 912.7 | 4857
2020 | 50 | 3537.7 | -- | 371 | 3908.7 | 943.5 | 4852.2
2021 | 50 | 3541.8 | -- | 369.4 | 3911.2 | 861.2 | 4772.4
2022 | 50 | 3528.2 | -- | 366.6 | 3894.8 | 755.2 | 4650
2023 | 50 | 3473.6 | -- | 364.4 | 3838 | 674.7 | 4512.7
2024 | 50 | 3513 | -- | 362.4 | 3875.4 | 521.9 | 4397.3
2025 | 50 | 3505.7 | -- | 353.3 | 3859 | 466.4 | 4325.4
2026 | 50 | 3259.5 | -- | 273.8 | 3533.3 | 442.2 | 3975.5
2027 | 15 | 1230.7 | -- | 109.1 | 1339.8 | 220.3 | 1560.1
Subtotal | 680 | 53642.9 | -- | 7011.3 | 60654.2 | 14306 | 74960.2
Cost Quantity Information, Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2002 $M
2007 | -- | --
2008 | 6 | 1000.6
2009 | 7 | 1152.5
2010 | 20 | 2583.8
2011 | 10 | 1480.6
2012 | 13 | 1457.4
2013 | 18 | 1818.4
2014 | 22 | 2026.2
2015 | 31 | 2520.4
2016 | 38 | 2870.7
2017 | 50 | 3831.6
2018 | 50 | 3640.4
2019 | 50 | 3562.3
2020 | 50 | 3537.7
2021 | 50 | 3541.8
2022 | 50 | 3528.2
2023 | 50 | 3473.6
2024 | 50 | 3543
2025 | 50 | 3535.7
2026 | 50 | 3289.5
2027 | 15 | 1248.5
Subtotal | 680 | 53642.9
Annual Funding TY$, Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2006 | -- | 117.4 | -- | -- | 117.4 | -- | 117.4
2007 | 2 | 475.2 | -- | 50.1 | 525.3 | 56.3 | 581.6
2008 | 6 | 1111.4 | -- | 207.8 | 1319.2 | 162.6 | 1481.8
2009 | 7 | 1170.5 | -- | 340.2 | 1510.7 | 211 | 1721.7
2010 | 10 | 1475.6 | -- | 550.6 | 2026.2 | 458.4 | 2484.6
2011 | 22 | 2902.6 | -- | 675.9 | 3578.5 | 870.5 | 4449
2012 | 19 | 2402.6 | -- | 540.4 | 2943 | 872.6 | 3815.6
2013 | 24 | 2690.1 | -- | 595.1 | 3285.2 | 801.1 | 4086.3
2014 | 40 | 3868.6 | -- | 482.8 | 4351.4 | 1274.6 | 5626
2015 | 50 | 4557.8 | -- | 534.8 | 5092.6 | 1401.3 | 6493.9
2016 | 70 | 5639.8 | -- | 656.5 | 6296.3 | 2177.7 | 8474
2017 | 80 | 6786.8 | -- | 906.1 | 7692.9 | 1455 | 9147.9
2018 | 80 | 6475.9 | -- | 675.6 | 7151.5 | 1400.5 | 8552
2019 | 80 | 6474.1 | -- | 669.1 | 7143.2 | 1331.2 | 8474.4
2020 | 80 | 6547.3 | -- | 666.3 | 7213.6 | 1423.8 | 8637.4
2021 | 80 | 6693.5 | -- | 683.5 | 7377 | 1479.4 | 8856.4
2022 | 80 | 6883.6 | -- | 698.4 | 7582 | 1419.3 | 9001.3
2023 | 80 | 6998.3 | -- | 710.5 | 7708.8 | 1427.9 | 9136.7
2024 | 80 | 7181.3 | -- | 725 | 7906.3 | 1380.1 | 9286.4
2025 | 80 | 7310 | -- | 735.6 | 8045.6 | 1330.3 | 9375.9
2026 | 80 | 7429.9 | -- | 751.7 | 8181.6 | 1235.3 | 9416.9
2027 | 80 | 7715.3 | -- | 783.9 | 8499.2 | 1306 | 9805.2
2028 | 80 | 8032 | -- | 809.4 | 8841.4 | 1186.1 | 10027.5
2029 | 80 | 8228.5 | -- | 822.7 | 9051.2 | 1001.8 | 10053
2030 | 80 | 8431.7 | -- | 835.9 | 9267.6 | 792.2 | 10059.8
2031 | 80 | 8639.2 | -- | 852.6 | 9491.8 | 746.4 | 10238.2
2032 | 80 | 8859.5 | -- | 871.4 | 9730.9 | 765.8 | 10496.7
2033 | 80 | 9082.8 | -- | 888.7 | 9971.5 | 785.3 | 10756.8
2034 | 80 | 9241.3 | -- | 856.6 | 10097.9 | 806.2 | 10904.1
2035 | 73 | 7889.5 | -- | 550.9 | 8440.4 | 757.1 | 9197.5
Subtotal | 1763 | 171312.1 | -- | 19128.1 | 190440.2 | 30315.8 | 220756
Annual Funding BY$, Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2002 $M | Non End Item Recurring Flyaway BY 2002 $M | Non Recurring Flyaway BY 2002 $M | Total Flyaway BY 2002 $M | Total Support BY 2002 $M | Total Program BY 2002 $M
2006 | -- | 104.1 | -- | -- | 104.1 | -- | 104.1
2007 | 2 | 411.6 | -- | 43.5 | 455.1 | 48.7 | 503.8
2008 | 6 | 949.2 | -- | 177.5 | 1126.7 | 138.9 | 1265.6
2009 | 7 | 988.2 | -- | 287.1 | 1275.3 | 178.2 | 1453.5
2010 | 10 | 1229.7 | -- | 458.8 | 1688.5 | 382.1 | 2070.6
2011 | 22 | 2383.4 | -- | 555.1 | 2938.5 | 714.7 | 3653.2
2012 | 19 | 1941.5 | -- | 436.7 | 2378.2 | 705.2 | 3083.4
2013 | 24 | 2137.8 | -- | 472.9 | 2610.7 | 636.7 | 3247.4
2014 | 40 | 3023 | -- | 377.3 | 3400.3 | 996 | 4396.3
2015 | 50 | 3502 | -- | 410.9 | 3912.9 | 1076.7 | 4989.6
2016 | 70 | 4260.9 | -- | 496 | 4756.9 | 1645.3 | 6402.2
2017 | 80 | 5041.8 | -- | 673.1 | 5714.9 | 1080.9 | 6795.8
2018 | 80 | 4730.7 | -- | 493.5 | 5224.2 | 1023.2 | 6247.4
2019 | 80 | 4650.1 | -- | 480.6 | 5130.7 | 956.1 | 6086.8
2020 | 80 | 4624 | -- | 470.6 | 5094.6 | 1005.6 | 6100.2
2021 | 80 | 4648.3 | -- | 474.7 | 5123 | 1027.3 | 6150.3
2022 | 80 | 4700.4 | -- | 476.9 | 5177.3 | 969.1 | 6146.4
2023 | 80 | 4698.8 | -- | 477 | 5175.8 | 958.8 | 6134.6
2024 | 80 | 4741.1 | -- | 478.6 | 5219.7 | 911.2 | 6130.9
2025 | 80 | 4745.4 | -- | 477.6 | 5223 | 863.5 | 6086.5
2026 | 80 | 4742.6 | -- | 479.8 | 5222.4 | 788.5 | 6010.9
2027 | 80 | 4842.4 | -- | 492.1 | 5334.5 | 819.7 | 6154.2
2028 | 80 | 4957 | -- | 499.5 | 5456.5 | 732 | 6188.5
2029 | 80 | 4993.3 | -- | 499.2 | 5492.5 | 608 | 6100.5
2030 | 80 | 5031.1 | -- | 498.8 | 5529.9 | 472.7 | 6002.6
2031 | 80 | 5068.6 | -- | 500.3 | 5568.9 | 437.9 | 6006.8
2032 | 80 | 5111.1 | -- | 502.7 | 5613.8 | 441.8 | 6055.6
2033 | 80 | 5152.4 | -- | 504.1 | 5656.5 | 445.5 | 6102
2034 | 80 | 5154.6 | -- | 477.8 | 5632.4 | 449.7 | 6082.1
2035 | 73 | 4327.1 | -- | 302.1 | 4629.2 | 415.3 | 5044.5
Subtotal | 1763 | 112892.2 | -- | 12974.8 | 125867 | 20929.3 | 146796.3
Cost Quantity Information, Aircraft Procurement, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2002 $M
2006 | -- | --
2007 | 2 | 411.6
2008 | 6 | 949.2
2009 | 7 | 988.2
2010 | 10 | 1229.7
2011 | 22 | 2383.4
2012 | 19 | 1941.5
2013 | 24 | 2137.8
2014 | 40 | 3023
2015 | 50 | 3502
2016 | 70 | 4260.9
2017 | 80 | 5041.8
2018 | 80 | 4730.7
2019 | 80 | 4650.1
2020 | 80 | 4624
2021 | 80 | 4648.3
2022 | 80 | 4700.4
2023 | 80 | 4698.8
2024 | 80 | 4741.1
2025 | 80 | 4745.4
2026 | 80 | 4742.6
2027 | 80 | 4842.4
2028 | 80 | 4957
2029 | 80 | 4993.3
2030 | 80 | 5031.1
2031 | 80 | 5068.6
2032 | 80 | 5141.1
2033 | 80 | 5182.4
2034 | 80 | 5184.6
2035 | 73 | 4341.2
Subtotal | 1763 | 112892.2
Annual Funding TY $, Military Construction, Navy and Marine Corps
Fiscal Year | Total Program TY $M
2004 | 24.4
2005 | --
2006 | --
2007 | --
2008 | --
2009 | --
2010 | 3
Subtotal | 27.4
Annual Funding BY $, Military Construction, Navy and Marine Corps
Fiscal Year | Total Program BY 2002 $M
2004 | 22.8
2005 | --
2006 | --
2007 | --
2008 | --
2009 | --
2010 | 2.5
Subtotal | 25.3
Annual Funding TY $, Military Construction, Air Force
Fiscal Year | Total Program TY $M
2004 | 20.1
2005 | 10.6
2006 | --
2007 | --
2008 | 74.3
2009 | 22
2010 | 73.4
2011 | 139.7
2012 | 73.8
2013 | 82.3
2014 | --
2015 | 27.6
Subtotal | 523.8
Annual Funding BY $, Military Construction, Air Force
Fiscal Year | Total Program BY 2002 $M
2004 | 18.7
2005 | 9.6
2006 | --
2007 | --
2008 | 63.4
2009 | 18.6
2010 | 61.2
2011 | 114.6
2012 | 59.5
2013 | 65.3
2014 | --
2015 | 21.2
Subtotal | 432.1

## Low Rate Initial Production
Low Rate Initial Production
| Initial LRIP Decision | Current Total LRIP
Approval Date | 2001-10-26 | 2010-02-24
Approved Quantity | 465 | 420
Reference | ADM | ADM
Start Year | 2006 | 2006
End Year | 2015 | 2018

## Foreign Military Sales
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Memo
Israel (IS) | 2010-10-07 | 19 | 2750

## Unit Cost
Unit Cost Report | BY 2002 $M | BY 2002 $M
Unit Cost | Current UCR Baseline | Current Estimate (DEC 2010 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | -- | 270599.7
Quantity | -- | 2457
Unit Cost | -- | 110.134 | --
Average Procurement Unit Cost (APUC)
Cost | -- | 221756.5
Quantity | -- | 2443
Unit Cost | -- | 90.772 | --
| BY 2002 $M | BY 2002 $M
Unit Cost | Original UCR Baseline | Current Estimate (DEC 2010 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | -- | 270599.7
Quantity | -- | 2457
Unit Cost | -- | 110.134 | --
Average Procurement Unit Cost (APUC)
Cost | -- | 221756.5
Quantity | -- | 2443
Unit Cost | -- | 90.772 | --
Unit Cost History
|  | BY 2002 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | N/A | N/A | N/A | N/A | N/A
APB as of JAN 2006 | 2004-03-01 | 78.592 | 61.195 | 100.407 | 81.826
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | 2004-03-01 | 78.592 | 61.195 | 100.407 | 81.826
Current APB | N/A | N/A | N/A | N/A | N/A
Prior Annual SAR | 2009-12-01 | 97.11 | 79.003 | 133.599 | 113.604
Current Estimate | 2010-12-01 | 110.134 | 90.772 | 154.413 | 132.806
SAR Unit Cost History | Changes | [7 empty] | PAUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial PAUC Dev Est
81.298 | -3.249 | 3.245 | 14.21 | 5.205 | 45.232 | 0 | 8.472 | 73.115 | 154.413
| Changes Econ: Changes | APUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial APUC Dev Est
68.934 | -3.685 | 1.13 | 11.071 | 3.853 | 42.983 | 0 | 8.52 | 63.872 | 132.806
SAR Baseline History | bar: Changes Econ to Changes Eng
Item/Event | Changes Econ: SAR Planning Estimate (PE); Changes Qty: SAR Development Estimate (DE); Changes Sch: SAR Production Estimate (PdE); Changes Eng: Current Estimate
Milestone I | Changes Econ: N/A; Changes Qty: 1996-11-01; Changes Sch: N/A; Changes Eng: 1996-11-01
Milestone B | Changes Econ: 2001-03-01; Changes Qty: 2001-10-01; Changes Sch: N/A; Changes Eng: 2001-10-01
Milestone C | Changes Econ: TBD; Changes Qty: 2012-04-01; Changes Sch: N/A; Changes Eng: TBD
IOC | Changes Econ: TBD; Changes Qty: 2010-04-01; Changes Sch: N/A; Changes Eng: TBD
Total Cost (TY $M) | Changes Econ: 24800; Changes Qty: 233000; Changes Sch: N/A; Changes Eng: 379392.8
Total Quantity | Changes Econ: N/A; Changes Qty: 2866; Changes Sch: N/A; Changes Eng: 2457
Prog. Acq. Unit Cost (PAUC) | Changes Econ: N/A; Changes Qty: 81.298; Changes Sch: N/A; Changes Eng: 154.413

## Cost Variance
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 34400 | 196600 | 2000 | 233000
Previous Changes
Economic | +936.2 | -7553.3 | -4.9 | -6595.0
Quantity | +157.0 | -25434.9 | -- | -25277.9
Schedule | +7866.9 | +23895.5 | -- | +31762.4
Engineering | +3122.5 | +9414.0 | +252.8 | +12789.3
Estimating | +3658.5 | +69592.0 | -1696.7 | +71553.8
Other | -- | -- | -- | --
Support | -- | +11020.3 | -- | +11020.3
Subtotal | +15768.1 | +80933.6 | -1448.8 | +95252.9
Current Changes
Economic | +63 | -1449.8 | -- | -1386.8
Quantity | -- | -- | -- | --
Schedule | -- | +31511.0 | -- | +3151.0
Engineering | -- | -- | -- | --
Estimating | +4165.6 | +35415.4 | -- | +39581.0
Other | -- | -- | -- | --
Support | -- | +9794.7 | -- | +9794.7
Subtotal | +4228.6 | +46911.3 | -- | +51139.9
Total Changes | +19996.7 | +127844.9 | -1448.8 | +146392.8
CE - Cost Variance | 54396.7 | 324444.9 | 551.2 | 379392.8
CE - Cost & Funding | 54396.7 | 324444.9 | 551.2 | 379392.8
Summary Base Year 2002 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 32300 | 143300 | 1500 | 177100
Previous Changes
Economic | -- | -- | -- | --
Quantity | +130.6 | -16249.1 | -- | -16118.5
Schedule | +6779.4 | +2017.7 | -- | +8797.1
Engineering | +2814.6 | +6644.8 | +227.3 | +9686.7
Estimating | +3111.4 | +50538.8 | -1269.9 | +52380.3
Other | -- | -- | -- | --
Support | -- | +6753.0 | -- | +6753.0
Subtotal | +12836.0 | +49705.2 | -1042.6 | +61498.6
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | +3249.8 | +22353.5 | -- | +25603.3
Other | -- | -- | -- | --
Support | -- | +6397.8 | -- | +6397.8
Subtotal | +3249.8 | +28751.3 | -- | +32001.1
Total Changes | +16085.8 | +78456.5 | -1042.6 | +93499.7
CE - Cost Variance | 48385.8 | 221756.5 | 457.4 | 270599.7
CE - Cost & Funding | 48385.8 | 221756.5 | 457.4 | 270599.7

## Contracts
Contract Name: JSF Air System SDD
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
18981.9 | N/A | 14 | 27593.8 | N/A | 14 | 33317.6 | 33317.6
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -998.8 | -391.5
Previous Cumulative Variances | -727.4 | -358.4
Net Change | -271.4 | -33.1
Contract Name: Propulsion JSF F135 SDD
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
4827.8 | N/A | 33 | 6672.7 | N/A | 30 | 6910.8 | 6769.8
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -77.2 | -50.5
Previous Cumulative Variances | +10.1 | -66.0
Net Change | -87.3 | +15.5
Contract Name: F136 Propulsion Sys SDD
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2486.2 | N/A | 6 | 2418.9 | N/A | 6 | 2763.9 | 2142.3
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -140.5 | -47.0
Previous Cumulative Variances | -107.8 | -29.7
Net Change | -32.7 | -17.3
Contract Name: JSF Air System LRIP 2
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2208 | N/A | 12 | 2585.8 | N/A | 12 | 2585.8 | 2585.8
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -250.9 | -130.1
Previous Cumulative Variances | -71.4 | -110.4
Net Change | -179.5 | -19.7
Contract Name: JSF F135 LRIP 2
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
392.1 | N/A | 16 | 495.8 | N/A | 16 | 543.9 | 543.9
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -36.7 | -29.8
Previous Cumulative Variances | -- | --
Net Change | -36.7 | -29.8
Contract Name: JSF Air System LRIP 3
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
2775.2 | N/A | 17 | 2795.1 | N/A | 17 | 3612.5 | 3612.5
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -163.5 | -136.5
Previous Cumulative Variances | -14.8 | -1.9
Net Change | -148.7 | -134.6
Contract Name: JSF F135 LRIP 3
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
649.2 | N/A | 21 | 673.1 | N/A | 21 | 709.5 | 709.5
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -11.8 | -108.3
Previous Cumulative Variances | -0.4 | +0.4
Net Change | -11.4 | -108.7
Contract Name: JSF Air System LRIP 4
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
3783.1 | 4026.4 | 31 | 3783.1 | 4026.4 | 31 | 3783.1 | 3783.1
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | 0 | 0
Previous Cumulative Variances | -- | --
Net Change | 0 | 0

## Deliveries and Expenditures
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 13 | 10 | 14 | 71.43%
Production | 14 | 0 | 2443 | 0%
Total Program Quantities Delivered | 27 | 10 | 2457 | 0.41%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 379392.8 | Years Appropriated | 18
Expenditures to Date | 45544.8 | Percent Years Appropriated | 42.86%
Precent Expended | 12% | Appropriated to Date | 65990
Total Funding Years | 42 | Percent Appropriated | 17.39%

## Operating and Support Cost
Costs BY 2002 $K
Cost Element | F-35 Cost per Flying Hour ($) | F-16C/D Cost per Flying Hour ($)
Unit-Level Manpower | 4.605 | 5.534
Unit Operations | 2.219 | 2.171
Maintenance | 7.627 | 3.778
Sustaining Support | 1.82 | 0.431
Continuing System Improvements | 0.154 | 0.217
Indirect Support | -- | 1.335
Other | -- | --
Total Unitized Cost (Base Year 2002 $) | 16.425 | 13.466
Total O&S Costs $M | F-35 | F-16C/D
Base Year | 420322.2 | --
Then Year | 1005342 | --