## Cost and Funding
Appropriation and Quantity Summary
SEP 2001 Exception SAR (TY $M)
Appropriation | Prior | FY2001 | FY2002 | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | To Complete | Total
RDT&E | 3545 | 684.9 | 1631.8 | 4119 | 3887.1 | 3509 | 2287.3 | 1192.1 | 1082.6 | 21938.8
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SEP 2001 Total | 3545 | 684.9 | 1631.8 | 4119 | 3887.1 | 3509 | 2287.3 | 1192.1 | 1082.6 | 21938.8
PB2001 Total | 3545.5 | 922.8 | 2804.3 | 4082.4 | 3848.9 | 3471.1 | 2260.4 | 1117.7 | 1067.2 | 23179.7
Delta | -0.5 | -237.9 | -1172.5 | 36.6 | 38.2 | 37.9 | 26.9 | 15 | 15.4 | -1240.9
Appropriation | Prior | FY2001 | FY2002 | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SEP 2001 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB2001 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Annual Funding by Appropriation
Annual Funding TY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1994 | -- | -- | -- | -- | -- | -- | 29.5
1995 | -- | -- | -- | -- | -- | -- | 98.3
1996 | -- | -- | -- | -- | -- | -- | 80.4
1997 | -- | -- | -- | -- | -- | -- | 243.3
1998 | -- | -- | -- | -- | -- | -- | 448.2
1999 | -- | -- | -- | -- | -- | -- | 471.3
2000 | -- | -- | -- | -- | -- | -- | 238.4
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 767.3
2003 | -- | -- | -- | -- | -- | -- | 1949.8
2004 | -- | -- | -- | -- | -- | -- | 1878.4
2005 | -- | -- | -- | -- | -- | -- | 1657
2006 | -- | -- | -- | -- | -- | -- | 1078.6
2007 | -- | -- | -- | -- | -- | -- | 524
2008 | -- | -- | -- | -- | -- | -- | 311
2009 | -- | -- | -- | -- | -- | -- | 119.1
2010 | -- | -- | -- | -- | -- | -- | 65.1
2011 | -- | -- | -- | -- | -- | -- | 27
Subtotal | -- | -- | -- | -- | -- | -- | 10327.9
Annual Funding BY$
1319 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Navy
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1994 $M | Non End Item Recurring Flyaway BY 1994 $M | Non Recurring Flyaway BY 1994 $M | Total Flyaway BY 1994 $M | Total Support BY 1994 $M | Total Program BY 1994 $M
1994 | -- | -- | -- | -- | -- | -- | 29.5
1995 | -- | -- | -- | -- | -- | -- | 95.2
1996 | -- | -- | -- | -- | -- | -- | 76.6
1997 | -- | -- | -- | -- | -- | -- | 229
1998 | -- | -- | -- | -- | -- | -- | 418.3
1999 | -- | -- | -- | -- | -- | -- | 434.6
2000 | -- | -- | -- | -- | -- | -- | 216.6
2001 | -- | -- | -- | -- | -- | -- | 305
2002 | -- | -- | -- | -- | -- | -- | 674.8
2003 | -- | -- | -- | -- | -- | -- | 1683.8
2004 | -- | -- | -- | -- | -- | -- | 1588.8
2005 | -- | -- | -- | -- | -- | -- | 1372.7
2006 | -- | -- | -- | -- | -- | -- | 875.2
2007 | -- | -- | -- | -- | -- | -- | 416.4
2008 | -- | -- | -- | -- | -- | -- | 242.1
2009 | -- | -- | -- | -- | -- | -- | 90.8
2010 | -- | -- | -- | -- | -- | -- | 48.6
2011 | -- | -- | -- | -- | -- | -- | 19.7
Subtotal | -- | -- | -- | -- | -- | -- | 8817.3
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, AF
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1995 | -- | -- | -- | -- | -- | -- | 83.8
1996 | -- | -- | -- | -- | -- | -- | 81.3
1997 | -- | -- | -- | -- | -- | -- | 251.6
1998 | -- | -- | -- | -- | -- | -- | 444.3
1999 | -- | -- | -- | -- | -- | -- | 456.1
2000 | -- | -- | -- | -- | -- | -- | 249.1
2001 | -- | -- | -- | -- | -- | -- | 341.2
2002 | -- | -- | -- | -- | -- | -- | 769.5
2003 | -- | -- | -- | -- | -- | -- | 1944.5
2004 | -- | -- | -- | -- | -- | -- | 1871.7
2005 | -- | -- | -- | -- | -- | -- | 1649.8
2006 | -- | -- | -- | -- | -- | -- | 1078.6
2007 | -- | -- | -- | -- | -- | -- | 524
2008 | -- | -- | -- | -- | -- | -- | 311
2009 | -- | -- | -- | -- | -- | -- | 119.1
2010 | -- | -- | -- | -- | -- | -- | 65.1
2011 | -- | -- | -- | -- | -- | -- | 27
Subtotal | -- | -- | -- | -- | -- | -- | 10267.7
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, AF
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1994 $M | Non End Item Recurring Flyaway BY 1994 $M | Non Recurring Flyaway BY 1994 $M | Total Flyaway BY 1994 $M | Total Support BY 1994 $M | Total Program BY 1994 $M
1995 | -- | -- | -- | -- | -- | -- | 81.2
1996 | -- | -- | -- | -- | -- | -- | 77.4
1997 | -- | -- | -- | -- | -- | -- | 236.8
1998 | -- | -- | -- | -- | -- | -- | 414.7
1999 | -- | -- | -- | -- | -- | -- | 420.6
2000 | -- | -- | -- | -- | -- | -- | 226.3
2001 | -- | -- | -- | -- | -- | -- | 305
2002 | -- | -- | -- | -- | -- | -- | 676.7
2003 | -- | -- | -- | -- | -- | -- | 1679.2
2004 | -- | -- | -- | -- | -- | -- | 1583.1
2005 | -- | -- | -- | -- | -- | -- | 1366.7
2006 | -- | -- | -- | -- | -- | -- | 875.2
2007 | -- | -- | -- | -- | -- | -- | 416.4
2008 | -- | -- | -- | -- | -- | -- | 242.1
2009 | -- | -- | -- | -- | -- | -- | 90.8
2010 | -- | -- | -- | -- | -- | -- | 48.6
2011 | -- | -- | -- | -- | -- | -- | 19.7
Subtotal | -- | -- | -- | -- | -- | -- | 8760.5
Annual Funding TY$
9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 14
1997 | -- | -- | -- | -- | -- | -- | 71
1998 | -- | -- | -- | -- | -- | -- | 77.2
1999 | -- | -- | -- | -- | -- | -- | 54.7
2000 | -- | -- | -- | -- | -- | -- | 34.5
2001 | -- | -- | -- | -- | -- | -- | 2.5
2002 | -- | -- | -- | -- | -- | -- | 95
2003 | -- | -- | -- | -- | -- | -- | 224.7
2004 | -- | -- | -- | -- | -- | -- | 137
2005 | -- | -- | -- | -- | -- | -- | 202.2
2006 | -- | -- | -- | -- | -- | -- | 130.1
2007 | -- | -- | -- | -- | -- | -- | 144.1
2008 | -- | -- | -- | -- | -- | -- | 38.2
Subtotal | -- | -- | -- | -- | -- | -- | 1225.2
Annual Funding BY$
9999 ¦ RDT&E ¦ Non Treasury Funds
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1994 $M | Non End Item Recurring Flyaway BY 1994 $M | Non Recurring Flyaway BY 1994 $M | Total Flyaway BY 1994 $M | Total Support BY 1994 $M | Total Program BY 1994 $M
1996 | -- | -- | -- | -- | -- | -- | 13.3
1997 | -- | -- | -- | -- | -- | -- | 66.8
1998 | -- | -- | -- | -- | -- | -- | 72
1999 | -- | -- | -- | -- | -- | -- | 50.4
2000 | -- | -- | -- | -- | -- | -- | 31.3
2001 | -- | -- | -- | -- | -- | -- | 2.2
2002 | -- | -- | -- | -- | -- | -- | 83.5
2003 | -- | -- | -- | -- | -- | -- | 194
2004 | -- | -- | -- | -- | -- | -- | 115.9
2005 | -- | -- | -- | -- | -- | -- | 167.5
2006 | -- | -- | -- | -- | -- | -- | 105.6
2007 | -- | -- | -- | -- | -- | -- | 114.5
2008 | -- | -- | -- | -- | -- | -- | 29.7
Subtotal | -- | -- | -- | -- | -- | -- | 1046.7
"Other RDT&E Funding" reflects current and anticipated foreign funding.
Annual Funding TY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
1996 | -- | -- | -- | -- | -- | -- | 28.9
1997 | -- | -- | -- | -- | -- | -- | 68.2
1998 | -- | -- | -- | -- | -- | -- | 20.9
Subtotal | -- | -- | -- | -- | -- | -- | 118
Annual Funding BY$
0400 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Defense-Wide
Fiscal Year | Quantity | End Item Recurring Flyaway BY 1994 $M | Non End Item Recurring Flyaway BY 1994 $M | Non Recurring Flyaway BY 1994 $M | Total Flyaway BY 1994 $M | Total Support BY 1994 $M | Total Program BY 1994 $M
1996 | -- | -- | -- | -- | -- | -- | 28.9
1997 | -- | -- | -- | -- | -- | -- | 68.2
1998 | -- | -- | -- | -- | -- | -- | 20.9
Subtotal | -- | -- | -- | -- | -- | -- | 118

## Cost Variance
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Plan Est) | 24800 | -- | -- | 24800
Previous Changes
Economic | -2588.8 | -- | -- | -2588.8
Quantity | 0 | -- | -- | 0
Schedule | 0 | -- | -- | 0
Engineering | 1420 | -- | -- | 1420
Estimating | -451.5 | -- | -- | -451.5
Other | 0 | -- | -- | 0
Support | 0 | -- | -- | 0
Subtotal | -1620.3 | -- | -- | -1620.3
Current Changes
Economic | 641.5 | -- | -- | 641.5
Quantity | -- | -- | -- | --
Schedule | -1870.4 | -- | -- | -1870.4
Engineering | -- | -- | -- | --
Estimating | -12 | -- | -- | -12
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -1240.9 | -- | -- | -1240.9
Total Changes | -2861.2 | -- | -- | -2861.2
CE - Cost Variance | 21938.8 | -- | -- | 21938.8
CE - Cost & Funding | 21938.8 | -- | -- | 21938.8
Summary Base Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Plan Est) | 19000 | -- | -- | 19000
Previous Changes
Economic | 0 | -- | -- | 0
Quantity | 0 | -- | -- | 0
Schedule | 0 | -- | -- | 0
Engineering | 1120.8 | -- | -- | 1120.8
Estimating | -105.3 | -- | -- | -105.3
Other | 0 | -- | -- | 0
Support | 0 | -- | -- | 0
Subtotal | 1015.5 | -- | -- | 1015.5
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -1271 | -- | -- | -1271
Engineering | -- | -- | -- | --
Estimating | -8.8 | -- | -- | -8.8
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -1279.8 | -- | -- | -1279.8
Total Changes | -264.3 | -- | -- | -264.3
CE - Cost Variance | 18735.7 | -- | -- | 18735.7
CE - Cost & Funding | 18735.7 | -- | -- | 18735.7
RDT&E | $M
| Base | Then
Current Change Explanations | Year | Year
Revised escalation indices. (Economic) | N/A | 202.1
Economic adjustment for negative program change. (Economic) | N/A | 439.4
Revised EMD schedule (from 90 to 126 months) and a delay in EMD start shifted FY2001and FY2002 EMD funding to the right. However, the FY2003-FY2011 estimates are constrained to the FY2001 President's Budget. As a result, the RDT&E profile shown understates current requirements. (Schedule) | -1271 | -1870.4
Adjustment for Current and Prior Inflation (Estimating) | -8.8 | -12
RDT&E Subtotal | -1279.8 | 1240.9

## Deliveries and Expenditures
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 21938.8 | Years Appropriated | 8
Expenditures To Date | 0 | Percent Years Appropriated | 44.44%
Percent Expended | 0% | Appropriated to Date | 4229.9
Total Funding Years | 18 | Percent Appropriated | 19.28%