## CostSummary
Cost Summary
Total Acquisition Cost and Quantity - Total Program
| BY 2004 $M |  |  | BY2004 | TY $M
$M
Appropriation | SAR Baseline Dev Est | Current APB Objective/Threshold |  | Current Estimate
[5 empty] | SAR Baseline Dev Est | Current APB Objective | Current Estimate
RDT&E | 4992.3 | 4992.3 | -- | 3462.7 | 5737 | 5737 | 3965.3
Procurement | 17759.1 | 17759.1 | -- | 6165.7 | 24158.4 | 24158.4 | 8986.9
Flyaway | 15071.8 | -- | -- | 5662.5 | 20409.3 | -- | 8257.9
Recurring | 14809.2 | -- | -- | 5590.5 | 20095.8 | -- | 8170
Non Recurring | 262.6 | -- | -- | 72 | 313.5 | -- | 87.9
Support | 2687.3 | -- | -- | 503.2 | 3749.1 | -- | 729
Other Support | 1550.4 | -- | -- | 503.2 | 2125.1 | -- | 729
Initial Spares | 1136.9 | -- | -- | 0 | 1624 | -- | 0
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 22751.4 | 22751.4 | N/A | 9628.4 | 29895.4 | 29895.4 | 12952.2
Total Acquisition Cost and Quantity - FIRE UNIT
| BY 2004 $M |  |  | BY2004 | TY $M
$M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
[5 empty] | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 4531.4 | 4531.4 | 5211.1 | 2758.8 | 5255 | 5255 | 3177.1
Procurement | 11999.1 | 11999.1 | 13199 | 0 | 16584.4 | 16584.4 | 0
Flyaway | 9818.9 | -- | -- | 0 | 13494.5 | -- | 0
Recurring | 9556.3 | -- | -- | 0 | 13181 | -- | 0
Non Recurring | 262.6 | -- | -- | 0 | 313.5 | -- | 0
Support | 2180.2 | -- | -- | 0 | 3089.9 | -- | 0
Other Support | 1043.3 | -- | -- | 0 | 1465.9 | -- | 0
Initial Spares | 1136.9 | -- | -- | 0 | 1624 | -- | 0
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 16530.5 | 16530.5 | N/A | 2758.8 | 21839.4 | 21839.4 | 3177.1
| SAR Baseline | Current APB Development | Current Estimate
Quantity | Dev Est
RDT&E | 0 | 0 | 0
Procurement | 48 | 48 | 0
Total | 48 | 48 | 0
Total Acquisition Cost and Quantity - MISSILE
| BY 2004 $M |  |  | BY2004 | TY $M
$M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate
[5 empty] | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 460.9 | 460.9 | 530 | 703.9 | 482 | 482 | 788.2
Procurement | 5760 | 5760 | 6336 | 6165.7 | 7574 | 7574 | 8986.9
Flyaway | 5252.9 | -- | -- | 5662.5 | 6914.8 | -- | 8257.9
Recurring | 5252.9 | -- | -- | 5590.5 | 6914.8 | -- | 8170
Non Recurring | 0 | -- | -- | 72 | 0 | -- | 87.9
Support | 507.1 | -- | -- | 503.2 | 659.2 | -- | 729
Other Support | 507.1 | -- | -- | 503.2 | 659.2 | -- | 729
Initial Spares | 0 | -- | -- | 0 | 0 | -- | 0
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 6220.9 | 6220.9 | N/A | 6869.6 | 8056 | 8056 | 9775.1
| SAR Baseline | Current APB Development | Current Estimate
Quantity | Dev Est
RDT&E | 0 | 0 | 0
Procurement | 1528 | 1528 | 1528
Total | 1528 | 1528 | 1528

## Funding Summary
Cost and Funding
Funding Summary - Total Program
FY 2013 President's Budget / December 2011 SAR (TY$ M)
To
Appropriation | Prior | FY2012 | FY2013 | FY2014 | FY2015 | FY2016 | FY2017 | Complete | Total
RDT&E | 3048.2 | 478.6 | 438.5 | 0 | 0 | 0 | 0 | 0 | 3965.3
Procurement | 0 | 75 | 12.9 | 538.6 | 505.1 | 596.4 | 566.7 | 6692.2 | 8986.9
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2013 Total | 3048.2 | 553.6 | 451.4 | 538.6 | 505.1 | 596.4 | 566.7 | 6692.2 | 12952.2
PB 2012 Total | 3005.7 | 570.6 | 1121.6 | 532.5 | 487 | 560.1 | 474.2 | 5811.6 | 12563.3
Delta | 42.5 | -17 | -670.2 | 6.1 | 18.1 | 36.3 | 92.5 | 880.6 | 388.9
Appropriation and Quantity Summary - FIRE UNIT
FY 2013 President's Budget / December 2011 SAR (TY$ M)
To
Appropriation | Prior | FY2012 | FY2013 | FY2014 | FY2015 | FY2016 | FY2017 | Complete | Total
RDT&E | 2386.6 | 389.6 | 400.9 | 0 | 0 | 0 | 0 | 0 | 3177.1
Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2013 Total | 2386.6 | 389.6 | 400.9 | 0 | 0 | 0 | 0 | 0 | 3177.1
PB 2012 Total | 2403.1 | 406.6 | 493.8 | 0 | 0 | 0 | 0 | 0 | 3303.5
Delta | -16.5 | -17 | -92.9 | 0 | 0 | 0 | 0 | 0 | -126.4
Quantity | Undistributed | Prior | FY2012 | FY2013 | FY2014 | FY2015 | FY2016 | FY2017 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2012 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2011 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding Summary - MISSILE
FY 2013 President's Budget / December 2011 SAR (TY$ M)
To
Appropriation | Prior | FY2012 | FY2013 | FY2014 | FY2015 | FY2016 | FY2017 | Complete | Total
RDT&E | 661.6 | 89 | 37.6 | 0 | 0 | 0 | 0 | 0 | 788.2
Procurement | 0 | 75 | 12.9 | 538.6 | 505.1 | 596.4 | 566.7 | 6692.2 | 8986.9
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2012 Total | 661.6 | 164 | 50.5 | 538.6 | 505.1 | 596.4 | 566.7 | 6692.2 | 9775.1
PB 2011 Total | 602.6 | 164 | 627.8 | 532.5 | 487 | 560.1 | 474.2 | 5811.6 | 9259.8
Delta | 59 | 0 | -577.3 | 6.1 | 18.1 | 36.3 | 92.5 | 880.6 | 515.3
Quantity | Undistributed | Prior | FY2012 | FY2013 | FY2014 | FY2015 | FY2016 | FY2017 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | 0 | 0 | 0 | 0 | 56 | 72 | 80 | 82 | 1238 | 1528
PB 2013 Total | 0 | 0 | 0 | 0 | 56 | 72 | 80 | 82 | 1238 | 1528
PB 2012 Total | 0 | 0 | 0 | 56 | 82 | 76 | 80 | 90 | 1144 | 1528
Delta | 0 | 0 | 0 | -56 | -26 | -4 | 0 | -8 | 94 | 0
Annual Funding TY$, RDT&E, FIRE UNIT, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2004 | -- | -- | -- | -- | -- | -- | 126.9
2005 | -- | -- | -- | -- | -- | -- | 164
2006 | -- | -- | -- | -- | -- | -- | 193
2007 | -- | -- | -- | -- | -- | -- | 211
2008 | -- | -- | -- | -- | -- | -- | 316.3
2009 | -- | -- | -- | -- | -- | -- | 423.7
2010 | -- | -- | -- | -- | -- | -- | 501.1
2011 | -- | -- | -- | -- | -- | -- | 450.6
2012 | -- | -- | -- | -- | -- | -- | 389.6
2013 | -- | -- | -- | -- | -- | -- | 400.9
Subtotal | -- | -- | -- | -- | -- | -- | 3177.1
Annual Funding BY$, RDT&E, FIRE UNIT, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2004 $M | Non End Item Recurring Flyaway BY 2004 $M | Non Recurring Flyaway BY 2004 $M | Total Flyaway BY 2004 $M | Total Support BY 2004 $M | Total Program BY 2004 $M
2004 | -- | -- | -- | -- | -- | -- | 124
2005 | -- | -- | -- | -- | -- | -- | 155.7
2006 | -- | -- | -- | -- | -- | -- | 178.3
2007 | -- | -- | -- | -- | -- | -- | 190.4
2008 | -- | -- | -- | -- | -- | -- | 280
2009 | -- | -- | -- | -- | -- | -- | 370.4
2010 | -- | -- | -- | -- | -- | -- | 431.3
2011 | -- | -- | -- | -- | -- | -- | 380
2012 | -- | -- | -- | -- | -- | -- | 322.9
2013 | -- | -- | -- | -- | -- | -- | 325.8
Subtotal | -- | -- | -- | -- | -- | -- | 2758.8
Annual Funding TY$, RDT&E, MISSILE, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2004 | -- | -- | -- | -- | -- | -- | 109.9
2005 | -- | -- | -- | -- | -- | -- | 87.3
2006 | -- | -- | -- | -- | -- | -- | 81.4
2007 | -- | -- | -- | -- | -- | -- | 111.9
2008 | -- | -- | -- | -- | -- | -- | 53.5
2009 | -- | -- | -- | -- | -- | -- | 31
2010 | -- | -- | -- | -- | -- | -- | 65.1
2011 | -- | -- | -- | -- | -- | -- | 121.5
2012 | -- | -- | -- | -- | -- | -- | 89
2013 | -- | -- | -- | -- | -- | -- | 37.6
Subtotal | -- | -- | -- | -- | -- | -- | 788.2
Annual Funding BY$, RDT&E, MISSILE, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2004 $M | Non End Item Recurring Flyaway BY 2004 $M | Non Recurring Flyaway BY 2004 $M | Total Flyaway BY 2004 $M | Total Support BY 2004 $M | Total Program BY 2004 $M
2004 | -- | -- | -- | -- | -- | -- | 107.4
2005 | -- | -- | -- | -- | -- | -- | 82.9
2006 | -- | -- | -- | -- | -- | -- | 75.2
2007 | -- | -- | -- | -- | -- | -- | 101
2008 | -- | -- | -- | -- | -- | -- | 47.4
2009 | -- | -- | -- | -- | -- | -- | 27.1
2010 | -- | -- | -- | -- | -- | -- | 56
2011 | -- | -- | -- | -- | -- | -- | 102.5
2012 | -- | -- | -- | -- | -- | -- | 73.8
2013 | -- | -- | -- | -- | -- | -- | 30.6
Subtotal | -- | -- | -- | -- | -- | -- | 703.9
Annual Funding TY$, Missile Procurement, MISSILE, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2012 | -- | -- | -- | 75 | 75 | -- | 75
2013 | -- | -- | -- | 12.9 | 12.9 | -- | 12.9
2014 | 56 | 470.7 | -- | -- | 470.7 | 67.9 | 538.6
2015 | 72 | 454.6 | -- | -- | 454.6 | 50.5 | 505.1
2016 | 80 | 539.1 | -- | -- | 539.1 | 57.3 | 596.4
2017 | 82 | 512.3 | -- | -- | 512.3 | 54.4 | 566.7
2018 | 90 | 465.1 | -- | -- | 465.1 | 35 | 500.1
2019 | 90 | 456.7 | -- | -- | 456.7 | 34.4 | 491.1
2020 | 90 | 456.2 | -- | -- | 456.2 | 34.3 | 490.5
2021 | 90 | 453.6 | -- | -- | 453.6 | 35.7 | 489.3
2022 | 90 | 452.5 | -- | -- | 452.5 | 35.7 | 488.2
2023 | 90 | 451.1 | -- | -- | 451.1 | 35.6 | 486.7
2024 | 90 | 449.7 | -- | -- | 449.7 | 35.5 | 485.2
2025 | 90 | 448.2 | -- | -- | 448.2 | 35.4 | 483.6
2026 | 90 | 446.7 | -- | -- | 446.7 | 35.3 | 482
2027 | 90 | 446.8 | -- | -- | 446.8 | 33.6 | 480.4
2028 | 90 | 445.6 | -- | -- | 445.6 | 33.5 | 479.1
2029 | 90 | 444.3 | -- | -- | 444.3 | 33.4 | 477.7
2030 | 90 | 443 | -- | -- | 443 | 33.3 | 476.3
2031 | 68 | 333.8 | -- | -- | 333.8 | 25.1 | 358.9
2032 | -- | -- | -- | -- | -- | 11.6 | 11.6
2033 | -- | -- | -- | -- | -- | 11.5 | 11.5
Subtotal | 1528 | 8170 | -- | 87.9 | 8257.9 | 729 | 8986.9
Annual Funding BY$, Missile Procurement, MISSILE, Army
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2004 $M | Non End Item Recurring Flyaway BY 2004 $M | Non Recurring Flyaway BY 2004 $M | Total Flyaway BY 2004 $M | Total Support BY 2004 $M | Total Program BY 2004 $M
2012 | -- | -- | -- | 61.6 | 61.6 | -- | 61.6
2013 | -- | -- | -- | 10.4 | 10.4 | -- | 10.4
2014 | 56 | 371.3 | -- | -- | 371.3 | 53.6 | 424.9
2015 | 72 | 352.3 | -- | -- | 352.3 | 39.1 | 391.4
2016 | 80 | 410.4 | -- | -- | 410.4 | 43.6 | 454
2017 | 82 | 383.1 | -- | -- | 383.1 | 40.7 | 423.8
2018 | 90 | 341.6 | -- | -- | 341.6 | 25.7 | 367.3
2019 | 90 | 329.5 | -- | -- | 329.5 | 24.9 | 354.4
2020 | 90 | 323.4 | -- | -- | 323.4 | 24.3 | 347.7
2021 | 90 | 315.8 | -- | -- | 315.8 | 24.9 | 340.7
2022 | 90 | 309.5 | -- | -- | 309.5 | 24.4 | 333.9
2023 | 90 | 303.1 | -- | -- | 303.1 | 23.9 | 327
2024 | 90 | 296.8 | -- | -- | 296.8 | 23.4 | 320.2
2025 | 90 | 290.6 | -- | -- | 290.6 | 22.9 | 313.5
2026 | 90 | 284.5 | -- | -- | 284.5 | 22.5 | 307
2027 | 90 | 279.5 | -- | -- | 279.5 | 21 | 300.5
2028 | 90 | 273.8 | -- | -- | 273.8 | 20.6 | 294.4
2029 | 90 | 268.2 | -- | -- | 268.2 | 20.2 | 288.4
2030 | 90 | 262.7 | -- | -- | 262.7 | 19.7 | 282.4
2031 | 68 | 194.4 | -- | -- | 194.4 | 14.7 | 209.1
2032 | -- | -- | -- | -- | -- | 6.6 | 6.6
2033 | -- | -- | -- | -- | -- | 6.5 | 6.5
Subtotal | 1528 | 5590.5 | -- | 72 | 5662.5 | 503.2 | 6265.7

## Low Rate Initial Production
Low Rate Initial Production, FIRE UNIT
| Initial LRIP Decision | Current Total LRIP
Approval Date | 2004-08-06 | 2011-02-11
Approved Quantity | 7 | 0
Reference | ADM | ADM
Start Year | 2013
End Year | 2016
Low Rate Initial Production, MISSILE
| Initial LRIP Decision | Current Total LRIP
Approval Date | 2004-08-06 | 2004-08-06
Approved Quantity | 148 | 148
Reference | ADM | ADM
Start Year | 2010 | 2010
End Year | 2011 | 2011

## Foreign Military Sales
None

## Unit Cost
Unit Cost - FIRE UNIT
Unit Cost Report | BY 2004 $M | BY 2004 $M
Unit Cost | Current UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2011 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 16530.5 | 2758.8
Quantity | 48 | 0
Unit Cost | 344.385 | -- | --
Average Procurement Unit Cost (APUC)
Cost | 11999.1 | 0
Quantity | 48 | 0
Unit Cost | 249.981 | -- | --
| BY 2004 $M | BY 2004 $M
Unit Cost | Original UCR Baseline (APR 2004 APB) | Current Estimate (DEC 2011 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 16530.5 | 2758.8
Quantity | 48 | 0
Unit Cost | 344.385 | -- | --
Average Procurement Unit Cost (APUC)
Cost | 11999.1 | 0
Quantity | 48 | 0
Unit Cost | 249.981 | -- | --
Unit Cost History, FIRE UNIT
|  | BY 2004 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2004-08-01 | 344.385 | 249.981 | 454.988 | 345.508
APB as of JAN 2006 | 2004-08-01 | 344.385 | 249.981 | 454.988 | 345.508
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | N/A | N/A | N/A | N/A | N/A
Current APB | 2004-08-01 | 344.385 | 249.981 | 454.988 | 345.508
Prior Annual SAR | 2010-12-01 | N/A | N/A | N/A | N/A
Current Estimate | 2011-12-01 | N/A | N/A | N/A | N/A
SAR Unit Cost History | Changes | [7 empty] | PAUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial PAUC Dev Est
454.988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Changes Econ: Changes | APUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial APUC Dev Est
345.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SAR Baseline History | bar: Changes Econ to Changes Eng
Item/Event | Changes Econ: SAR Planning Estimate (PE); Changes Qty: SAR Development Estimate (DE); Changes Sch: SAR Production Estimate (PdE); Changes Eng: Current Estimate
Milestone A | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
Milestone B | Changes Econ: N/A; Changes Qty: 2004-08-01; Changes Sch: N/A; Changes Eng: 2004-08-01
Milestone C | Changes Econ: N/A; Changes Qty: 2012-11-01; Changes Sch: N/A; Changes Eng: 2012-11-01
IOC | Changes Econ: N/A; Changes Qty: 2017-09-01; Changes Sch: N/A; Changes Eng: 2017-09-01
Total Cost (TY $M) | Changes Econ: N/A; Changes Qty: 21839.4; Changes Sch: N/A; Changes Eng: 3177.1
Total Quantity | Changes Econ: N/A; Changes Qty: 48; Changes Sch: N/A; Changes Eng: 0
Prog. Acq. Unit Cost (PAUC) | Changes Econ: N/A; Changes Qty: 454.988; Changes Sch: N/A; Changes Eng: N/A
Unit Cost - MISSILE
Unit Cost Report | Changes Econ: BY 2004 $M; Changes Qty: BY 2004 $M
Unit Cost | Changes Econ: Current UCR Baseline (MAR 2004 APB); Changes Qty: Current Estimate (DEC 2011 SAR); Changes Sch: BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | Changes Econ: 6220.9; Changes Qty: 6869.6
Quantity | Changes Econ: 1528; Changes Qty: 1528
Unit Cost | Changes Econ: 4.071; Changes Qty: 4.496; Changes Sch: 10.44
Average Procurement Unit Cost (APUC)
Cost | Changes Econ: 5760; Changes Qty: 6165.7
Quantity | Changes Econ: 1528; Changes Qty: 1528
Unit Cost | Changes Econ: 3.77; Changes Qty: 4.035; Changes Sch: 7.03
| BY 2004 $M | BY 2004 $M
Unit Cost | Changes Econ: Original UCR Baseline (AUG 2004 APB); Changes Qty: Current Estimate (DEC 2011 SAR); Changes Sch: BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | Changes Econ: 6220.9; Changes Qty: 6869.6
Quantity | Changes Econ: 1528; Changes Qty: 1528
Unit Cost | Changes Econ: 4.071; Changes Qty: 4.496; Changes Sch: 10.44
Average Procurement Unit Cost (APUC)
Cost | Changes Econ: 5760; Changes Qty: 6165.7
Quantity | Changes Econ: 1528; Changes Qty: 1528
Unit Cost | Changes Econ: 3.77; Changes Qty: 4.035; Changes Sch: 7.03
Unit Cost History, MISSILE
|  | BY 2004 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2004-08-01 | 4.071 | 3.77 | 5.272 | 4.957
APB as of JAN 2006 | 2004-08-01 | 4.071 | 3.77 | 5.272 | 4.957
Revised Original APB | N/A | N/A | N/A | N/A | N/A
Prior APB | N/A | N/A | N/A | N/A | N/A
Current APB | 2004-08-01 | 4.071 | 3.77 | 5.272 | 4.957
Prior Annual SAR | 2010-12-01 | 4.435 | 4.005 | 6.06 | 5.583
Current Estimate | 2011-12-01 | 4.496 | 4.035 | 6.397 | 5.881
SAR Unit Cost History | Changes Econ: Changes | PAUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial PAUC Dev Est
5.272 | 0.131 | 0 | 0.501 | 0 | 0.458 | 0 | 0.035 | 1.125 | 6.397
| Changes Econ: Changes | APUC Current Est
Current SAR Baseline to Current Estimate (TY $M) | Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
Initial APUC Dev Est
4.957 | 0.12 | 0 | 0.5 | 0 | 0.27 | 0 | 0.035 | 0.925 | 5.881
SAR Baseline History | bar: Changes Econ to Changes Eng
Item/Event | Changes Econ: SAR Planning Estimate (PE); Changes Qty: SAR Development Estimate (DE); Changes Sch: SAR Production Estimate (PdE); Changes Eng: Current Estimate
Milestone A | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
Milestone B | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
Milestone C | Changes Econ: N/A; Changes Qty: N/A; Changes Sch: N/A; Changes Eng: N/A
FUE | Changes Econ: N/A; Changes Qty: 2011-03-01; Changes Sch: N/A; Changes Eng: 2015-09-01
Total Cost (TY $M) | Changes Econ: N/A; Changes Qty: 8056; Changes Sch: N/A; Changes Eng: 9775.1
Total Quantity | Changes Econ: N/A; Changes Qty: 1528; Changes Sch: N/A; Changes Eng: 1528
Prog. Acq. Unit Cost (PAUC) | Changes Econ: N/A; Changes Qty: 5.272; Changes Sch: N/A; Changes Eng: 6.397

## Cost Variance
Cost Variance - FIRE UNIT
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 5255 | 16584.4 | -- | 21839.4
Previous Changes
Economic | 103.4 | -195.3 | -- | -91.9
Quantity | -- | -12555.5 | -- | -12555.5
Schedule | -- | -86.5 | -- | -86.5
Engineering | -- | -- | -- | --
Estimating | -2151.6 | -608.3 | -- | -2759.9
Other | -- | -- | -- | --
Support | -- | -3042.1 | -- | -3042.1
Subtotal | -2048.2 | -16487.7 | -- | -18535.9
Current Changes
Economic | 20.1 | 1.7 | -- | 21.8
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -49.8 | -98.4 | -- | -148.2
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -29.7 | -96.7 | -- | -126.4
Total Changes | -2077.9 | -16584.4 | -- | -18662.3
CE - Cost Variance | 3177.1 | -- | -- | 3177.1
CE - Cost & Funding | 3178.1 | -- | -- | 3178.1
Summary Base Year 2004 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 4531.4 | 11999.1 | -- | 16530.5
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -8875.5 | -- | -8875.5
Schedule | -- | -148 | -- | -148
Engineering | -- | -- | -- | --
Estimating | -1730.9 | -716.4 | -- | -2447.3
Other | -- | -- | -- | --
Support | -- | -2180.2 | -- | -2180.2
Subtotal | -1730.9 | -11920.1 | -- | -13651
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | -41.7 | -79 | -- | -120.7
Other | -- | -- | -- | --
Support | -- | -- | -- | --
Subtotal | -41.7 | -79 | -- | -120.7
Total Changes | -1772.6 | -11999.1 | -- | -13771.7
CE - Cost Variance | 2758.8 | -- | -- | 2758.8
CE - Cost & Funding | 2758.8 | -- | -- | 2758.8
Cost Variance - MISSILE
Cost Variance Summary
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 482 | 7574 | -- | 8056
Previous Changes
Economic
Quantity | 15.1 | -37 | -- | -21.9
Schedule | -- | -- | -- | --
Engineering | -- | 538.9 | -- | 538.9
Estimating | -- | -- | -- | --
Other | 232.1 | 398.6 | -- | 630.7
Support | -- | -- | -- | --
Subtotal | 247.2 | 956.6 | -- | 1203.8
Current Changes
Economic | 2.8 | 219.6 | -- | 222.4
Quantity | -- | -- | -- | --
Schedule | -- | 225.4 | -- | 225.4
Engineering | -- | -- | -- | --
Estimating | 56.2 | 13.2 | -- | 69.4
Other | -- | -- | -- | --
Support | -- | -1.9 | -- | -1.9
Subtotal | 59 | 456.3 | -- | 515.3
Total Changes | 306.2 | 1412.9 | -- | 1719.1
CE - Cost Variance | 788.2 | 8986.9 | -- | 9775.1
CE - Cost & Funding | 788.2 | 8986.9 | -- | 9775.1
Summary Base Year 2004 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 460.9 | 5760 | -- | 6220.9
Previous Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | -- | -- | -- | --
Estimating | 195.5 | 350.9 | -- | 546.4
Other | -- | -- | -- | --
Support | -- | 8.9 | -- | 8.9
Subtotal | 195.5 | 359.8 | -- | 555.3
Current Changes
Economic | -- | -- | -- | --
Quantity | -- | -- | -- | --
Schedule | -- | 48.6 | -- | 48.6
Engineering | -- | -- | -- | --
Estimating | 47.5 | 10.1 | -- | 57.6
Other | -- | -- | -- | --
Support | -- | -12.8 | -- | -12.8
Subtotal | 47.5 | 45.9 | -- | 93.4
Total Changes | 243 | 405.7 | -- | 648.7
CE - Cost Variance | 703.9 | 6165.7 | -- | 6869.6
CE - Cost & Funding | 703.9 | 6165.7 | -- | 6869.6

## Contracts
Contract Name: PAC-3 MSE
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
260 | N/A | 0 | 278.4 | N/A | 0 | 415.7 | 417.8
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -13.5 | -2.3
Previous Cumulative Variances | -8.2 | -3.8
Net Change | -5.3 | 1.5
Contract Name: Design & Development
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
3400 | N/A | 0 | 3619 | N/A | 0 | 3620.8 | 3620.8
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | 5.6 | -1.1
Previous Cumulative Variances | 0 | 0
Net Change | 5.6 | -1.1
Contract Name: MSE Follow-On Test Program
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
49.1 | N/A | N/A | 49.1 | N/A | N/A | 45.4 | 49.1
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | 2.4 | -7.9
Previous Cumulative Variances | -- | --
Net Change | 2.4 | -7.9
Contract Name: JSF Air System LRIP 5
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
3949.6 | N/A | 32 | 4772.8 | N/A | 32 | 5027.4 | 0
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -130.5 | -185.9
Previous Cumulative Variances | -62.1 | -339.1
Net Change | -68.4 | 153.2
Contract Name: JSF Propulsion F135 LRIP 5
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
1122.3 | 1122.3 | 36 | 1016.4 | 1026.4 | 36 | 1008.5 | 1016.4
Variance | Cost Variance | Schedule Variance
Cumulative Variances to Date | -26.7 | -19.4
Previous Cumulative Variances | -- | --
Net Change | -26.7 | -19.4

## Deliveries and Expenditures
FIRE UNIT
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 0 | --
Total Program Quantities Delivered | 0 | 0 | 0 | --
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 3177.1 | Years Appropriated | 9
Expenditures to Date | 2432.3 | Percent Years Appropriated | 90%
Precent Expended | 75.56% | Appropriated to Date | 2776.2
Total Funding Years | 10 | Percent Appropriated | 87.38%
F-35 Engine
Deliveries to Date | Plan to Date | Actual to Date | Total Quantity | Percent Delivered
Development | 0 | 0 | 0 | --
Production | 0 | 0 | 1528 | 0%
Total Program Quantities Delivered | 0 | 0 | 1528 | 0%
Expenditures and Appropriations (TY $M)
Total Acquisition Cost | 9775.1 | Years Appropriated | 9
Expenditures to Date | 539.1 | Percent Years Appropriated | 30%
Precent Expended | 5.52% | Appropriated to Date | 825.6
Total Funding Years | 30 | Percent Appropriated | 8.45%

## Operating and Support Cost
FIRE UNIT
Unitized O&S Costs BY 2004 $K
Cost Element | FIRE UNIT Average Annual Cost of All Fire Units | No Antecedent System
Unit-Level Manpower | 345.6 | --
Unit Operations | 139.2 | --
Maintenance | 144 | --
Sustaining Support | 67.2 | --
Continuing System Improvements | 0 | --
Indirect Support | 57.6 | --
Other | -- | --
Total Unitized Cost (Base Year 2002 $) | 753.6 | --
| FIRE UNIT | No Antecedent System
Total O&S Costs $M
Base Year | 33094.4 | --
Then Year | 61902.2 | --
MISSILE
Unitized O&S Costs BY 2004 $K
Cost Element | FIRE UNIT Average Annual Cost of All Fire Units | No Antecedent System
Unit-Level Manpower | 48.9 | --
Unit Operations | 18.9 | --
Maintenance | 20.5 | --
Sustaining Support | 9.5 | --
Continuing System Improvements | 0 | --
Indirect Support | 7.9 | --
Other | 0 | --
Total Unitized Cost (Base Year 2002 $) | 105.7 | --
| FIRE UNIT | No Antecedent System
Total O&S Costs $M
Base Year | 4582.6 | --
Then Year | 8571.8 | --