## Funding Summary
Appropriation and Quantity Summary - Total Program
FY2015 President's Budget / December 2013 SAR (TY$ M)
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | To Complete | Total
RDT&E | 3897.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3897.7
Procurement | 83.2 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 8718.6
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 3980.9 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 12616.3
PB 2014 Total | 4038.3 | 540.4 | 540.5 | 559.6 | 566.8 | 655.2 | 536.8 | 5394.4 | 12832
Delta | -57.4 | 150 | -155.9 | -139.8 | -144.2 | -196.5 | -39.2 | 367.3 | -215.7
Funding Summary - Fire Unit
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | Complete | Total
RDT&E | 3897.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3897.7
Procurement | 83.2 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 8718.6
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 3980.9 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 12616.3
PB 2014 Total | 4038.3 | 540.4 | 540.5 | 559.6 | 566.8 | 655.2 | 536.8 | 5394.4 | 12832
Delta | -57.4 | 150 | -155.9 | -139.8 | -144.2 | -196.5 | -39.2 | 367.3 | -215.7
Quantity | Undistributed | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2014 Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding Summary - Missile
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | Complete | Total
RDT&E | 785.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785.3
Procurement | 83.2 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 8718.6
MILCON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 868.5 | 690.4 | 384.6 | 419.8 | 422.6 | 458.7 | 497.6 | 5761.7 | 9503.9
PB 2014 Total | 873.2 | 540.4 | 540.5 | 559.6 | 566.8 | 655.2 | 536.8 | 5394.4 | 9666.9
Delta | -4.7 | 150 | -155.9 | -139.8 | -144.2 | -196.5 | -39.2 | 367.3 | -163
The Army Acqusition Objective for the Patriot Advanced Capability Missile Segment Enhancement is 3.376 missiles.
The cost estimates for the Missile Subprogram in this report are based on the original program of record.
Quantity | Undistributed | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | 0 | 0 | 86 | 70 | 76 | 80 | 88 | 94 | 1034 | 1528
PB 2015 Total | 0 | 0 | 86 | 70 | 76 | 80 | 88 | 94 | 1034 | 1528
PB 2014 Total | 0 | 0 | 56 | 72 | 80 | 82 | 104 | 108 | 1026 | 1528
Delta | 0 | 0 | 30 | -2 | -4 | -2 | -16 | -14 | 0 | 0

## Cost Summary
Cost Summary - Total Program
| BY2004 $M |  |  | BY2004 $M | TY $M
Appropriation | SAR Baseline Deve Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 4992.3 | 4992.3 | -- | 3462.7 | 5737 | 5737 | 3965.3
Procurement | 17759.1 | 17759.1 | -- | 6165.7 | 24158.4 | 24158.4 | 8986.9
Flyaway | 15071.8 | -- | -- | 5662.5 | 20409.3 | -- | 8257.9
Recurring | 14809.2 | -- | -- | 5590.5 | 20095.8 | -- | 8170
Non Recurring | 262.6 | -- | -- | 72 | 313.5 | -- | 87.9
Support | 2687.3 |  | -- | 503.2 | 3749.1 | -- | 729
Other Support | 1550.4 | -- | -- | 503.2 | 2125.1 | -- | 729
Initial Spares | 1136.9 | -- | -- | 0 | 1624 | -- | 0
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 22751.4 | 22751.4 | N/A | 9628.4 | 29895.4 | 29895.4 | 12952.2
Cost Summary - Fire Unit
| BY2004 $M |  |  | BY2004 $M | TY $M
Appropriation | SAR Baseline Deve Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 4531.4 | 4531.4 | 5211.1 | 2758.8 | 5255 | 5255 | 3177.1
Procurement | 11999.1 | 11999.1 | 13199 | 0 | 16584.4 | 16584.4 | 0
Flyaway | 9818.9 | -- | -- | 0 | 13494.5 | -- | 0
Recurring | 9556.3 | -- | -- | 0 | 13181 | -- | 0
Non Recurring | 262.6 | -- | -- | 0 | 313.5 | -- | 0
Support | 2180.2 |  | -- | 0 | 3089.9 | -- | 0
Other Support | 1043.3 | -- | -- | 0 | 1465.9 | -- | 0
Initial Spares | 1136.9 | -- | -- | 0 | 1624 | -- | 0
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 16530.5 | 16530.5 | N/A | 2758.8 | 21839.4 | 21839.4 | 3177.1
Current estimate is based on the February 11, 2011, U.S. DoD decision to place aceiling on MEADS spending at $4B and continue with a modified Esigned and Development phase in a "Demonstration of Capabilities" effort funded through FY 2013. FY 2013 was the final year of funding for the Fire Unit (FU) Subprogram.
| SAR Baseline | Current APB Development
Quantity | Dev Est |  | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 48 | 48 | 0
Total | 48 | 48 | 0
Unit of Measure: FU is a representative unit of measure defined to include the ground support elements of the objective MEADS system: a Surveillance Radar; two Mu-ltFi unction Fire Control Radars; two Battle Management Command, Control, Communications, Computers and Intelligence Tactical Operations Centers; Launchers; and three Launcher Reloaders. The program FU development estimate quantity is based on the planned objective force of 48 tactical FUs, which comprise 16 Battalions with three FUs each. Unit cost calculations include equipment at the Battalion level, which is above that at the FU level.
Cost Summary - Missile
| BY2004 $M |  |  | BY2004 $M | TY $M
Appropriation | SAR Baseline Deve Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 460.9 | 460.9 | 530 | 701.9
Procurement | 5760 | 5760 | 6336 | 5908.6 | 7574 | 7574 | 8718.6
Flyaway | -- | -- | -- | 5397.5 | -- | -- | 7972.8
Recurring | -- | -- | -- | 5329.1 | -- | -- | 7889.6
Non Recurring | -- | -- | -- | 68.4 | -- | -- | 83.2
Support | -- |  | -- | 511.1 | -- | -- | 745.8
Other Support | -- | -- | -- | 511.1 | -- | -- | 745.8
Initial Spares | -- | -- | -- | 0 | -- | -- | 0
MILCON | 0 | 0 | -- | 0 | 0 | 0 | 0
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 6220.9 | 6220.9 | N/A | 6610.5 | 8056 | 8056 | 9503.9
Signifies APB Breach
The Patriot/MEADS CAP missile procurement funds in FY 2010 - FY 2013 were transferred to the Patriot Advanced Capability-3 (PAC-3) procurement funding line to obtain additional PAC-3 missile quantities.
Quantity | SAR Baseline Dev Est | Current APB Development | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 1528 | 1528 | 1528
Total | 1528 | 1528 | 1528
Unit of Measure: The Missile Segment Enhancement is the representative unit of measure for the Missile Subprogram.

## Annual Funding
Annual Funding TY$ - Fire Unit
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2004 | -- | -- | -- | -- | -- | -- | 126.9
2005 | -- | -- | -- | -- | -- | -- | 164
2006 | -- | -- | -- | -- | -- | -- | 193
2007 | -- | -- | -- | -- | -- | -- | 211
2008 | -- | -- | -- | -- | -- | -- | 316.3
2009 | -- | -- | -- | -- | -- | -- | 423.7
2010 | -- | -- | -- | -- | -- | -- | 501.1
2011 | -- | -- | -- | -- | -- | -- | 450.6
2012 | -- | -- | -- | -- | -- | -- | 377.6
2013 | -- | -- | -- | -- | -- | -- | 348.2
Subtotal | -- | -- | -- | -- | -- | -- | 3112.4
Annual Funding BY$ - Fire Unit
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, and Evaluation, Army
Non End Item Recurring Flyaway
|  | End Item Recurring Flyaway | BY 2004 $M | Non Recurring Flyaway | Total | Total | Total
Fiscal |  | BY 2004 $M |  | BY 2004 $M | Flyaway | Support | Program
Year | Quantity |  |  |  | BY 2004 $M | BY 2004 $M | BY 2004 $M
2004 | -- | -- | -- | -- | -- | -- | 124
2005 | -- | -- | -- | -- | -- | -- | 155.7
2006 | -- | -- | -- | -- | -- | -- | 178.3
2007 | -- | -- | -- | -- | -- | -- | 190.4
2008 | -- | -- | -- | -- | -- | -- | 280.1
2009 | -- | -- | -- | -- | -- | -- | 370.4
2010 | -- | -- | -- | -- | -- | -- | 431.5
2011 | -- | -- | -- | -- | -- | -- | 380.5
2012 | -- | -- | -- | -- | -- | -- | 313.8
2013 | -- | -- | -- | -- | -- | -- | 284.1
Subtotal | -- | -- | -- | -- | -- | -- | 2708.8
Annual Funding TY$ - Missile
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Non End Item Recurring Flyaway TY $M
|  | End Item Recurring Flyaway TY $M |  | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
Fiscal
Year | Quantity
2004 | -- | -- | -- | -- | -- | -- | 109.9
2005 | -- | -- | -- | -- | -- | -- | 87.3
2006 | -- | -- | -- | -- | -- | -- | 81.4
2007 | -- | -- | -- | -- | -- | -- | 111.9
2008 | -- | -- | -- | -- | -- | -- | 53.5
2009 | -- | -- | -- | -- | -- | -- | 31
2010 | -- | -- | -- | -- | -- | -- | 65.1
2011 | -- | -- | -- | -- | -- | -- | 121.5
2012 | -- | -- | -- | -- | -- | -- | 86.1
2013 | -- | -- | -- | -- | -- | -- | 37.6
Subtotal | -- | -- | -- | -- | -- | -- | 785.3
Annual Funding BY$ - Missile
2040 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Army
Non End Item Recurring Flyaway
|  | End Item Recurring Flyaway | BY 2004 $M | Non Recurring Flyaway | Total | Total | Total
Fiscal |  | BY 2004 $M |  | BY 2004 $M | Flyaway | Support | Program
Year | Quantity |  |  |  | BY 2004 $M | BY 2004 $M | BY 2004 $M
2004 | -- | -- | -- | -- | -- | -- | 107.4
2005 | -- | -- | -- | -- | -- | -- | 82.9
2006 | -- | -- | -- | -- | -- | -- | 75.2
2007 | -- | -- | -- | -- | -- | -- | 101
2008 | -- | -- | -- | -- | -- | -- | 47.4
2009 | -- | -- | -- | -- | -- | -- | 27.1
2010 | -- | -- | -- | -- | -- | -- | 56.1
2011 | -- | -- | -- | -- | -- | -- | 102.6
2012 | -- | -- | -- | -- | -- | -- | 71.5
2013 | -- | -- | -- | -- | -- | -- | 30.7
Subtotal | -- | -- | -- | -- | -- | -- | 701.9
Annual Funding TY$ - Missile
2032 ¦ Procurement ¦ Missile Procurement, Army
Non End Item Recurring Flyaway TY $M
|  | End Item Recurring Flyaway TY $M |  | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
Fiscal
Year | Quantity
2012 | -- | -- | -- | 75 | 75 | -- | 75
2013 | -- | -- | -- | 8.2 | 8.2 | -- | 8.2
2014 | 86 | 603.4 | -- | -- | 603.4 | 87 | 690.4
2015 | 70 | 336.1 | -- | -- | 336.1 | 48.5 | 384.6
2016 | 76 | 377.8 | -- | -- | 377.8 | 42 | 419.8
2017 | 80 | 382 | -- | -- | 382 | 40.6 | 422.6
2018 | 88 | 414.7 | -- | -- | 414.7 | 44 | 458.7
2019 | 94 | 449.8 | -- | -- | 449.8 | 47.8 | 497.6
2020 | 90 | 467.8 | -- | -- | 467.8 | 35.2 | 503
2021 | 90 | 466 | -- | -- | 466 | 36.7 | 502.7
2022 | 90 | 465.8 | -- | -- | 465.8 | 36.7 | 502.5
2023 | 90 | 465.3 | -- | -- | 465.3 | 36.7 | 502
2024 | 90 | 464.7 | -- | -- | 464.7 | 36.7 | 501.4
2025 | 90 | 464.1 | -- | -- | 464.1 | 36.7 | 500.8
2026 | 90 | 463.5 | -- | -- | 463.5 | 36.7 | 500.2
2027 | 90 | 464.5 | -- | -- | 464.5 | 35 | 499.5
2028 | 90 | 464.1 | -- | -- | 464.1 | 34.9 | 499
2029 | 90 | 463.7 | -- | -- | 463.7 | 34.9 | 498.6
2030 | 90 | 463.3 | -- | -- | 463.3 | 34.9 | 498.2
2031 | 44 | 213 | -- | -- | 213 | 16 | 229
2032 | -- | -- | -- | -- | -- | 12.4 | 12.4
2033 | -- | -- | -- | -- | -- | 12.4 | 12.4
Subtotal | 1528 | 7889.6 | -- | 83.2 | 7972.8 | 745.8 | 8718.6
Annual Funding BY$ - Missile
2032 ¦ Procurement ¦ Missile Procurement, Army
2012 | -- | -- | -- | 61.8 | 61.8 | -- | 61.8
2013 | -- | -- | -- | 6.6 | 6.6 | -- | 6.6
2014 | 86 | 477.6 | -- | -- | 477.6 | 68.8 | 546.4
2015 | 70 | 261.4 | -- | -- | 261.4 | 37.7 | 299.1
2016 | 76 | 288.1 | -- | -- | 288.1 | 32 | 320.1
2017 | 80 | 285.5 | -- | -- | 285.5 | 30.4 | 315.9
2018 | 88 | 303.9 | -- | -- | 303.9 | 32.3 | 336.2
2019 | 94 | 323.2 | -- | -- | 323.2 | 34.3 | 357.5
2020 | 90 | 329.5 | -- | -- | 329.5 | 24.8 | 354.3
2021 | 90 | 321.8 | -- | -- | 321.8 | 25.3 | 347.1
2022 | 90 | 315.4 | -- | -- | 315.4 | 24.8 | 340.2
2023 | 90 | 308.8 | -- | -- | 308.8 | 24.4 | 333.2
2024 | 90 | 302.4 | -- | -- | 302.4 | 23.9 | 326.3
2025 | 90 | 296.1 | -- | -- | 296.1 | 23.4 | 319.5
2026 | 90 | 289.9 | -- | -- | 289.9 | 23 | 312.9
2027 | 90 | 284.8 | -- | -- | 284.8 | 21.5 | 306.3
2028 | 90 | 279 | -- | -- | 279 | 21 | 300
2029 | 90 | 273.3 | -- | -- | 273.3 | 20.6 | 293.9
2030 | 90 | 267.7 | -- | -- | 267.7 | 20.2 | 287.9
2031 | 44 | 120.7 | -- | -- | 120.7 | 9 | 129.7
2032 | -- | -- | -- | -- | -- | 6.9 | 6.9
2033 | -- | -- | -- | -- | -- | 6.8 | 6.8
Subtotal | 1528 | 5329.1 | -- | 68.4 | 5397.5 | 511.1 | 5908.6

## Unit Cost Report
Fire Unit, Unit Cost Report
| BY2004 $M | BY2004 $M
| Current UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Unit Cost
Program Acquisition Unit Cost (PAUC)
Cost | 16530.5 | 2708.8
Quantity | 48 | 0
Unit Cost | 344.385 | -- | --
Average Procurement Unit Cost (APUC)
Cost | 11999.1 | 0
Quantity | 48 | 0
Unit Cost | 249.981 | -- | --
| BY2004 $M | BY2004 $M
| Current UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Unit Cost
Program Acquisition Unit Cost (PAUC)
Cost | 16530.5 | 2708.8
Quantity | 48 | 0
Unit Cost | 344.385 | -- | --
Average Procurement Unit Cost (APUC)
Cost | 11999.1 | 0
Quantity | 48 | 0
Unit Cost | 249.981 | -- | --
Fire Unit, Unit Cost History
|  | BY2004 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2004-08-01 | 344.385 | 249.981 | 454.988 | 345.508
APB as of January 2006 | 2004-08-01 | 344.385 | 249.981 | 454.988 | 345.508
Revised Original APB | NA | NA | NA | NA | NA
Prior APB | NA | NA | NA | NA | NA
Current APB | 2004-08-01 | 344.385 | 249.981 | 454.988 | 345.508
Prior Annual SAR | 2012-12-01 | NA | NA | NA | NA
Current Estimate | 2013-12-01 | NA | NA | NA | NA
Missile, Unit Cost Report
| BY2004 $M | BY2004 $M
| Current UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Unit Cost
Program Acquisition Unit Cost (PAUC)
Cost | 6220.9 | 6610.5
Quantity | 1528 | 1528
Unit Cost | 4.071 | 4.326 | 6.26
Average Procurement Unit Cost (APUC)
Cost | 5760 | 5908.6
Quantity | 1528 | 1528
Unit Cost | 3.77 | 3.867 | 2.57
| BY2004 $M | BY2004 $M
| Current UCR Baseline (AUG 2004 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Unit Cost
Program Acquisition Unit Cost (PAUC)
Cost | 6220.9 | 6610.5
Quantity | 1528 | 1528
Unit Cost | 4.071 | 4.326 | 6.26
Average Procurement Unit Cost (APUC)
Cost | 5760 | 5908.6
Quantity | 1528 | 1528
Unit Cost | 3.77 | 3.867 | 2.57

## Cost Variance
Cost Variance
Fire Unit
Summary Then Year $M |  |  |  |  | Change Time | Unit | SubProgram | FYearSourcSARS
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 5255 | 16584.4 | -- | 21839.4 | Previous Changes | Then Year $M | Fire Unit | 2014
[5 empty] | Previous Changes | Then Year $M | Fire Unit | 2014
Economic | 127.2 | -193.6 | -- | -66.4 | Previous Changes | Then Year $M | Fire Unit | 2014
Quantity | -- | -12555.5 | -- | -12555.5 | Previous Changes | Then Year $M | Fire Unit | 2014
Schedule | -- | -86.5 | -- | -86.5 | Previous Changes | Then Year $M | Fire Unit | 2014
Engineering | -- | -- | -- | -- | Previous Changes | Then Year $M | Fire Unit | 2014
Estimating | -2217.1 | -706.7 | -- | -2923.8 | Previous Changes | Then Year $M | Fire Unit | 2014
Other | -- | -- | -- | -- | Previous Changes | Then Year $M | Fire Unit | 2014
Support | -- | -3042.1 | -- | -3042.1 | Previous Changes | Then Year $M | Fire Unit | 2014
Subtotal | -2089.9 | -16584.4 | -- | -18674.3 | Previous Changes | Then Year $M | Fire Unit | 2014
Current Changes |  |  |  |  | Current Changes | Then Year $M | Fire Unit | 2014
Economic | -7 | -- | -- | -7 | Current Changes | Then Year $M | Fire Unit | 2014
Quantity | -- | -- | -- | -- | Current Changes | Then Year $M | Fire Unit | 2014
Schedule | -- | -- | -- | -- | Current Changes | Then Year $M | Fire Unit | 2014
Engineering | -- | -- | -- | -- | Current Changes | Then Year $M | Fire Unit | 2014
Estimating | -45.7 | -- | -- | -45.7 | Current Changes | Then Year $M | Fire Unit | 2014
Other | -- | -- | -- | -- | Current Changes | Then Year $M | Fire Unit | 2014
Support | -- | -- | -- | -- | Current Changes | Then Year $M | Fire Unit | 2014
Subtotal | -52.7 | -- | -- | -52.7 | Current Changes | Then Year $M | Fire Unit | 2014
Total Changes | -2142.6 | -16584.4 | -- | -18727 | Total | Then Year $M | Fire Unit | 2014
CE - Cost Variance | 3112.4 | -- | -- | 3112.4 | Total | Then Year $M | Fire Unit | 2014
CE - Cost & Funding | 3112.4 | -- | -- | 3112.4 | Total | Then Year $M | Fire Unit | 2014
2014
Summary Base Year 2004 $M | [5 empty] | Base Year $M | Fire Unit | 2014
| RDT&E | Proc | MILCON | Total |  | Base Year $M | Fire Unit | 2014
SAR Baseline (Dev Est) | 4531.4 | 11999.1 | -- | 16530.5 |  | Base Year $M | Fire Unit | 2014
Previous Changes | [5 empty] | Base Year $M | Fire Unit | 2014
Economic | -- | -- | -- | -- |  | Base Year $M | Fire Unit | 2014
Quantity | -- | -8875.5 | -- | -8875.5 |  | Base Year $M | Fire Unit | 2014
Schedule | -- | -148 | -- | -148 |  | Base Year $M | Fire Unit | 2014
Engineering | -- | -- | -- | -- |  | Base Year $M | Fire Unit | 2014
Estimating | -1785.5 | -795.4 | -- | -2580.9 |  | Base Year $M | Fire Unit | 2014
Other | -- | -- | -- | -- |  | Base Year $M | Fire Unit | 2014
Support | -- | -2180.2 | -- | -2180.2 |  | Base Year $M | Fire Unit | 2014
Subtotal | -1785.5 | -11999.1 | -- | -13784.6 |  | Base Year $M | Fire Unit | 2014
Current Changes | [5 empty] | Base Year $M | Fire Unit | 2014
Economic | -- | -- | -- | -- |  | Base Year $M | Fire Unit | 2014
Quantity | -- | -- | -- | -- |  | Base Year $M | Fire Unit | 2014
Schedule | -- | -- | -- | -- |  | Base Year $M | Fire Unit | 2014
Engineering | -- | -- | -- | -- |  | Base Year $M | Fire Unit | 2014
Estimating | -37.1 | -- | -- | -37.1 |  | Base Year $M | Fire Unit | 2014
Other | -- | -- | -- | -- |  | Base Year $M | Fire Unit | 2014
Support | -- | -- | -- | -- |  | Base Year $M | Fire Unit | 2014
Subtotal | -37.1 | -- | -- | -37.1 |  | Base Year $M | Fire Unit | 2014
Total Changes | -1822.6 | -11999.1 | -- | -13821.7 |  | Base Year $M | Fire Unit | 2014
CE - Cost Variance | 2708.8 | -- | -- | 2708.8 |  | Base Year $M | Fire Unit | 2014
CE - Cost & Funding | 2708.8 | -- | -- | 2708.8 |  | Base Year $M | Fire Unit | 2014
Previous Estimate: December 2012
Cost Variance
Missile
Summary Then Year $M | [5 empty] | Then Year $M | Missile | 2014
| RDT&E | Proc | MILCON | Total |  | Then Year $M | Missile | 2014
SAR Baseline (Dev Est) | 482 | 7574 | -- | 8056 |  | Then Year $M | Missile | 2014
[6 empty] | Then Year $M | Missile | 2014
Economic | 18.5 | 325.9 | -- | 344.4 |  | Then Year $M | Missile | 2014
Quantity | -- | -- | -- | -- |  | Then Year $M | Missile | 2014
Schedule | -- | 634.8 | -- | 634.8 |  | Then Year $M | Missile | 2014
Engineering | -- | -- | -- | -- |  | Then Year $M | Missile | 2014
Estimating | 284.8 | 335.2 | -- | -2923.8 |  | Then Year $M | Missile | 2014
Other | -- | -- | -- | -- |  | Then Year $M | Missile | 2014
Support | -- | 11.7 | -- | 11.7 |  | Then Year $M | Missile | 2014
Subtotal | 303.3 | 1307.6 | -- | 1610.9 |  | Then Year $M | Missile | 2014
Current Changes | [5 empty] | Then Year $M | Missile | 2014
Economic | -1.1 | -54.2 | -- | -55.3 |  | Then Year $M | Missile | 2014
Quantity | -- | -- | -- | -- |  | Then Year $M | Missile | 2014
Schedule | -- | -162.6 | -- | -162.6 |  | Then Year $M | Missile | 2014
Engineering | -- | -- | -- | -- |  | Then Year $M | Missile | 2014
Estimating | 1.1 | 1.1 | -- | 2.2 |  | Then Year $M | Missile | 2014
Other | -- | -- | -- | -- |  | Then Year $M | Missile | 2014
Support | -- | 52.7 | -- | 52.7 |  | Then Year $M | Missile | 2014
Subtotal | -52.7 | -163 | -- | -163 |  | Then Year $M | Missile | 2014
Total Changes | 303.3 | 1144.6 | -- | 1447.9 |  | Then Year $M | Missile | 2014
CE - Cost Variance | 785.3 | 8718.6 | -- | 9503.9 |  | Then Year $M | Missile | 2014
CE - Cost & Funding | 785.3 | 8718.6 | -- | 9503.9 |  | Then Year $M | Missile | 2014
Missile
Summary Base Year 2004 $M | [5 empty] | Base Year $M | Missile | 2014
| RDT&E | Proc | MILCON | Total |  | Base Year $M | Missile | 2014
SAR Baseline (Dev Est) | 460.9 | 5760 | -- | 6220.9 |  | Base Year $M | Missile | 2014
Previous Changes | [5 empty] | Base Year $M | Missile | 2014
Economic | -- | -- | -- | -- |  | Base Year $M | Missile | 2014
Quantity | -- | -- | -- | -- |  | Base Year $M | Missile | 2014
Schedule | -- | 48.6 | -- | 48.6 |  | Base Year $M | Missile | 2014
Engineering | -- | -- | -- | -- |  | Base Year $M | Missile | 2014
Estimating | 240.1 | 302.9 | -- | 543 |  | Base Year $M | Missile | 2014
Other | -- | -- | -- | -- |  | Base Year $M | Missile | 2014
Support | -- | -24.6 | -- | -24.6 |  | Base Year $M | Missile | 2014
Subtotal | 240.1 | 326.9 | -- | 567 |  | Base Year $M | Missile | 2014
Current Changes | [5 empty] | Base Year $M | Missile | 2014
Economic | -- | -- | -- | -- |  | Base Year $M | Missile | 2014
Quantity | -- | -- | -- | -- |  | Base Year $M | Missile | 2014
Schedule | -- | -208.2 | -- | -208.2 |  | Base Year $M | Missile | 2014
Engineering | -- | -- | -- | -- |  | Base Year $M | Missile | 2014
Estimating | 0.9 | 1.3 | -- | 2.2 |  | Base Year $M | Missile | 2014
Other | -- | -- | -- | -- |  | Base Year $M | Missile | 2014
Support | -- | 28.6 | -- | 28.6 |  | Base Year $M | Missile | 2014
Subtotal | 0.9 | -178.3 | -- | -177.4 |  | Base Year $M | Missile | 2014
Total Changes | 241 | 148.6 | -- | 389.6 |  | Base Year $M | Missile | 2014
CE - Cost Variance | 701.9 | 5908.6 | -- | 6610.5 |  | Base Year $M | Missile | 2014
CE - Cost & Funding | 701.9 | 5908.6 | -- | 6610.5 |  | Base Year $M | Missile | 2014
RDT&E | $M
| Base | Then
Current Change Explanations | Year | Year
Revised escalation indices. (Economic) | N/A | -1.1
Adjustment for current and prior escalation. (Estimating) | 0.9 | 1.1
RDT&E Subtotal | 0.9 | 0
Procurement | $M
| Base | Then
Current Change Explanations | Year | Year
Revised escalation indices. (Economic) | N/A | -54.2
Stretch-out of procurement buy profile in FY 2020 through FY 2033. (Schedule)
(Schedule) | 0 | 93.3
Adjustment for current and prior escalation. (Estimating) | 4.8 | 5.8
Additional Schedule Variance due to the acceleration of 30 missiles in FY 2014
(procurement changed from 56 to 86 missiles). (Schedule) | -208.2 | -255.9
Decrease in FY 2013 funding due to Congressional reduction. (Estimating) | -3.5 | -4.7
Adjustment for current and prior escalation. (Support) | 0.5 | 0.8
Increase in Other Support due to stretch-out of procurement buy profile. (Support)
(Support) | 28.1 | 51.9
Procurement Subtotal | -178.3 | -163

## Unit Cost History
Missile Unit Cost History
|  | BY2004 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2004-08-01 | 4.071 | 3.77 | 5.272 | 4.957
APB as of January 2006 | 2004-08-01 | 4.071 | 3.77 | 5.272 | 4.957
Revised Original APB | NA | NA | NA | NA | NA
Prior APB | NA | NA | NA | NA | NA
Current APB | 2004-08-01 | 4.071 | 3.77 | 5.272 | 4.957
Prior Annual SAR | 2012-12-01 | 4.442 | 3.984 | 6.327 | 5.813
Current Estimate | 2013-12-01 | 4.326 | 3.867 | 6.22 | 5.706
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Dev Est | Changes | [7 empty] | PAUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
5.272 | 0.189 | 0 | 0.309 | 0 | 0.408 | 0 | 0.042 | 0.948 | 6.22
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes Econ: Changes | APUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
4.957 | 0.178 | 0 | 0.309 | 0 | 0.22 | 0 | 0.042 | 0.749 | 5.7

## Baseline History
SAR Baseline History
Item/Event | SAR Planning Estimate (PE) | SAR Development Estimate (DE) | SAR Production Estimate (PdE) | Current Estimate
Milestone A | N/A | N/A | N/A | N/A
Milestone B | N/A | N/A | N/A | N/A
Milestone C | N/A | N/A | N/A | N/A
FUE | N/A | 2011-03-01 | N/A | 2015-09-01
Total Cost (TY $M) | N/A | 8056 | N/A | 9503.9
Total Quantity | N/A | 1528 | N/A | 1528
Prog. Acq. Unit Cost (PAUC) | N/A | 5.272 | N/A | 6.22

## Contracts
Appropriation: RDT&E
Contract Name | D&D
Contractor | MEADS International Inc.
Contractor Location | 5600 W Sand Lake Road Orlando FL 32819
Contract Number, Type | NAMEAD-04-C-6000, CPFF Award Date
Award Date | 2004-09-28
Definitization Date | 2005-02-16
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
3400 | N/A | 0 | 3653 | N/A | 0 | 3653 | 3653
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to contract modifications implemented for emerging program requirements, which included Missile Segment Enhancement integration, extended risk reduction actvities, and flight test activities.
Variance | Cost Variance | Schedule Variance
Cumulative Variances To Date (1/31/2014) | -2.5 | -3.1
Previous Cumulative Variances | 29.9 | -15.3
Net Change | -32.4 | 12.2
Cost and Schedule Variance Explanations
The unfavorable net change in the cost variance is due to additional Integrated Product Team (IPT) support requirements leading up to the November 2013 flight test and continued activities to support additional testing at the White Sands Missile Range, New Mexico, as well as continued software build work for FY 2014 demonstrations.
The favorable net change in the schedule variance is due to the fact that IPTs implemented revised contract performance measurement baselines to reflect current flight test dates and revised test requirements.
Appropriation: RDT&E
Contract Name | MSE Follow on Test Prg
Contractor | Lockheed Martin Corporation
Contractor Location | 1701 W Marshall Drive, Dallas TX 75265
Contract Number, Type | W31P4Q-07-G-0001/12, CPFF
Award Date | 2010-08-23
Definitization Date | 2011-07-18
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
49.1 | N/A | N/A | 51 | N/A | N/A | 77.4 | 78.9
Target Price Change Explanation
The difference between the Initial Contract Price Target and the Current Contract Price Target is due to a contract modification to extend the period of performance.
However, the Contractor and Program Manager Estimated Prices at Completion have increased due to an undefinitized contract modification for components for four test missiles. The effort was placed on contract as authorized unpriced work; therefore, until definitized, the Current Contract Price Target is unchanged.
Variance | Cost Variance | Schedule Variance
Cumulative Variances To Date (1/26/2014) | -0.1 | -0.5
Previous Cumulative Variances | 1.2 | -1.4
Net Change | -1.3 | 0.9
Cost and Scheduel Variance Explanations
The unfavorable net change in the cost variance is due to additional manpower added to support the preparation for the Flight Test 7-5. Manpower increased due to added effort to procure and assemble four Patriot Advanced Capability-3 (PAC-3) Missile Segment Enhancement (MSE) missiles.
The favorable net change in the schedule variance is due to successful Flight Tests 7-4 and 7-5 with minimal remaining tasks to be completed.
Appropriation: Procurement
Contract Name | MSE IPF (Missile Segment Enhancement Initial Production Facilities
Contractor | Lockheed Martin Corporation
Contractor Location | 1701 W Marshall Drive, Dallas TX 75265
Contract Number, Type | W31P4Q-07-G-0001, CPFF
Award Date | 2012-07-02
Definitization Date | 2012-07-02
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
69 | N/A | 0 | 69 | N/A | 0 | 77.4 | 78.2
Variance | Cost Variance | Schedule Variance
Cumulative Variances To Date (1/26/2014) | 2.2 | -9.3
Previous Cumulative Variances | 0.1 | 0.2
Net Change | 2.1 | -9.5
Target Price Change Explanation
The favorable net change in the cost variance is due to contract requirements not being met, which delayed major purchase orders during the 12-month period.
The unfavorable net change in the schedule variance is due to delays in tool fabrication and development of control surfaces during the first six months. During the last six-month period, delays were driven by tool fabrication, material delivery and tool orders, and Dallas production operations tool capacity issues. Aerojet also experienced delays with its subtier suppliers ordering materials and tools.
Variance | Cost Variance | Schedule Variance
Cumulative Variances To Date (1/31/2014) | -2.5 | -3.1
Previous Cumulative Variances | 29.9 | -15.3
Net Change | -32.4 | 12.2
Deliveries and Expenditures
Fire Unit
Expended and Appropriated (TY $M)
Total Acquisition Cost | 3112.4 | Years Appropriated | 10
Expended to Date | 3149.9 | Percent Years Appropriated | 100%
Percent Expended | 101.2% | Appropriated to Date | 3112.4
Total Funding Years | 10 | Percent Appropriated | 100%
Missile
Expended and Appropriated (TY $M)
Total Acquisition Cost | 9503.9 | Years Appropriated | 11
Expended to Date | 726.2 | Percent Years Appropriated | 36.67%
Percent Expended | 7.64% | Appropriated to Date | 155839
Total Funding Years | 30 | Percent Appropriated | 16.4%