## Cost Summary
| BY2000 $M |  |  | BY2000 $M | TY $M
Appropriation | SAR Baseline Dev Est | Current APB Development Objective/Threshold |  | Current Estimate | SAR Baseline Dev Est | Current APB Development Objective | Current Estimate
RDT&E | 840.4 | 3076.8 | 3384.5 | 3237.2 | 906.2 | 3572 | 3783.2
Procurement | 3484.4 | 4904.9 | 5395.4 | 4302 | 4459.8 | 6022.6 | 5223.6
Flyaway | -- | -- | -- | 3349 | -- | -- | 4054.7
Recurring | -- | -- | -- | 3131.1 | -- | -- | 3771.4
Non Recurring | -- | -- | -- | 217.9 | -- | -- | 283.3
Support | -- | -- | -- | 953 | -- | -- | 1168.9
Other Support | -- | -- | -- | 305.4 | -- | -- | 368.2
Initial Spares | -- | -- | -- | 647.6 | -- | -- | 800.7
MILCON | 25.5 | 121.9 | 134.1 | 106 | 28 | 139.8 | 122.9
Acq O&M | 0 | 0 | -- | 0 | 0 | 0 | 0
Total | 4350.3 | 8103.6 | N/A | 7645.2 | 5394 | 9734.4 | 9129.7
Quantity | SAR Baseline Dev Est | Current APB Development | Current Estimate
RDT&E | 0 | 0 | 0
Procurement | 63 | 54 | 45
Total | 63 | 54 | 45
Unit of measure is number of aircraft. The FY 2014 baseline is 45 aircraft (7 Block 10s, 6 Block 20s, 21 Block 30s, and 11 Block 40s).

## Cost and Funding
Appropritaion and Quantity Summary
FY2015 President's Budget/December 2013 SAR (TY$ M)
Appropriation | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | To Complete | Total
RDT&E | 3237.5 | 94 | 157.5 | 160.3 | 133.9 | 0 | 0 | 0 | 3783.2
Procurement | 4773 | 45.7 | 86.8 | 150 | 64.3 | 69.9 | 15.2 | 18.7 | 5223.6
MILCON | 122.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122.9
Acq O&M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB 2015 Total | 8133.4 | 139.7 | 244.3 | 310.3 | 198.2 | 69.9 | 15.2 | 18.7 | 9129.7
PB 2014 Total | 8496.4 | 170.5 | 166.3 | 81.1 | 44 | 44.8 | 6.2 | 0 | 9009.3
Delta | -363 | -30.8 | 78 | 229.2 | 154.2 | 25.1 | 9 | 18.7 | 120.4
Quantity | Undistributed | Prior | FY2014 | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | To Complete | Total
Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
PB 2015 Total | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
PB 2014 Total | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
Delta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Annual Funding By Appropriation
Annual Funding TY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2001 | -- | -- | -- | -- | -- | -- | 129.5
2002 | -- | -- | -- | -- | -- | -- | 198.3
2003 | -- | -- | -- | -- | -- | -- | 329.1
2004 | -- | -- | -- | -- | -- | -- | 351.6
2005 | -- | -- | -- | -- | -- | -- | 368.3
2006 | -- | -- | -- | -- | -- | -- | 254.7
2007 | -- | -- | -- | -- | -- | -- | 223.1
2008 | -- | -- | -- | -- | -- | -- | 264.6
2009 | -- | -- | -- | -- | -- | -- | 227.7
2010 | -- | -- | -- | -- | -- | -- | 219.3
2011 | -- | -- | -- | -- | -- | -- | 190.9
2012 | -- | -- | -- | -- | -- | -- | 286.5
2013 | -- | -- | -- | -- | -- | -- | 193.9
2014 | -- | -- | -- | -- | -- | -- | 94
2015 | -- | -- | -- | -- | -- | -- | 157.5
2016 | -- | -- | -- | -- | -- | -- | 160.3
2017 | -- | -- | -- | -- | -- | -- | 133.9
Subtotal | -- | -- | -- | -- | -- | -- | 3783.2
Annual Funding BY$
3600 ¦ RDT&E ¦ Research, Development, Test, and Evaluation, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
2001 | -- | -- | -- | -- | -- | -- | 126.6
2002 | -- | -- | -- | -- | -- | -- | 191.8
2003 | -- | -- | -- | -- | -- | -- | 314
2004 | -- | -- | -- | -- | -- | -- | 327.3
2005 | -- | -- | -- | -- | -- | -- | 334.3
2006 | -- | -- | -- | -- | -- | -- | 224.4
2007 | -- | -- | -- | -- | -- | -- | 191.5
2008 | -- | -- | -- | -- | -- | -- | 222.7
2009 | -- | -- | -- | -- | -- | -- | 189.1
2010 | -- | -- | -- | -- | -- | -- | 179.9
2011 | -- | -- | -- | -- | -- | -- | 153.7
2012 | -- | -- | -- | -- | -- | -- | 226.6
2013 | -- | -- | -- | -- | -- | -- | 150.7
2014 | -- | -- | -- | -- | -- | -- | 71.8
2015 | -- | -- | -- | -- | -- | -- | 118.2
2016 | -- | -- | -- | -- | -- | -- | 118
2017 | -- | -- | -- | -- | -- | -- | 96.6
Subtotal | -- | -- | -- | -- | -- | -- | 3237.2
Annual Funding TY$
3600 ¦ RDT&E ¦ Other Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2003 | -- | -- | -- | -- | -- | 0.6 | 0.6
2004 | -- | -- | -- | -- | -- | 0.2 | 0.2
2005 | -- | -- | -- | -- | -- | 0.3 | 334.3
2006 | -- | -- | -- | -- | -- | 0.3 | 0.3
2007 | -- | -- | -- | -- | -- | -- | --
2008 | -- | -- | -- | -- | -- | 0.8 | 0.8
2009 | -- | -- | -- | -- | -- | 0.3 | 0.3
Subtotal | -- | -- | -- | -- | -- | 2.5 | 2.5
Annual Funding BY$
3600 ¦ RDT&E ¦ Other Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
2003 | -- | -- | -- | -- | -- | 0.6 | 0.6
2004 | -- | -- | -- | -- | -- | 0.2 | 0.2
2005 | -- | -- | -- | -- | -- | 0.3 | 334.3
2006 | -- | -- | -- | -- | -- | 0.3 | 0.3
2007 | -- | -- | -- | -- | -- | -- | --
2008 | -- | -- | -- | -- | -- | 0.7 | 0.7
2009 | -- | -- | -- | -- | -- | 0.2 | 0.2
Subtotal | -- | -- | -- | -- | -- | 2.3 | 2.3
Annual Funding TY$
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway TY $M | Non End Item Recurring Flyaway TY $M | Non Recurring Flyaway TY $M | Total Flyaway TY $M | Total Support TY $M | Total Program TY $M
2001 | -- | 21 | -- | -- | 21 | -- | 21
2002 | 3 | 144.4 | -- | 8.7 | 153.1 | 7.1 | 160.2
2003 | 3 | 136.4 | -- | 11.1 | 147.5 | 31.1 | 178.6
2004 | 4 | 210.4 | -- | 3.5 | 213.9 | 38.1 | 252
2005 | 4 | 252.3 | -- | 8.4 | 260.7 | 84.5 | 345.2
2006 | 5 | 290.3 | -- | 2.4 | 292.7 | 59.1 | 351.8
2007 | 5 | 328.2 | 7.5 | 12.2 | 347.9 | 75.2 | 423.1
2008 | 5 | 362.5 | 25.7 | 7.4 | 395.6 | 132 | 527.6
2009 | 5 | 388.3 | 84.7 | 32.4 | 505.4 | 240.1 | 745.5
2010 | 4 | 341.1 | 86.7 | 20.3 | 448.1 | 127.2 | 575.3
2011 | 4 | 415.6 | 84.2 | -- | 499.8 | 65.5 | 565.3
2012 | 3 | 293.3 | 88.9 | -- | 382.2 | 106.6 | 488.8
2013 | -- | -- | 7 | 11.5 | 18.5 | 117.6 | 136.1
2014 | -- | -- | 33 | 11 | 44 | 1.7 | 45.7
2015 | -- | -- | 21.4 | 32.7 | 54.1 | 32.7 | 86.8
2016 | -- | -- | 46.1 | 90.1 | 136.2 | 13.8 | 150
2017 | -- | -- | 34.5 | 15.6 | 50.1 | 14.2 | 64.3
2018 | -- | -- | 38.4 | 16 | 54.4 | 15.5 | 69.9
2019 | -- | -- | 13.2 | -- | 13.2 | 2 | 15.2
2020 | -- | -- | 9.5 | -- | 9.5 | 1.4 | 10.9
2021 | -- | -- | 5.4 | -- | 5.4 | 0.8 | 6.2
2022 | -- | -- | 1.4 | -- | 1.4 | 0.2 | 1.6
Subtotal | 45 | 3183.8 | 587.6 | 283.3 | 4054.7 | 1166.4 | 5221.1
Annual Funding BY$
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway BY 2000 $M | Non End Item Recurring Flyaway BY 2000 $M | Non Recurring Flyaway BY 2000 $M | Total Flyaway BY 2000 $M | Total Support BY 2000 $M | Total Program BY 2000 $M
2001 | -- | 20.3 | -- | -- | 20.3 | -- | 20.3
2002 | 3 | 138.1 | -- | 8.3 | 146.4 | 6.8 | 153.2
2003 | 3 | 128.3 | -- | 10.4 | 138.7 | 29.3 | 168
2004 | 4 | 192.8 | -- | 3.2 | 196 | 34.9 | 230.9
2005 | 4 | 224.6 | -- | 7.5 | 232.1 | 75.2 | 307.3
2006 | 5 | 251.8 | -- | 2.1 | 253.9 | 51.2 | 305.1
2007 | 5 | 277.2 | 6.3 | 10.3 | 293.8 | 63.6 | 357.4
2008 | 5 | 301.4 | 21.4 | 6.2 | 329 | 109.7 | 438.7
2009 | 5 | 317.4 | 69.2 | 26.5 | 413.1 | 196.3 | 609.4
2010 | 4 | 273.6 | 69.5 | 16.3 | 359.4 | 102 | 461.4
2011 | 4 | 327.8 | 66.4 | -- | 394.2 | 51.7 | 445.9
2012 | 3 | 227.6 | 68.9 | -- | 296.5 | 82.7 | 379.2
2013 | -- | -- | 5.3 | 8.7 | 14 | 89 | 103
2014 | -- | -- | 24.5 | 8.2 | 32.7 | 1.3 | 34
2015 | -- | -- | 15.6 | 23.9 | 39.5 | 23.8 | 63.3
2016 | -- | -- | 32.9 | 64.4 | 97.3 | 9.9 | 107.2
2017 | -- | -- | 24.2 | 10.9 | 35.1 | 9.9 | 45
2018 | -- | -- | 26.4 | 11 | 37.4 | 10.6 | 48
2019 | -- | -- | 8.9 | -- | 8.9 | 1.3 | 10.2
2020 | -- | -- | 6.3 | -- | 6.3 | 0.9 | 7.2
2021 | -- | -- | 3.5 | -- | 3.5 | 0.5 | 4
2022 | -- | -- | 0.9 | -- | 0.9 | 0.1 | 1
Subtotal | 45 | 2680.9 | 450.2 | 217.9 | 3349 | 950.7 | 4299.7
Cost Quantity Information
3010 ¦ Procurement ¦ Aircraft Procurement, Air Force
Fiscal Year | Quantity | End Item Recurring Flyaway (Aligned with Quantity) BY 2000 $M
2001 | -- | --
2002 | 3 | 128.3
2003 | 3 | 121.8
2004 | 4 | 182.9
2005 | 4 | 217.4
2006 | 5 | 252.8
2007 | 5 | 274.7
2008 | 5 | 287.1
2009 | 5 | 334.7
2010 | 4 | 235.2
2011 | 4 | 355.7
2012 | 3 | 290.3
2013 | -- | --
2014 | -- | --
2015 | -- | --
2016 | -- | --
2017 | -- | --
2018 | -- | --
2019 | -- | --
2020 | -- | --
2021 | -- | --
2022 | -- | --
Subtotal | 45 | 2680.9
Annual Funding TY$
3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | Total Program TY $M
2003 | 11.7
2004 | 22.2
2005 | 9.8
2006 | 14.1
2007 | 48.6
2008 | --
2009 | --
2010 | 16.5
Subtotal | 45
Annual Funding BY$
3300 ¦ MILCON ¦ Military Construction, Air Force
Fiscal Year | Total Program BY 2000 $M
2003 | 10.9
2004 | 20.2
2005 | 8.6
2006 | 12.1
2007 | 40.9
2008 | --
2009 | --
2010 | 13.3
Subtotal | 106

## FMS
Foreign Military Sales
Country | Date of Sale | Quantity | Total Cost $M | Memo
NATO | 2009-09-03 | 5 | 2383 | The North Atlantic Treaty Organization (NATO) Alliance Ground Surveillance (AGS) program is pursuing a Direct Commercial Sale (DCS) to obtain five RQ-4B Global Hawk Block 40-like aircraft equipped with the Multi Platform Radar Technology Insertion Program (MP-RTIP) Synthetic Aperture Radar sensor and integrated with a NATO-unique ground station. The program is a cooperative development effort with 14 of the 28 NATO nations funding the procurement effort. Poland will officially join the program as soon as the Program Memorandum of Understanding (MOU) Amendment One is ratified by the two remaining nations in October 2014; industrial participation opportunities are under assessment. US Government (USG) costs include: 41.7% direct financial contribution to NATO for administrative/prime contract costs; alliance support (program management administration), and agreed MP-RTIP capability enhancements/configuration changes. The NATO AGS Management Agency (NAGSMA) program office awarded the DCS contract with Northrop Grumman on May 20, 2012. USG support is provided through a “Technical Arrangement” and not a Foreign Military Sales (FMS) case. Office of the Secretary of Defense transitioned the management of NATO AGS to the Air Force in May 2012. Incremental Preliminary Design Reviews are in progress and are scheduled to complete in March 2014.

## Unit Cost Report
| BY2000 $M | BY2000 $M
Unit Cost | Current UCR Baseline (MAR 2007 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 8103.6 | 7645.2
Quantity | 54 | 45
Unit Cost | 150.067 | 169.893 | 13.21
Average Procurement Unit Cost (APUC)
Cost | 4904.9 | 4302
Quantity | 54 | 45
Unit Cost | 90.831 | 95.6 | 5.25
| BY2000 $M | BY2000 $M
Unit Cost | Revised Original UCR Baseline (MAR 2007 APB) | Current Estimate (DEC 2013 SAR) | BY % Change
Program Acquisition Unit Cost (PAUC)
Cost | 8103.6 | 7645.2
Quantity | 54 | 45
Unit Cost | 150.067 | 169.893 | 13.21
Average Procurement Unit Cost (APUC)
Cost | 4904.9 | 4302
Quantity | 54 | 45
Unit Cost | 90.831 | 95.6 | 5.25
APB Unit Cost Breach
Global Hawk initially reported a critical Nunn-McCurdy breach and provided detailed Unit Cost reporting in the December 2010 SAR. The unit cost percent change will continue to be measured against the March 2007 Acquisition Program Baseline (APB) until the revised APB is approved.

## APB Unit Cost History
APB Unit Cost History
|  | BY2000 $M |  | TY $M
| Date | PAUC | APUC | PAUC | APUC
Original APB | 2001-03-01 | 69.052 | 55.308 | 85.619 | 70.79
APB as of January 2006 | 2002-12-01 | 101.896 | 56.953 | 115.459 | 65.673
Revised Original APB | 2007-03-01 | 150.067 | 90.831 | 180.267 | 111.53
Prior APB | 2007-12-01 | 101.986 | 56.953 | 115.459 | 65.673
Current APB | 2007-03-01 | 150.067 | 90.831 | 180.267 | 111.53
Prior Annual SAR | 2012-12-01 | 168.327 | 97.304 | 200.207 | 117.74
Current Estimate | 2013-12-01 | 169.893 | 95.6 | 202.882 | 116.08
Current SAR Baseline to Current Estimate (TY $M)
Initial PAUC Dev Est | Changes | [7 empty] | PAUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
85.619 | 0.802 | 20.726 | 1.664 | 51.896 | 24.833 | 0 | 17.342 | 117.263 | 202.882
Current SAR Baseline to Current Estimate (TY $M)
Initial APUC Dev Est | Changes Econ: Changes | PAUC Current Est
| Econ | Qty | Sch | Eng | Est | Oth | Spt | Total
70.79 | 0.142 | 14.795 | -10.502 | 14.564 | 10.682 | 0 | 16.609 | 45.29 | 116.08

## Cost Variance
Summary Then Year $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 906.2 | 4459.8 | 28 | 5394
Previous Changes
Economic | 32.4 | 18.4 | 3.6 | 54.4
Quality | -- | -608.5 | -- | -608.5
Schedule | 555.6 | -472.6 | -8.1 | 74.9
Engineering | 1547.2 | 644.3 | 117 | 2308.5
Estimating | 471.7 | 559.2 | -20.6 | 1010.3
Other | -- | -- | -- | --
Support | 75 | 697.7 | 3 | 775.7
Subtotal | 2681.9 | 838.5 | 94.9 | 3615.3
Current Changes
Economic | -6.3 | -12 | -- | -18.3
Quality | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | 15.7 | 11.1 | -- | 26.8
Estimating | 185.7 | -78.5 | -- | 107.2
Other | -- | -- | -- | --
Support | -- | 4.7 | -- | 4.7
Subtotal | 195.1 | -74.7 | -- | 120.4
Total Changes | 2877 | 763.8 | 94.9 | 3735.7
CE - Cost Variance | 3783.2 | 5223.6 | 122.9 | 9129.7
CE - Cost & Funding | 3783.2 | 5223.6 | 122.9 | 9129.7
Summary Base Year 2000 $M
| RDT&E | Proc | MILCON | Total
SAR Baseline (Dev Est) | 840.4 | 3484.4 | 25.5 | 4350.3
Previous Changes
Economic | -- | -- | -- | --
Quality | -- | -406.8 | -- | -406.8
Schedule | 414.4 | -357.2 | -2.1 | 55.1
Engineering | 1405.8 | 661.3 | 98.3 | 2165.4
Estimating | 355.7 | 441 | -18.2 | 778.2
Other | -- | -- | -- | --
Support | 73.7 | 556 | 2.5 | 632.2
Subtotal | 2249.6 | 894.3 | 80.5 | 3224.4
Current Changes
Economic | -- | -- | -- | --
Quality | -- | -- | -- | --
Schedule | -- | -- | -- | --
Engineering | 11.6 | 6.4 | -- | 18
Estimating | 135.6 | -82.2 | -- | 53.4
Other | -- | -- | -- | --
Support | -- | -0.9 | -- | -0.9
Subtotal | 147.2 | -76.7 | -- | 70.5
Total Changes | 2396.8 | 817.6 | 80.5 | 3294.9
CE - Cost Variance | 3237.2 | 4302 | 106 | 7645.2
CE - Cost & Funding | 3237.2 | 4302 | 106 | 7645.2
RDT&E | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -6.3
Removal of Ground Station Technology Refresh development. (Engineering) | -36.7 | -49.5
Addition of Block 30 unique development of Airborne Signals Intelligence Payload. (Engineering) | 26.8 | 36.4
Addition of Weather upgrades development. (Engineering) Adjustment for current and prior escalation. (Estimating) | 21.5 | 28.8
| 3.2 | 3.9
Net adjustments due to sequestration and congressional marks to the FY 2012, FY 2013, and FY 2014 PBs (Estimating) | -21.5 | -27.7
Adjustments to reconcile to prior years actual expenditures (Estimating) | -0.3 | -0.3
Revised estimate for System Engineering/Program Managemnet/System Testing to support additional development (Estimating) | 97.4 | 132
Revised estimate for Government Testing (Estimating) | 27.1 | 36.9
Revised estimate for Program Office support costs (Estimating) | 4.7 | 6.2
Revised Joint Mission Planning System development estimate and inclusion of Block 30 development (Estimating) | 25 | 34.7
RDT&E Subtotal | 147.2 | 195.1
Procurement | $M
Current Change Explanations | Base Year | Then Year
Revised escalation indices. (Economic) | N/A | -12
Removal of Ground Station Technology Refresh development. (Engineering) | -21.1 | -29
Removal of Communications Systems Technology Refresh modifications (Engineering) | -28.1 | -40.2
Restored retrofits of Advanced Signals Intelligence Porgram sensors on Block 30 aircraft (engineering) | 39.7 | 57.5
Addition of Weather Radar modifications (Engineering) | 15.9 | 22.8
Adjustment for current and prior escalation (Estimating) | 6.2 | 8.2
Net adjustments due to sequestration and congressional marks for FY 2012, FY 2013, & FY 2014 | -120.2 | -157.6
Adjustments to reconcile to prior years actual expenditures (Estimating) | -111.9 | -131.6
Revised estimate of modification for change requests and diminishing manufacturing sources (Estimating) | 42 | 59.7
Revised estimate and rephasing of program office management/other Government costs due to Blcok 30 continuation (Estimating) | 16.5 | 23.1
Revised estimate and rephasing of production shutdown costs due to Blcok 30 continuation (Estimating) | 49.5 | 69.4
Revised estimate for Mode 5/Automatic Dependent Surveillance -Broadcast Out modifications (Estimating) | 3.7 | 6
Revised estimate for International Maritime Satellite/Communication Security modifications due to rephasing and continuation of Block 30 (Estimating) | 29.9 | 41.3
Revised estiamte for low cost modifications (Estimating) | 2.1 | 3
Adjustment to current and prior escalation (Support) | 2.5 | 2.9
Increase in Other Support Adjustments to reconcile to prior years actual expenditures (Support) | 9.5 | 9.8
Decrease in Initial Spares. Adjustments to reconcile to prior years actual expenditures. (Support) | -12.9 | -8
Procurement Subtotal | -76.7 | -74.7

## Contracts
Appropriations: RDT&E
Contract Name | Global Hawk EMD Ground Station Re-Architecture (GSRA)
Contractor | Northrop Grumman
Contractor Location | San Diego, CA 92127-2412
Contract Number, Type | F33657-01-C-4600/2, CPIF
Award Date | 2009-09-29
Definitization Date | 2010-10-27
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price at Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
16.2 | N/A | N/A | 84.2 | N/A | N/A | 90.3 | 90.9
Variance | Cost Variance | Schedule Variance
Cumulative Variances To Date (2/21/2014) | -10 | -0.8
Previous Cumulative Variances | -4.7 | -1.2
Net Change | -5.3 | 0.4
The unfavorable net change in the cost variance is due to increased rates that occurred as part of the Northrop Grumman Corporation (NGC) corporate restructuring, as well as underestimated system engineering costs. These are a result of NGC merging two different System Engineering Organizations, which caused some delays but will benefit future programs by sharing NGC resources and reducing total costs across the enterprise.
Appropriations: Procurement
Contract Name | Global Hawk EMD Ground Station Re-Architecture (GSRA)
Contractor | Northrop Grumman
Contractor Location | San Diego, CA 92127-2412
Contract Number, Type | F33657-01-C-4600/2, CPIF
Award Date | 2009-09-29
Definitization Date | 2010-10-27
Initial Contract Price ($M)
Target | Ceiling | Qty
16.2 | N/A | N/A
Variance | Cost Variance | Schedule Variance
Cumulative Variances To Date (2/21/2014) | -10 | -0.8
Previous Cumulative Variances | -4.7 | -1.2
Net Change | -5.3 | 0.4