## SM-3 SARs
16-F-04020_DOC_45_BMDS_DEC_2015_SAR
RDT&E $M | $M
Current Change Explanations | Base Year | Then Year
Realigned SM-3 IIA initial procurement to RDT&E for test rounds, SPY-1 modernization, and Aegis Weapon System (AWS) 6.x; other Aegis adjustments. (Estimating) | +362.2 | +488.5
Procurement | $M
Current Change Explanations | Base Year | Then Year
Realigned SM-3 IIA missile funding to RDT&E for test rounds. (Estimating) | -189 | -250.5
Contract Identification
Block IIA AUR Development & Integration
Contract Price
Initial Contract Price ($M) |  |  | Current Contract Price ($M) |  |  | Estimated Price At Completion ($M)
Target | Ceiling | Qty | Target | Ceiling | Qty | Contractor | Program Manager
160 | N/A | N/A |  | N/A | N/A | 1643 | 1697
Contract Variance
Item | Cost Variance | Schedule Variance
Cumulative Variances To Date (12/31/2015) | -185.7 | -8
Previous Cumulative Variances | -114 | -8
Net Change | -71.7 | 0
BMDS-SAR_31_DEC_2011
RDT&E $M
Current Change Explanations | Base Year | Then Year
Additional Aegis SM-3 Block IIA test rounds (Estimating) | plus 117.1 | plus 153.8
Procurement $M
Current Change Explanations | Base Year | Then Year
Delayed Aegis SM-3 Block IIA Procurement by one year (Schedule) | minus 91.5 | minus 124.7
BMDS_Decebmer_2012_SAR
RDT&E
Block IIA AUR Development & Integration
Initial Contract Price ($M) | Current Contract Price ($M) | Estimated Price At Completion ($M)
Target Ceiling Qty | Target Ceiling Qty | Contractor Program Manager
160.0 N/A N/A | 1415.0 N/A N/A | 1401.0 1405.0
Variance | Cost Variance | Schedule Variance
Cumulative Variances To Date (2/13/2013) | -3 | -16
Previous Cumulative Variances
Net Change | -3 | -16
14-F-0402-DOC_12_BMDSDecember2013
RDT&E
Block IIA AUR Development & Integration
Initial Contract Price ($M) | Current Contract Price ($M) | Estimated Price At Completion ($M)
Target Ceiling Qty | Target Ceiling Qty | Contractor Program Manager
160.0 N/A N/A | 1442.0 N/A N/A | 1462.0 1472.0
Variance | Cost Variance | Schedule Variance
Cumulative Variances To Date (2/13/2013) | -41 | -26
Previous Cumulative Variances | -3 | -16
Net Change | -38 | -10
15-F-0504-BMDS_SAR__Dec_2014
Procurement
Current Change Explanations | Base Year | Then Year
Aegis realignment to implement SM-3 IB multi-year procurement; reduced SM-3 IIA buys and other program/Congressional adjustments (Estimating) | -243.3 | -328.8
RDT&E
Block IIA AUR Development & Integration
Initial Contract Price ($M) | Current Contract Price ($M) | Estimated Price At Completion ($M)
Target Ceiling Qty | Target Ceiling Qty | Contractor Program Manager
160.0 N/A N/A | 1481.0 N/A N/A | 1569.0 1584.0
Variance | Cost Variance | Schedule Variance
Cumulative Variances To Date (2/13/2013) | -114 | -8
Previous Cumulative Variances | -41 | -26
Net Change | -73 | 18