## Schedule
2010
Project: MD09 SM-3 BLOCK IIA Co-Development
Exhibit R-4, RDT&E | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015
SM-3 Blk llA System Design Review (SDR) | bar: FY 2009
SM-3 Blk IIA Preliminary Design Review (PDR) | bar: FY 2012
SM-3 Blk IIA Critical Design Review (CDR) | bar: FY 2013
2011 | FY 2009: Start; FY 2011: End
| Quarter | Year | Quarter | Year
SM-3 Blk IIA Preliminary Design Review (PDR) | FY 2009: 2; FY 2010: 2011; FY 2011: 2; FY 2012: 2011
BMD 4.0.1 Eng REL Preliminary Design Review (PDR) | FY 2009: 2; FY 2010: 2012; FY 2011: 2; FY 2012: 2012
SM-3 Blk IIA Critical Design Review (CDR) | FY 2009: 2; FY 2010: 2012; FY 2011: 2; FY 2012: 2012
BMD 4.0.1 Eng REL Critical Design Review (CDR) | FY 2009: 2; FY 2010: 2013; FY 2011: 2; FY 2012: 2013
BMD 4.0.1 Eng REL: Engineering Assessment (EA) #1 | FY 2009: 4; FY 2010: 2014; FY 2011: 4; FY 2012: 2014
BMD 4.0.1 Eng REL: Engineering Assessment (EA) #2 | FY 2009: 1; FY 2010: 2015; FY 2011: 1; FY 2012: 2015
Restrained Level Firing | FY 2009: 1; FY 2010: 2013; FY 2011: 1; FY 2012: 2013
Propulsion Test Vehicle -1 (PTV-I ) | FY 2009: 4; FY 2010: 2013; FY 2011: 4; FY 2012: 2013
Control Test vehicle - 1 (SCD CTV-I) | FY 2009: 2; FY 2010: 2014; FY 2011: 2; FY 2012: 2014
Control Test Vehicle -2 (SCD CTV-2) | FY 2009: 3; FY 2010: 2014; FY 2011: 3; FY 2012: 2014
SCD Flight Test Mission 1 (SFTM-I) | FY 2009: 1; FY 2010: 2015; FY 2011: 1; FY 2012: 2015
SCD Flight Test Mission 2 (SFTM-2) | FY 2009: 2; FY 2010: 2015; FY 2011: 2; FY 2012: 2015
2012 | FY 2009: Start; FY 2011: End
| Quarter | Year | Quarter | Year
SM-3 Blk IIA DACS Risk Reduction Implementation Decision | FY 2009: 1; FY 2010: 2012; FY 2011: 1; FY 2012: 2012
SM-3 Blk IIA DACS Preliminary Design Review (PDR) | FY 2009: 1; FY 2010: 2012; FY 2011: 1; FY 2012: 2012
SM-3 Blk IIA KW Preliminary Design Review (PDR) | FY 2009: 2; FY 2010: 2012; FY 2011: 2; FY 2012: 2012
SM-3 Blk IIA System Preliminary Design Review (PDR) | FY 2009: 2; FY 2010: 2012; FY 2011: 2; FY 2012: 2012
SM-3 Blk IIA ps Critical Design Review (CDR) | FY 2009: 2; FY 2010: 2013; FY 2011: 2; FY 2012: 2013
SM-3 Blk IIA SYS/KW Critical Design Review (CDR) | FY 2009: 4; FY 2010: 2013; FY 2011: 4; FY 2012: 2013
Restrained Level Firing | FY 2009: 2; FY 2010: 2013; FY 2011: 2; FY 2012: 2013
2013
| FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018
SM-3 Blk IIA DACS Risk Reduction Implementation Decision | bar: FY 2012
SM-3 Blk IIA DACS Preliminary Design Review (PDR) | bar: FY 2012
SM-3 Blk IIA KW Preliminary Design Review (PDR) | bar: FY 2012
SM-3 Blk IIA System Preliminary Design Review (PDR) | bar: FY 2012
SM-3 Blk IIA PS Critical Design Review (CDR) (Significant Event Planned) | bar: FY 2013
SM-3 Blk IIA SYS/KW Critical Design Review (CDR) (Significant Event Planned) | bar: FY 2013
Restrained Level Firing (Element Test Planned) | bar: FY 2013
2014
| FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019
SM-3 Blk IIA PS Critical Design Review (CDR) | bar: FY 2013
SM-3 Blk IIA SYS/KW Critical Design Review (CDR) | bar: FY 2013
Restrained Level Firing (Element Test Complete) | bar: FY 2013
2015
| FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 | FY 2019 | FY 2020
MD40 Program-Wide Support (Planned Activity) | FY 2014: Q1-4; FY 2015: Q1-4; FY 2016: Q1-4; FY 2017: Q1-4